## Evidence_Matrix
Paper ID | Authors | Year | Title | Journal | DOI | OA licence (per README; not re-verified) | Country / context | Method (as read) | Probability / impact method | Risk matrix | Delay / value distribution | Monte Carlo (iterations) | Dependency modelling | EMV / cost | Risk response | AI method | Decision support | Key finding | Relevance to proposed system | Evidence strength (my judgement)
R01 | Yaseen, Ali, Salih, Al-Ansari | 2020 | Prediction of Risk Delay in Construction Projects Using a Hybrid AI Model | Sustainability 12(4):1514 | 10.3390/su12041514 | CC BY 3.0 | NC | Questionnaire + 15 expert interviews; RF-GA classifier trained on past projects | 5-pt Likert mapped to probability 0.1/0.3/0.5/0.7/0.9 and impact 0.05/0.1/0.2/0.4/0.8 (Table in paper) | Probability x impact scale used (matrix size NC) | No (delay classified into 3 levels) | No | No | No | No | RF-GA; accuracy 91.67%, kappa 87% | No | Hybrid RF-GA beats plain RF for delay-level classification | Source of an explicit Likert->numeric probability/impact mapping; ML needs data we lack | Medium
R02 | Araujo-Rey, Sebastian | 2021 | Causes of Delays in Industrial Construction Projects through Planning and Statistical Computing | Sustainability 13(7):3975 | 10.3390/su13073975 | CC BY 3.0 | Industrial construction (authors Spain; project data hypothetical) | Statistical analysis of hypothetical-but-realistic planning data | NR | No | No | No | No | No | No | No | No | Delays linked to activity/component structure via statistics; data are SIMULATED | Low: shows activity-level delay attribution, but synthetic data | Low
R04 | Zorrilla, Seijo, Arenal, Mena | 2026 | AI-Driven Decision Support System for Proactive Risk Management in Construction Projects | Intelligent Infrastructure and Construction 2(2):4 (README name; prompt says 'International Infrastructure Construction' - verify) | 10.3390/iic2020004 | CC BY 3.0 | Spain (FCC Construccion dataset) | Clustering, ensemble anomaly detection, XAI on BPM document dataset | NR | No | No | No | No | No | No | ML + XAI (3 decision rules); F1=0.73 bottleneck detection; 6% anomalies | Yes (risk detection) | Explainable ML surfaces bottlenecks from document workflow data | Recent AI-DSS architecture reference; detects risk, does not simulate delay or evaluate responses | Medium
R05 | Ivanovic et al. | 2022 | Detection and In-Depth Analysis of Causes of Delay: ML and Expert Knowledge (DREAM) | Sustainability 14(22):14927 | 10.3390/su142214927 | CC BY 3.0 | Serbia (single case project) | Minutes-of-meetings text mining + expert knowledge | NR | No | No | No | No | No | No | ML/text mining | No | Expert-based cause-of-delay lists show bias at single-project level (low Spearman on case) | Supports need for project-specific evidence, not only generic lists | Medium
R06 | Zagia, Kajewski, Motamedisedeh, Omrani, Rose | 2026 | Risk Maturity Level and Construction Delay Factors: ML Model | Buildings 16(16):3149 | 10.3390/buildings16163149 | CC BY 3.0 | Australia | Survey; experts rated severity, probability, composite criticality of 22 delay risks; XGBoost+SHAP | Expert-rated probability and impact -> composite criticality | Discusses P-I matrices only in background | No | No | No | No | No | XGBoost + SHAP | No | Owner's late decisions top risk at all maturity levels | Delay-risk factor list with probability/impact; Australian context, transferability to India must be assessed | Medium
R07 | Alsugair et al. | 2023 | ANN Model to Predict Final Construction Contract Duration | Applied Sciences 13(14):8078 | 10.3390/app13148078 | CC BY 3.0 | Saudi Arabia (135 projects) | ANN vs 3 linear regressions | NR | No | No | No | No | No | No | ANN; MAPE 12.22% | No | ANN MAPE 12.22%, comparable to EVM in prior study | Shows ML duration prediction needs contract-level data (n=135); not activity-level | Medium
R08 | Singh et al. | 2025 | Construction Delays Due to Weather in Cold Regions: SEM + ANN | Buildings 15(11):1916 | 10.3390/buildings15111916 | CC BY 3.0 | India (cold regions) | Literature 42 factors, 83-expert survey; EFA, SEM, ANN | Significance scores (snowfall 1.000, rainfall 0.890, low temp 0.790) | No | No | No | No | No | Mitigation strategies proposed (qualitative) | ANN | No | Weather dominates delay in Indian cold regions | INDIA-SPECIFIC evidence for weather risk; region-limited | Medium
R09 | Plebankiewicz, Wieczorek | 2020 | Prediction of Cost Overrun Risk in Construction Projects | Sustainability 12(22):9341 | 10.3390/su12229341 | CC BY 3.0 | Road-object example (country NC) | 27-rule Mamdani fuzzy inference; 3 inputs | Fuzzy linguistic | No | Triangular membership functions (fuzzy, not sampling) | No | No | Cost-overrun risk index | No | Fuzzy rule base | Rule-based DSS | Rule base validated for monotonic behaviour only | Template for a transparent rule engine; no empirical validation | Low-Medium
R10 | Ashtari, Ansari, Hassannayebi, Jeong | 2022 | Cost Overrun Risk Assessment: Bayesian Network Classifier | Buildings 12(10):1660 | 10.3390/buildings12101660 | CC BY 3.0 | Iran (Zanjan province, government projects) | Expert questionnaires; BN classifier vs NB and DT | Expert probability and impact (mean, SD table) | No | No | No | Yes (BN models interdependence) | No | No | BN (avg accuracy 78.86%) | No | Modelling risk interdependence improves accuracy; top risks: material cost, staff experience, inflation | Evidence that risks interact -> independence assumption must be tested | Medium
R11 | Chadee et al. | 2023 | Risk Evaluation of Cost Overruns in Public Sector Projects: Fuzzy Synthetic Evaluation | Buildings 13(5):1116 | 10.3390/buildings13051116 | CC BY 3.0 | Trinidad and Tobago | Questionnaire; fuzzy synthetic evaluation | Linguistic scale | No | No | No | No | No | No | No | No | Funding problems and client variations ranked top | Low direct relevance (cost, SIDS) | Low-Medium
R12 | Fitzsimmons, Lu, Hong, Brilakis | 2022 | Construction Schedule Risk Analysis - Hybrid ML Approach | ITcon 27:70-93 | 10.36680/j.itcon.2022.004 | CC BY 4.0 | UK (302 infrastructure projects, 293,263 tasks, 2007-2019) | GMM + SVM + Word2Vec on historical schedules feeding Monte Carlo | Data-derived (empirical) | No | Empirical/data-driven duration uncertainty (SVM prediction + random normal deviate) | Yes (iteration count NR here) | Task/risk-group relationships discussed | No | No | ML (SVM, Word2Vec) | Planner decision aid | Shows ML+MCS is only feasible with very large task databases | Defines the data threshold at which ML is justified; we do not have it | High
R13 | Starczyk-Kolbyk, Jedras | 2025 | Risk Matrix vs Monte Carlo on a High-Rise Office Building | Applied Sciences 15(17):9371 | 10.3390/app15179371 | CC BY 3.0 | High-rise office (country NC) | 12 risks (threats+opportunities); expert judgement + historical data | Probability ~ Uniform(min,max); value ~ Triangular(min,ML,max) | Yes; notes P x I from ordinal scales (size NC) | Triangular (value); uniform (probability) | Yes (COST outcomes; iterations NR in extract) | No (independent) | Expected cost per risk in table | Value engineering treated as opportunity | No | No | Matrix and MC largely agree; 60% certainty of no extra overrun | CLOSEST published match of matrix+MC combination; COST not schedule/activity; no mitigation simulation | Medium-High
R14 | Hendradewa | 2019 | Schedule Risk Analysis by Phases: CPM-PERT and Monte Carlo | IOP Conf. Ser. Mater. Sci. Eng. 528:012035 | 10.1088/1757-899X/528/1/012035 | CC BY 3.0 | Residential building (country NC) | CPM-PERT + MC | Three-point estimates | No | Beta (PERT), inverse-transform sampling | Yes, 10,000 replications | No | No | Risk response qualitative | No | No | Simulation gives probability of on-time completion | Simple reproducible MC/Beta-PERT baseline | Low-Medium
R15 | Senova, Tobisova, Rozenberg | 2023 | New Approaches to Project Risk Assessment Utilizing Monte Carlo | Sustainability 15(2):1006 | 10.3390/su15021006 | CC BY 3.0 | Investment projects, 12-yr equipment life (weak construction link) | Crystal Ball MC; tornado sensitivity | Risk matrix used | Yes (size NC) | NC | Yes (iterations NR) | No | NPV-type financial | No | No | No | Sensitivity via tornado graphs | Sensitivity-analysis reference; construction relevance weak | Low
R16 | Sobieraj, Metelski | 2022 | Combined Monte Carlo and Time-at-Risk: Fort Bema Housing Estate | Applied Sciences 12(3):1044 | 10.3390/app12031044 | CC BY 3.0 | Warsaw, Poland (~120,000 m2, 1999-2012) | MC + Time-at-Risk; covariance matrix between phases | NR | No | NC (PERT discussed in background) | Yes | Yes (covariance between phases) | No | No | No | No | Ordering of phases changes time-extension risk | Time-at-Risk = percentile-style schedule metric; dependency via covariance | Medium
R18 | Koulinas, Xanthopoulos, Tsilipiras, Koulouriotis | 2020 | Schedule Delay Risk Analysis with a Simulation-Based Expert System | Buildings 10(8):134 | 10.3390/buildings10080134 | CC BY 3.0 | Hotel renovation (country NC) | Risk-manager questionnaire -> total activity risk equation -> distribution assignment -> MC; compared to PERT | 5-pt Likert (VL..VH) mapped to [0,1], step 0.25; probability + time impact questions | No matrix in this paper | Uniform, PERT, triangular compared per activity type | Yes, 1000 iterations | NR | No (budget/time overrun discussed) | Reduce non-tolerable risks loop (qualitative) | No (rule/questionnaire expert system) | Yes: P(finish by deadline) | Better uncertainty expression than classic PERT under lack of data | CLOSEST published match for activity-level expert-system + MC delay; no EMV, no post-mitigation cost comparison | High
R19 | Serrano-Gomez, Munoz-Hernandez | 2019 | Monte Carlo Approach to Fuzzy AHP Risk Analysis in Renewable Energy Construction | PLOS ONE 14(6):e0215943 | 10.1371/journal.pone.0215943 | CC BY 4.0 | Spain (250 MW PV plant) | Probabilistic fuzzy AHP; expert Confidence Level parameter | Expert probability and impact with coherence weighting | Risk index | Triangular | Yes (NR) | Hierarchy only | No | No | No | Risk ranking | Confidence-level weighting of experts avoids loss from fuzzy arithmetic | Supports expert-coherence weighting and probabilistic expert input | Medium
R20 | Zavala, Flores, Santos, Cano | 2025 | Stochastic Cost Estimation with MC and Correlated Risk Variables | Future Transportation 5(4):176 | 10.3390/futuretransp5040176 | CC BY 3.0 | Peru (Oyon-Ambo highway) | @Risk MC with correlation matrices; historical price data | Fitted distributions (KS, AD tests) | No | Normal (fitted), Beta-PERT | Yes, 10,000 iterations; 5,000/10,000/50,000 compared; stable from ~10,000 | Yes (correlation matrix) | Cost distributions, confidence intervals | No | No | No | Statistics stable from ~10k iterations | Empirical basis for 10,000-iteration default and correlated sampling | Medium-High
R21 | El-Dash, Abdel-Monem, Alshaer | 2022 | Risk Factors Affecting Accuracy of Conceptual Cost Estimation (Middle East) | Buildings 12(7):950 | 10.3390/buildings12070950 | CC BY 3.0 | Middle East | Questionnaire; 51 risk factors; response plans | Survey | Risk matrix guides responses | NR | NR in extract (README: MC used) | No | Contingency | Response plans for critical risks | No | Guidelines | 51 risk factors with root causes and response plans | Source of risk-response library structure; cost-estimating not schedule | Medium
R22 | Erdenekhuu, Kocsi, Mate | 2022 | Risk-Based Analysis for Sustainable Construction by Environmental Impacts | Energies 15(18):6736 | 10.3390/en15186736 | CC BY 3.0 | Warehouse construction (authors Hungary; country of project NC) | AHP + EMV + MC on construction activities | Min/max with Bernoulli occurrence | NC | Bernoulli occurrence; time/cost min-max | Yes, 500 repetitions (convergence rationale given) | NR | YES: EMV explicit + MC | No | No | Risk ranking | Equipment breakdown most affects duration; unavailable materials most affects cost | BEST published precedent for Bernoulli occurrence + EMV + MC at activity level | Medium-High
R23 | Ariza Flores, Pinedo, Orellana, Pinedo | 2026 | Input Price Forecasting for Probabilistic Contingency (Bridge) | Buildings 16(11):2124 | 10.3390/buildings16112124 | CC BY 3.0 | Peru | Bi-GRU/Random Walk price forecasts + MC | Data-derived | No | Log-return based | Yes, 10,000 iterations | Exogenous variables | P95 contingency 3.92% (Bi-GRU) / 3.96% (RW) | No | Bi-GRU (benchmarked vs Random Walk) | Contingency | Random Walk beat Bi-GRU in 7 of 8 comparisons | Shows simple baselines can beat ML; P95 contingency reporting | Medium
R25 | Mahmoud, Ahmed, Beheiry | 2021 | Construction Cash Flow Risk Index | JRFM 14(6):269 | 10.3390/jrfm14060269 | CC BY 4.0 | NC | Literature 44 factors -> Delphi 36; 32 professionals; RII | Likert relative importance | No | No | No | No | Cash-flow index | No | No | No | Delphi consolidation 44->36 factors | Delphi/RII protocol for expert consolidation | Low-Medium
R26 | Safaeian et al. | 2022 | Risk Response Strategies with Utility Function and Budget Constraints | Buildings 12(2):98 | 10.3390/buildings12020098 | CC BY 3.0 | Iran (construction company) | Optimisation maximising utility under budget; PMBOK; 10 metaheuristics vs CPLEX | Risk weights | No | No | No | No | Budget constraint | YES: selection of response strategies | Metaheuristics (not LLM) | YES: optimisation | MFO and HHO performed best; sensitivity analyses | Precedent for constrained response selection; not activity simulation | Medium-High
R27 | Canesi, Gallo | 2024 | Risk Assessment in Sustainable Infrastructure: Mitigating Cost Overruns | Land 13(1):41 | 10.3390/land13010041 | CC BY 3.0 | Italy (SS51 variant) | ANAC matrix: 4 categories, 21 risk types | Probability x cost impact | Yes (ANAC based) | No | No | No | Forecast overrun 7.53% vs actual within 1.34% | No | No | No | Ex-ante 7.53% overrun forecast, 1.34% from outcome | Rare case with ex-post check of a matrix-based estimate (cost) | Medium
R28 | Merisalu, Sundell, Rosen | 2021 | Risk-Based Cost-Benefit Analysis for Hydrogeological Risks in Underground Construction | Geosciences 11(2):82 | 10.3390/geosciences11020082 | CC BY 3.0 | Underground construction (country NC) | ISO-aligned framework; probabilistic cause-effect chain; expert elicitation + models; CBA | Elicited probabilities | No | Probabilistic | Probabilistic (NR) | Cause-effect chain | Monetised consequences; CBA | YES: risk-reducing measures valued by benefit vs cost | No | YES: CBA | Framework supports updating with new knowledge | Template for pre/post-mitigation expected-cost comparison | Medium-High
R29 | Senic, Ivanovic, Dobrodolac, Stojadinovic | 2025 | Prioritization of Preventive Measures: MCDM in Road Infrastructure | Mathematics 13(2):278 | 10.3390/math13020278 | CC BY 3.0 | Road infrastructure (country NC) | Delphi, 37 experts; 302 measures across 56 risks; MCDM + fuzzy | Expert criteria: cost, time, complexity, probability of success | No | No | No | No | No | YES: preventive-measure ranking | No | YES: MCDM | Measures rated on 4 criteria incl. probability of success | Source of a mitigation-attribute schema; effect on risk probability not simulated | Medium
R30 | Deng, Jian | 2022 | Project Duration and Cost upon Completion: MC and Improved EVM | Buildings 12(12):2173 | 10.3390/buildings12122173 | CC BY 3.0 | Commercial expansion project (country NC) | Improved EVM + CPM + PERT + MCS | PERT three-point | No | PERT/Beta | Yes (NR) | Path logic (CPM) | Cost estimate at completion | No | No | Manager focus on critical activities | Replaces deterministic EVM estimate with range | MC replacing deterministic estimate; monitoring-stage rather than planning-stage | Medium
R31 | Koulinas, Demesouka, Sidas, Koulouriotis | 2021 | A TOPSIS-Risk Matrix and Monte Carlo Expert System for Risk Assessment in Engineering Projects | Sustainability 13(20):11277 | 10.3390/su132011277 | NC (not in folder; read via publisher-hosted PDF copy, 14 pp.) | Greece (artificial lake project, Alonissos) | Brainstorming + literature risk identification per task; TOPSIS; risk matrix probability and impact per activity; triangular activity durations; MC | Risk matrix per activity (scale size NR in extract) | Yes (per-activity matrix) | Triangular for activity durations | Yes (iteration count NR in extract); P(on-time completion) | Cascade through scheduled activities (per summary) | Budget allocation mentioned; no EMV located | Loop: if total risk unacceptable, apply mitigation actions and rerun (qualitative) | No (expert system) | Yes: proactive mitigation and budget allocation | Matrix -> triangular MC gives probability of on-time completion | DIRECT precedent for matrix + MC at activity level with a mitigate-and-rerun loop; no quantified mitigation effect, no EMV | High
R32 | Namazian, Yakhchali, Yousefi, Tamosaitiene | 2019 | Combining Monte Carlo Simulation and Bayesian Networks Methods for Assessing Completion Time of Projects under Risk | IJERPH 16(24):5024 | 10.3390/ijerph16245024 | CC BY 4.0 (per PMC page) | Gas refinery construction (20 activities, 25-110 days; 24 risks, 24 causal links) | Bayesian network for risk interactions + MC; occurrence by comparing U(0,1) draws with (conditional) probabilities | Probability scale 0.1 (rare) - 0.9 (frequent); 5-pt scales | No | Delay factor d_r = d_r0(1 + max R_rk), intensified by parent risks | Yes, 1,000 iterations; simulated delay 19.93 d vs exact 19.68 d | YES (BN causal dependencies) | No | No | No | Sensitivity: resource shortage most critical | Simulation agrees with exact BN calculation (19.93 vs 19.68 days) | Evidence that interacting risks amplify delay; template for dependency extension and MC-vs-analytical validation | High
R33 | Ghaeb, Mahjoob | 2023 | Risk Response in Construction Project: A Review Study | Journal of Engineering (Baghdad) 29(8):121-137 | 10.31026/j.eng.2023.08.09 | CC BY 4 (stated in PDF) | Review of 38 studies, 1997-2020 | Review of 38 studies (1997-2020); FULL TEXT read (targeted) | NR | NR | NR | No | NR | NR | Reviews response tools: optimisation models minimising expected makespan and cost; fuzzy AHP/TOPSIS/decision-tree response selection; case-based reasoning cycle; Ben-David & Raz (2001) model linking WBS, risks, reduction actions, overlapping action impacts and secondary risks, maximising expected risk reduction under budget | No | No | Concludes most research targets identification/assessment; response stage is essential to complete the risk process | Shows quantified action-effect + budget-constrained response models already exist (as cited by the review); response taxonomy source. Original papers still to be read | Medium (secondary source)
R34 | Ebid, Ammar, Mahdi, Hegazy | 2025 | Evaluating planning efficiency for repetitive construction projects using Monte Carlo simulation | Scientific Reports (2025) | NC | CC BY 4.0 (PMC page) | Egypt highways (3 real projects 2016-2021 for validation) | MC sampling productivity +/-50%, crews 1-10, crew cost +/-25%; 500 runs x 18 hypothetical scenarios | NR | No | Uniform-style range sampling (as summarised) | Yes, 500 per case | No | Crew cost | No | No | Planning efficiency | Productivity rate is dominant factor | Productivity-driven MC for repetitive work (relevant to masonry); page summary only, DOI not yet captured | Low-Medium (summary only)
R35 | Vilibic, Sigmund, Zavrski | 2026 | Intelligent Risk Identification in Construction Projects: A Case Study of an AI-Based Framework | Buildings 16(2):409 | 10.3390/buildings16020409 | CC BY (stated in PDF) | Croatia ('Trg pravde' judicial complex, Zagreb) | Phase-based prompting mapped to PM2 lifecycle; cross-model comparison of GPT-5, Gemini 2.5, Sonnet 4.5 on project documentation; four-layer validation (incl. cross-model triangulation) + expert questionnaire | Not quantified: identification only; notes prioritisation consistency was limited | NR | No | No | Mentions interdependencies as a limit of conventional methods | No | No (states human experts must do prioritisation and mitigation) | LLMs (GPT-5, Gemini 2.5, Sonnet 4.5) | Human-in-the-loop | LLMs broaden risk coverage but prioritisation and context are weak; authors warn of hallucinated issues | Direct precedent for the LLM risk-identification route; supports keeping numbers deterministic and labelling AI-suggested risks as unverified | Medium
Legend: NR = not reported in the paper (as far as read). NC = not checked in this pass. Evidence strength is a qualitative judgement, not a validated score. R03, R17, R24 are listed in README but PDFs are absent.

## Anchor_Verification
Anchor | Reference as verified | Local status | What was verified | Action / discrepancy
Anchor 1 | Koulinas et al. 2020, Buildings 10(8):134 | In folder as R18 | Full text read (targeted). | Matches prompt.
Anchor 2 | Koulinas, Demesouka, Sidas, Koulouriotis 2021, Sustainability 13(20):11277 | Not in folder (read via publisher-hosted PDF) | Full text extracted and read in targeted fashion: authors confirmed; risk matrix per activity + TOPSIS + triangular durations + MC; case = artificial lake, Alonissos, Greece; mitigation is a qualitative rerun loop. | Save PDF into folder as 31_Koulinas_2021. Matrix + MC at activity level is ALREADY PUBLISHED.
Anchor 3 | Namazian, Yakhchali, Yousefi, Tamosaitiene 2019, IJERPH 16(24):5024 | NOT in folder | CORRECTION: authors are Namazian, Yakhchali, Yousefi, Tamosaitiene (CC BY 4.0). Read via PMC: BN + MC, 1,000 iterations, 24 risks, 20 activities; simulated 19.93 d vs exact 19.68 d. | Save PDF as 32_Namazian_2019.
Anchor 4 | Atasoy, Erol, Kaya, Birgonul (Dikmen as lead per search snippet) 2022, Computers in Industry 141:103694 | NOT in folder | Bibliographic details from search only; author list needs confirming. Accepted manuscript exists at Reading CentAUR; ScienceDirect page is an abstract page (OA status unverified). PRICOVIS tool: predicts cost contingency from complexity factors, contract conditions and mitigation strategies, based on 11 projects. | Confirm authors and OA before citing.
Anchor 5 | Ghaeb, Mahjoob 2023, J. Eng. (Baghdad) 29(8):121-137 | NOT in folder | Full text read (targeted). CC BY 4 in PDF. 38 studies 1997-2020. Reviews optimisation and fuzzy MCDM response selection and the Ben-David & Raz (2001) action-effect model. | Done. Follow up: read Ben-David & Raz 2001 and other cited response models if accessible.
Anchor 6 | Vilibic, Sigmund, Zavrski 2026, Buildings 16(2):409 | In folder (4_Added_Anchors, R35) | Full text read (targeted). Authors confirmed: Vilibic, Sigmund, Zavrski (Univ. Zagreb). GPT-5/Gemini 2.5/Sonnet 4.5 identify risks from documentation; four-layer validation; identification only. | Done.
Anchor 7 | AI-Driven DSS for Proactive Risk Management, IIC 2(2):4, 2026 | In folder as R04 | Authors: Zorrilla, Seijo, Arenal, Mena. Prompt's journal name differs from README ('Intelligent Infrastructure and Construction'); check the PDF masthead. | Resolve journal name.
Anchor 8 | Systematic reviews | Partly located | Seen in search only, not read: Elsevier 2025 bibliometric SLR 'AI in risk management within construction projects' (S2444569X25000617); 2025 T&F 'Enhanced Monte Carlo simulation for project risk analysis: integrating cost and schedule impacts with time-shifted risks and dependency modeling'. | Add to search log; read before citing.

## Gap_Matrix
Component | Found in literature? | Representative papers | Existing method | Implication for proposed system
Risk identification (expert/questionnaire) | Yes | R01, R05, R06, R08, R25 | Literature + survey/Delphi lists | Activity-level, evidence-tagged register (literature vs expert vs AI-suggested)
Probability-impact matrix | Yes | R13, R27, R21, R15 | Ordinal P x I; sizes rarely stated | Keep continuous p alongside ordinal cell (R13 flags ordinal-product problem)
Likert -> numeric probability | Yes | R01 (0.1-0.9), R18 (0-1, step 0.25) | Scale-to-number tables, unsourced boundaries | Make mapping user-editable and labelled ASSUMPTION
Activity-level delay modelling | Partly | R18, R22 | Questionnaire/expert ranges per activity | Not novel; adopt
Monte Carlo schedule/cost | Yes | R12, R14, R16, R18, R20, R23, R30 | Triangular / PERT / empirical; 500-10,000 iterations | Default 10,000 + convergence diagnostic (R20)
Bernoulli occurrence x conditional delay | Yes (R22); partly R13 | R22, R13 | Occurrence indicator plus min-max impact | Adopt; document as candidate, test independence
Risk dependence in MC | Yes | R32 (Bayesian network), R20, R16, R10 | BN, correlation, covariance | Baseline independent + correlation sensitivity extension
Matrix + MC combined | Yes | R31 (Koulinas 2021, activity-level, duration), R13 (cost) | Matrix prioritises, MC quantifies | NOT novel: published at activity level for schedule (R31). Any contribution must lie elsewhere.
Expert system + MC | Yes | R18 | Questionnaire rules -> distributions -> MC | NOT novel at activity level
EMV + MC | Yes | R22 | EMV with MC on construction activities | Adopt; use simulated E[C] rather than only sum P x C
AI risk identification | Yes | R04, R35 (LLMs), R05 | ML/NLP on documents | LLM risk identification exists (R35) and its authors keep prioritisation/mitigation human; our design must keep numbers deterministic
Mitigation generation by AI/LLM | Partly | 2025 RAG-LLM construction SAFETY guidance from 64,740 accident cases (ScienceDirect S0926580524006629 - seen in search, abstract-level only) | - | LLM/RAG mitigation exists for safety; not located for schedule-risk responses. Read before claiming.
Response selection (optimisation / MCDM / CBA) | Yes | R26, R29, R28 | Utility+budget; MCDM; CBA | Adopt explicit criterion; avoid the word 'optimal' unless solved
Pre- vs post-mitigation simulation | Partly | R28 (CBA of measures); PRICOVIS (mitigation in contingency) | R31 qualitative rerun loop; R28 CBA; R33 cites Ben-David & Raz 2001 (actions, overlapping effects, secondary risks, expected exposure) | Not novel in concept: action-effect optimisation models exist (via R33). Activity-level schedule MC + EMV + traceable evidence still not located; read Ben-David & Raz before any claim.
End-to-end activity-level integration | Not located in reviewed set | - | - | Only a candidate contribution: integration + auditability, pending broader search

## Method_Comparison
Method | Advantages | Limitations | Data needed | Explainability | Suitability here
Rule-based / fuzzy expert system | Transparent, auditable, works without data | Rules and thresholds need sources (subjective) | Expert knowledge | High | R09, R18: suitable core
Likert/Delphi expert elicitation | Standard, cheap | Bias, scale is ordinal, R05 shows single-project bias | Experts (R29 used 37) | High | Suitable; document aggregation
Risk matrix | Familiar, quick prioritisation | Ordinal; not EMV (R13) | Low | High | Use for classification only
Monte Carlo | Full distribution, P-values | Inputs subjective without data | Three-point estimates | High | Suitable core
Bayesian network | Models interdependence (R10) | Needs CPTs/data | Moderate-high | Medium | Extension, not baseline
Fuzzy (AHP/synthetic) | Handles linguistic input | Adds complexity; R19 notes information loss | Low-moderate | Medium | Only if needed
ML (RF, ANN, SVM, XGBoost) | Accurate with large data (R12: 293k tasks) | R07 n=135; R23 baseline beat ML | Large labelled data | Low-Medium | Not justified without data
LLM + retrieval | Evidence retrieval, explanation, mitigation drafting | Hallucination, unsupported numbers | Curated papers | Medium (with citations) | Interpretation layer only; numbers stay deterministic
EMV | Simple expected loss | Ignores variance/tail; sum of P x C ignores interactions | Cost per day, probabilities | High | Report with P90 and deadline probability
Utility/budget optimisation (R26) | Explicit constraint handling | Needs utility weights | Weights | Medium | Later extension
CBA (R28) | Monetised benefit of measures | Needs consequence valuation | Cost data | Medium-High | Model for TEC = C_mit + E[C_res]
MCDM (R29) | Multi-criteria | Weights subjective | Expert ratings | Medium | Only if constraints beyond cost

## Design_Implications
Design decision | Choice | Supporting papers | Caveat
Default iterations | 10,000; provide 1k-100k options | R20 (5k/10k/50k stable ~10k), R14, R23 = 10,000; R18 = 1,000; R22 = 500 | Convergence still to be checked per run
Occurrence model | Bernoulli(p_i) per risk | R22 | Independence is an assumption (R10, R16, R20 show interaction)
Delay magnitude | Beta-PERT default, triangular alternative, uniform option | R13 triangular; R14/R20 Beta-PERT; R18 compares three | R18 says PERT has thinner tails; choice must be user-visible
Probability handling | Store continuous p; derive ordinal class; label source | R01, R18 mappings; R13 caution on ordinal products | Mapping boundaries are assumptions, not findings
Matrix role | Classification only | R13 | Matrix score is not EMV
Decision criterion | Minimum expected total cost SUBJECT TO P(T>deadline) limit (user-set) | R26 constraint idea; R28 CBA | Threshold is USER INPUT REQUIRED
AI role | Retrieval, risk explanation, mitigation drafting with citations | R04, R05 | No calibrated confidence numbers; no invented probabilities
ML | Not used | R12 (needs ~293k tasks), R07, R23 | Revisit only if activity data appear
India evidence | Only R08 in folder is India-specific; masonry-productivity Indian papers surfaced in search but are not yet read or licence-checked | R08 | Do not import foreign probabilities as Indian values
Activity choice: brick masonry | Model as repetitive productivity-driven activity: baseline = quantity / (crew x productivity); risk delays added on top | R34 (productivity dominant in repetitive MC); Indian masonry-productivity studies located by search but NOT yet read | Need India-specific masonry sources with open full text; productivity ranges are USER INPUT REQUIRED
Validation of MC engine | Compare simulated E[delay] with analytic sum p_i*E[D_i] for independent risks | R32 checked simulation (19.93) against exact calculation (19.68) | Only valid under independence
Mitigation model | Represent action as (p -> p', delay distribution -> F'), plus mitigation cost and possible secondary risk | R33 (Ben-David & Raz 2001 as cited); R28 | Effect sizes are USER INPUT REQUIRED / EXPERT JUDGMENT REQUIRED
AI risk identification | Multi-model or cross-checked LLM output, tagged AI-SUGGESTED-UNVERIFIED until user/literature confirms | R35 four-layer validation | LLM output may include hallucinated risks (R35)
Masonry baseline | T0 = quantity / (crew size x productivity); productivity variability kept separate from discrete risk events | M03 (26.2 m2/day, 2-person crew, Palestine), M01 (India observation) | India productivity values: USER INPUT REQUIRED (site data or observation)
Avoid double counting | Decide whether material shortage, rework and weather are discrete events or already inside the productivity distribution | M01, M03, M04 | Otherwise delay is counted twice
Candidate masonry risk register | Material shortage, tools delay, poor planning / unrealistic scheduling, unsafe conditions / work at height, weather, rework, labour availability and skills, payment delay | M01, M03, M06, M15 | Ranks are perceptions, not probabilities; probabilities must be user/expert input
Mitigation candidates with evidence | Overtime, crew increase / crashing, buffer stock, BIM coordination | M09, M02, M12 | Effect sizes vary widely (M09); user-set

## Masonry_Productivity_Evidence
ID | Authors (as extracted) | Year | Title (short) | Journal / access statement in PDF | Country | Activity | Method / sample | Masonry-relevant values (from the paper) | Risk / delay factors reported | Use in model | Transferability to India | Caveat
M01 | Karthik, Rao | 2019 | Essential factors responsible for loss of labour productivity in building construction in India | Chulalongkorn-hosted PDF; access statement NC | India (Telangana) | Brick wall construction | Survey (RII, factor analysis) + time-and-motion study of 24 mason-helper combinations on a residential site | ~15% of time in a category of non-productive task motions; RII table: unsafe working conditions 0.809, poor planning 0.791, unrealistic scheduling 0.791, material shortages 0.777 (respondent count inferred ~44 from table rows; verify) | Material shortage and tools delay most influential at site; work characteristics, organisational characteristics, safety, workers management | INDIA-SPECIFIC risk candidates and non-productive time share for brickwork | India-specific | Single site; no m2/day output rate extracted; check what the 15% covers
M02 | AlJassmi, Abduljalil, Philip | 2023 | Towards self-recovering construction schedules (NN productivity forecasting) | J. Asian Architecture and Building Eng.; Open Access statement present | UAE | Brickwork | 1,487 working days, 132 masons; NN regression; 60-point validation; recovery via crashing / crew increase | Paper claims 98% accuracy predicting labour productivity; productivity rate values NOT extracted | Weather, working height, building size, crew size as inputs; crashing and crew increase as recovery actions | Precedent for productivity modelling and for recovery actions as mitigation on brickwork | Comparable (Gulf); not India | ML needs 1,000+ data points which we lack; recovery-action idea reusable
M03 | Mahamid | 2020 | Relationship between rework and labor productivity in building construction projects | Access statement NC | Palestine | Brick works (also plastering, ceramic) | Questionnaires + regression on 40 building projects | Brick works: mean rework cost 4.51%; mean productivity 26.2 m2/day (2-labour crew); Y = 34.36 - 1.71X (Y m2/day, X rework %), R2 = 0.78, F(1,39) = 62.71 | Rework as productivity driver | Quantified rework->productivity slope (comparable-context reference only) | Comparable developing country; NOT India | Mean over 40 projects, not a distribution; no support outside observed rework range
M04 | Mahamid | 2022 | Relationship between delay and productivity in construction projects | IJAAS 9(2); CC BY-NC-ND stated | Saudi Arabia | Ceramic and brick works | Questionnaire; regression on 34 building projects; 14 time-overrun factors, 13 productivity factors | Strong correlation between delay and labour productivity reported (coefficients not extracted) | Delay and productivity factors ranked | Supports productivity -> time overrun link | Comparable | Correlation, not causation
M05 | Sheikh, Ullah, Ayub, Thaheem | 2017 | Labor productivity assessment using activity analysis, semi high-rise buildings, Pakistan | Chulalongkorn-hosted; access NC | Pakistan | Block masonry, plastering, formwork, steel fixing, concrete | Activity analysis on five projects | ~35% direct work, 37% support work, 28% delay work (all trades pooled) | Delay-time share | Benchmark of delay share of working time | Comparable South Asia | Not masonry-specific
M06 | Dixit, Mandal, Thanikal, Saurabh | NC | Significant factors affecting construction productivity using RII, Indian construction industry | Open access / Creative Commons statement present; year NC | India | General (cites bricklaying) | Questionnaire, 201 valid responses (32% response rate), reliability >0.95 | Top factors: availability of resources, contractual disputes, scope clarity, design capability, frequent design changes; a cited study reports 40% unproductive time in bricklaying (secondary citation) | Resource availability, design changes | INDIA-SPECIFIC factor ranking | India-specific | 40% figure is a citation, not a primary finding
M07 | Gupta, Hasan, Jain, Jha | 2018 | Site amenities and workers' welfare factors, Indian construction projects | ASCE; open-access status NOT stated in PDF | India | General workforce | Factor analysis, 151 responses, 38 attributes -> 8 factors | None masonry-specific | Health/medical, site services, camps, hygiene, leave, welfare, remuneration, accommodation | Labour availability / attendance rationale | India-specific | ASCE: check licence before quoting at length
M08 | Gurmu, Ongkowijoyo | 2020 | Predicting construction labor productivity from HRM practices | ASCE; access NOT stated in PDF | NC | Multistory buildings | Logistic regression, 39 contractors (2011-2016) | None masonry-specific | Project delay linked with lower productivity | Background only | NC | ASCE: check licence
M09 | Lendra, Resnawan, Nuswantoro, Andi | 2026 | Impact of overtime on construction labor productivity (work sampling) | Acadlore; CC BY 4.0 | Indonesia | Plastering, skim coat; lightweight brick wall | 1,296 observations over 6 days, five-minute rating | Plastering LUR fell ~1%, skim coat ~6%; lightweight brick wall productivity increased by 185%, 32%, 22% (as stated) | Overtime as acceleration action | Overtime effect is context-dependent: mitigation effect must be user-set | Comparable | Six-day sample; large brick-wall gains need context check
M10 | (first author surname truncated in extract) | 2023 | Meta-analysis of factors affecting construction labour productivity, Middle East | J. Constr. Developing Countries 28(1); CC BY | Middle East | General | Ten studies meta-analysed | None masonry-specific | Factor list with quantitative data from 10 studies | Factor cross-check | Comparable | Region-specific
M11 | Elsaid, Albasyouni | 2025 | Impact of infection rate on resource productivity (COVID-19) | Licence statement NC | Egypt / UK affiliations | Model includes masonry crews | Simulation model, e.g. 2 crews for masonry | Crew counts only; no rates extracted | Pandemic-driven labour reduction | Labour-availability shock as a scenario | Comparable | Scenario model, not empirical
M12 | Bakr, Elbeltagi, Tantawy | 2025 | BIM utilization to eliminate claims, risks and improve productivity | Civil Engineering Journal 11(12); open access | NC | Cites masonry labour productivity regression | Questionnaire + SEM + 2 case studies | Not extracted | BIM mitigates claim/risk/productivity factors (survey-based) | Perceived mitigation evidence | Comparable | Perception-based
M13 | Mahamid | 2021 | Effects of design quality on delay in residential construction projects | JSACE 28; Open Access | Saudi Arabia | Residential buildings | Questionnaire | None masonry-specific | Design quality drives delay | Design-documentation risk source | Comparable | Perception survey
M14 | Loekito, Dani et al. (authors truncated in extract) | 2026 | Factors influencing construction worker productivity in Indonesia | Multidisciplinary Sci. J. 8:e2026243 | Indonesia | General | 83 construction workers, RII; engineers surveyed for improvement measures | None masonry-specific | Worker-perceived factors | Worker-perspective factor list | Comparable | Author list incomplete
M15 | (authors NC) | 2021 | Study of delays in constructions, private companies in Brasilia | Open Access CC statement; year per filename | Brazil | Buildings | 24 causes, 47 professionals, RII | Top causes: rework, poor labour productivity, lack of qualified labour, unqualified labour, project changes | Same | Rework and labour productivity ranking | International | Perception survey
M16 | Van Basten, Firstyanandara, Crevits | 2026 | Risk mapping in shopping mall construction: VERA approach | Int. J. Technology 17(3) | Indonesia | Shopping mall | Delphi, FAST diagram, FMEA (RPN) | None masonry-specific | RPN-based priorities with mitigation for delay | Example of FMEA-style scoring and mitigation | International | Not activity-level
NC = not checked / not stated. Only values shown were verified in the extracted text. Nothing here yields an India-specific minimum / most-likely / maximum productivity range for brick masonry.

## Agent_Notes_Index
File (Research_Notes/) | Topic group | Entries | Evidence depth (as reported by the agent) | Key caveat
A_masonry_india.md | Masonry productivity, India delay causes, supply, labour, weather, rework | A01-A21+ | Mixed: full text, fetch-summarised, abstract only, snippet only (labelled per entry) | No peer-reviewed India brick-masonry output rate (m2/day) or spread found; snippet numbers must not be used
B_methods.md | Probability elicitation, distributions, Monte Carlo precision, sensitivity, dependency | B01-B27 + leads L01-L22 | 22 full text, 5 abstract only; leads unread | No paper calibrates the PERT lambda; no Likert-to-probability validation; no explicit double-counting treatment
C_economics_decision.md | Delay cost, EMV limits, contingency, response selection, MCDA, deadline criteria | C01-C27 + G01 | 18 full text, 9 abstract/landing page only | No Indian masonry delay-cost figure; CPWD liquidated-damages rate discrepancy unresolved; Ben-David & Raz (2001) paywalled
D_mitigation.md | Quantified mitigation effectiveness, response representation, secondary risks | D01-D37 + 7 bibliographic-only | 7 full text, 30 abstract only | Almost no transferable effect size for masonry mitigations; effects must be elicited
E_ai_layer.md | LLM/RAG, XAI, rule-based systems, governance, small-data ML | E01-E57 | Mixed (labelled per entry); E04, E07, E25 snippet only; E11, E53, E56 preprints | No construction paper found where an LLM interprets a deterministic Monte Carlo/EMV engine
F_novelty_validation.md | Novelty check, validation, datasets, reviews | F01-F68 (65 items) | E1 full/page read, E2 abstract, E3 snippet (per item) | Novelty confidence moderate; ASCE/T&F/Elsevier full texts unread; Scholar and Scopus not searched

## Prior_Art_Coverage
ID (notes F) | Item | (a) risk ID | (b) P-I matrix | (c) Bernoulli + delay MC | (d) EMV / cost | (e) mitigation + re-simulation | (f) decision rule | (g) AI / LLM | (h) provenance | Note
F01 | Prins, Kammouh, Wolfert 2022 (arXiv 2206.09823, preprint) | Y | - | Y | p | Y (P(finish in 300 d) ~30% -> ~70%) | Y | - | - | Extension of Mitigation Controller; preprint
F02 | Kammouh et al. 2021, J. Constr. Eng. Manage. (Mitigation Controller), DOI 10.1061/(asce)co.1943-7862.0002126 | p | - | Y (risk events) | Y | Y | Y | - | - | DOI confirmed via Crossref; abstract level
F03 | Hadad & Keren 2025, J. Risk Financial Manag. 18(3):160, DOI 10.3390/jrfm18030160 | Y | p | Y | Y (expected net saving) | Y (residual impact) | Y (ILP) | - | - | DOI confirmed via Crossref
F04 | Gheewala et al. 2025, Int. J. Constr. Manag., DOI 10.1080/15623599.2025.2603423 (Indian metro rail) | Y | Y | Y (3-point MC) | p | Y (agent: Rs 3.32M mitigation, 26 days saved) | p | - | - | Title/journal/year confirmed via Crossref; numbers are the agent's, abstract level
F05 | Koulinas et al. 2021, Sustainability 13(20):11277 | Y | Y | p (duration ranges) | - | p (qualitative loop) | p | - | - | Read by me in full text
F07 | Erdenekhuu et al. 2022, Energies 15(18):6736 | Y | - | Y (Bernoulli) | Y (EMV) | - | p | - | - | Read by me (targeted)
F11 | Ichsan et al. 2025, Appl. Sci. 15(13):7464, DOI 10.3390/app15137464 (Jakarta rail station, 9 critical activities) | Y | - | p (PERT, no Bernoulli seen) | - | Y (inherent vs residual risk) | - | - | - | Only activity-level pre/post precedent found; title/journal/year confirmed via Crossref
F13 | Vilibic, Sigmund, Zavrski 2026, Buildings 16(2):409 | Y | - | - | - | - | - | Y (LLM) | - | Read by me; identification only
F14/F15 | Martin, James, Chadee 2025; Erfani & Khanjar 2025 | p | ? | - | - | p (LLM advice) | - | Y | - | Abstract/title level per agent

## Mitigation_Evidence_Gaps
Mitigation measure | Quantified evidence? | Best-supported statement (as reported in notes D) | Still requires expert / user input
Buffer stock / material management | P | Only inside a bundle (D03); an optimum buffer size exists (D11) so benefit is non-monotonic | p -> p', delay reduction, carrying cost, storage-damage risk
Supplier diversification | N (not located) | - | Everything
Advance material procurement | N (direction only, D35) | - | p', delay reduction, financing cost
Crew increase / crashing | P | Congestion side effect quantified in simulation (D12); AlJassmi 2023 recovery actions | Productivity loss per added mason, cost premium, availability
Overtime / shift work | P | D09 shift-work productivity loss -11 to 17% (sign convention unclear); D07 moderate occasional overtime not significant; Lendra 2026 mixed | Local multipliers, fatigue -> rework probability
Block/AAC/prefab substitution | P (lab and simulation; AAC not located) | D04 lab +60-120% (interlocking/dry-stack); D06 prefab -34% time (NZ) | Local AAC vs clay productivity, supply reliability, cracking/rework
Training | N | - | Effect size, cost, attrition
Incentives | P | D27: incentives account for 6-26% of output variance (NOT a gain) | Productivity multiplier, incentive cost, rework trade-off
Weather protection / monsoon scheduling | N (hazard size only) | D20: one Kolkata project +5% duration, +12% cost | Residual delay after mitigation, cost
Rework / quality control | N for masonry | - | Rework probability and days per defect type
Lean / Last Planner | Y for PPC only | PPC gains reported (D01 37.5->85%; D30 52.8->72.25%); PPC is reliability, not delay days | Conversion of PPC change to delay reduction
Response effect representation | Method only | D13 (overlap, secondary risk), D14 (5% residual assumed; focus-group post-response impacts, Indian refinery) | Every p', F' value

## Productivity_Model_Integration
Source ID (P1/P2/P3 notes) | Item | Integrated into app? | Where | Reason
P1-01 | Ouga, Alinaitwe, Mwesige 2020, Kampala block-laying (PRD = 0.53-0.08H+0.40P+0.36EXED, R2=0.65) | Yes | data/productivity_models.json (P1-01-ouga-kampala) | Full equation and coefficients verified in the paper's own tables; range checking implemented; usage_note added because porters are already a model input, not a crew multiplier
P1-12 / M03 | Mahamid 2020, Palestine brick-works rework model (Y=34.36-1.71X, R2=0.78) | Yes (already present) | data/productivity_models.json (M03-brick-rework) | Cross-checked independently by two agents against the same paper; consistent
P1-02 | Parthasarathy et al. 2018, India tall-building blockwork OLS (R2=0.93) | No | - | Monthly PROJECT-level quantity, confounded with tower-crane/hoist hours (VIF 14.9); not a mason/crew daily rate; agent's own verdict is 'use with strong caution'
P1-05 | Thomas & Sudhakumar 2014, Kerala masonry log-productivity regression (R2=0.794) | No | - | The paper does not print the equation; the agent RECONSTRUCTED it from a coefficients table and stated the back-transformation is not given. Shipping an unprinted, reconstructed equation as a verified model would break the no-invented-equations rule. Documented as a candidate for manual follow-up (read the original table directly) rather than auto-loaded
P1-10 | Rasool & Al-Zwainy 2016, Iraq brickwork regression (R2=0.466) | No | - | Output unit never stated in the source paper; cannot be converted or interpreted
P1-11 | Paikun et al. 2021, Indonesia light-brick wall crew model (R2=0.850) | No | - | Inputs (each crew member's effective daily working minutes) are only knowable AFTER the day worked; not usable to forecast a baseline BEFORE the activity. Also flagged by the agent: reproduction check shows internal data inconsistencies
P2 (all 18 records) | Productivity modifiers: heat/humidity, overtime, rework, weather day-count, Polish fuzzy factor model | No (documented only) | Research_Notes/P2_modifiers.md, P2_modifiers.json | Every record the agent found carries unit ambiguity, an internal inconsistency, or is a non-fitted structure (control limits, membership functions, day-count without a magnitude). Wiring a generic multiplier mechanism is a reasonable next step but was not done this pass to avoid shipping numbers the source agent itself flagged as unreliable
P3 (IS 7272, CPWD DAR) | India brick-masonry labour constants (mason/mazdoor/bhisti days per m3 or m2) | Yes | data/india_labour_norms.json; app/productivity/india_norms.py; service.india_norms(), service.india_norm_output() | Full text read from archive.org (IS 7272, BIS/CBRI) and CPWD Analysis of Rates (identical across 2007/2012/2014 editions per the agent). Exposed as a citable REFERENCE only -- converting a labour constant into a crew's output/day is the author's own derivation (paced by the mason count; support-role shortfall is flagged), clearly labelled, and never auto-applied to a case
P3 (state PWD SORs) | Odisha 2006, Tamil Nadu PWD standard data book (foundation items), ~1.4-2x higher mason-days/cum than CPWD | No | Research_Notes/P3_india_norms.md | Real cross-source spread worth knowing about, but not integrated as executable data this pass; flagged for a future 'norms vary by state' extension
P3 (measured India papers) | Karthik & Rao 2019 (Telangana, derived mean 1.65 m2/crew-hr, CV 0.43); Reddy & Chambrelin 2021 (Andhra Pradesh, 62.6-90.6% efficiency) | No | Research_Notes/P3_india_norms.md | Karthik & Rao's output figure is the AGENT's own derivation from raw time splits, not printed; Reddy & Chambrelin's printed productivity column was independently flagged as physically implausible by the same agent. Neither is safe to load as a verified model