## How it works
How Bricks-ly uses RII values from published research
What an RII is
Relative Importance Index = sum of all ratings / (highest possible rating x number of respondents). Survey respondents rate each delay factor (e.g. 1-5); the RII runs from about 0.2 to 1. A higher RII means respondents judged the factor more important.
An RII is NOT a probability and NOT a number of days of delay. It can only say which risks people consider more important than others.
Where the values come from
Sheet 'Studies' lists 11 published surveys; sheet 'RII_Data' holds every value recorded from them, as printed, with the table and page. Every factor is mapped to a library risk (only 4 unclear or group-level factors are left unmapped).
Seed studies (used by the model): RII surveys from India and Sri Lanka, closest to Indian masonry sites: M01 (India, masonry), A02 (India, masonry), M06 (India), A14 (Sri Lanka), A15 (Sri Lanka).
Validation studies (held out, never used by the model): M10 (Middle East meta-analysis of 10 surveys), M15 (Brazil), M14 (Indonesia, workers), plus A10, A21 and HAS25 with too few overlapping risks to test.
Step by step (sheet 'Seed_Calculation' does this with live formulas)
1. Map each factor to one of the tool's library risks (38 risks in 11 categories, built from every factor in the studies). Direct = names the same cause (e.g. 'Material shortages' -> R-MAT). Related = overlaps but is broader, narrower or an outcome (e.g. 'Accidents' -> R-SAFE); Related values are shown but not used.
2. For each risk and seed study, average that study's Direct values, so one study counts once even if it lists two matching factors.
3. Seed mean RII for the risk = average across the seed studies that have a value.
4. Rank the seeded risks by seed mean RII and split them into five equal-count bands (with 30 seeded risks, six per band): top band -> class 5, ... bottom band -> class 1. Risks with no seed-study value (for example R-TRN, R-PRD, R-GOV) are not seeded.
5. In the app, a library risk with no probability or delay entered yet is placed on the 5x5 matrix at (class, class), drawn with a dashed outline and labelled 'literature seed'.
6. If a site-fact rule flags the risk (e.g. monsoon overlaps the work), its probability class goes up by one, to a maximum of 5.
7. As soon as the user enters a probability and a delay range (with a Source), the seed is replaced by those numbers.
Worked example: R-WX (rain / monsoon stoppage)
Study values: M01 0.764, A02 0.700, M06 0.657, A14 0.653
Seed mean RII = 0.6934 -> rank 24 of 30 -> class 2 -> matrix cell p2 × i2
What the validation shows (sheet 'Validation')
Spearman rank correlation between the seed order and each held-out study, over the risks both cover. Read the 'Reading' column; with only 7-9 shared risks, a result must be strong to be statistically significant.
Limits to state in the report
RII is a perception of importance, not a measured frequency or delay. Studies differ in country, project type, respondents (managers vs workers) and rating scale (1-4 vs 1-5). Several values come from research notes rather than a re-read of the PDF (column 'How the values were obtained').
Most seed mean RIIs lie within a few hundredths of each other, so the order of the middle risks is fragile. The seed is a starting point until expert-survey or site data replace it.
Colour key
Blue text = value copied from a paper. Black = formula. Green = formula that pulls from another sheet. Yellow fill = a judgement you may change (study role, factor mapping); the sheets recalculate.
Built by scripts/build_rii_workbook.py from data/literature_seed.json, the same file the app reads. Edit the JSON and rebuild to keep the app and this workbook in step.

## Studies
Studies the RII values come from
Role and the mapping column on RII_Data (yellow) are judgements you may change; everything else is copied from the papers.
ID | Authors | Year | Title | Venue | DOI | Country | Context | Masonry-specific? | Respondents (N) | Rating scale | Where in the paper | How the values were obtained | Role | Note
M01 | Karthik, D. & Rao, C.B.K. | 2019 | The analysis of essential factors responsible for loss of labour productivity in building construction projects in India | Engineering Journal 23(2) | 10.4186/ej.2019.23.2.55 | India (Telangana) | Multi-storey residential building, masonry wall construction | Yes | 44 | 1-5 | Table 3, p.61 | Read from the PDF (Research_Papers/5_Masonry_Productivity_Delay) | Seed | N = 44 from the response counts in Table 3 (each row sums to 44).
A02 | Ponmalar, Aravindraj & Nandhini | 2018 | Study on factors influencing labour productivity in residential buildings in Indian scenario | IJETMR 5(2): 239-248 | 10.29121/ijetmr.v5.i2.2018.168 | India (Chennai) | Two 3-storey residential buildings, brick masonry activity | Yes | Not reported | 1-4 | Tables 1-2 and Fig. 1 | From the research notes (full text read in an earlier session); PDF not in the project folder | Seed | Low-tier journal; respondent count not reported. Payment delays printed as 775.8 on a 1000 scale.
M06 | Dixit, Mandal, Thanikal & Saurabh | 2019 | Study of significant factors affecting construction productivity using relative importance index in Indian construction industry | E3S Web of Conferences 140, 09010 | 10.1051/e3sconf/201914009010 | India | Construction industry (general), consultants, contractors, developers, academia | No | 201 | 1-5 | Table 3, p.5 | Read from the PDF (Research_Papers/5_Masonry_Productivity_Delay) | Seed | RII = total score / (5 x 201). 'Conflict of interest among team members' is printed twice with different values.
A14 | Abeysinghe & Jayathilaka | 2022 | Factors influencing the timely completion of construction projects in Sri Lanka | PLoS ONE 17(12): e0278318 | 10.1371/journal.pone.0278318 | Sri Lanka | Construction projects incl. buildings; clients, contractors, consultants | No | 163 | Not recorded | Table 2 | From the research notes (rows quoted verbatim from the PMC full text) | Seed | Only the rows quoted in the notes are listed (39 factors in the paper).
A15 | Manoharan et al. | 2022 | Labour-related factors affecting construction productivity in Sri Lankan building projects: perspectives of engineers and managers | Frontiers in Engineering and Built Environment | 10.1108/FEBE-03-2022-0009 | Sri Lanka | Building projects, 90 upper-grade contractor firms | No | 90 firms | Not recorded | Top-ranked factors | From the research notes (summary of the full text, two decimals; lower confidence) | Seed | Only the top five factors (of 32) are recorded.
M10 | Adebowale & Agumba | 2023 | A meta-analysis of factors affecting construction labour productivity in the Middle East | Journal of Construction in Developing Countries 28(1): 193-220 | 10.21315/jcdc-12-21-0192 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Meta-analysis: pooled RII ('effect summary', random model) of 35 factors | No | 10 studies | Pooled RII | Table 7, pp.210-211 | Read from the PDF (Research_Papers/5_Masonry_Productivity_Delay) | Validation | Rows Man. 20 (delays responding to requests for information, overall rank 1) and Tec. 5 (type of project) were not captured by text extraction; neither maps to a tool risk.
M15 | de Almeida, Feitoza, Carvalho, Pina, Araujo et al. | 2021 | Study of delays in constructions: a managerial point of view of private companies in Brasilia, Brazil | Gestao & Producao 28(3): e5194 | 10.1590/1806-9649-2021v28e5194 | Brazil (Brasilia) | Private building companies; directors, managers, engineers | No | 47 | 1-4 | Table 3, p.8 | Read from the PDF (Research_Papers/5_Masonry_Productivity_Delay) | Validation | RII printed as a percentage; converted to 0-1.
M14 | Loekito, Dani, Zulfikar, Triarso & Prasetyono | 2026 | Factors influencing construction worker productivity in Indonesia and strategies for improvement | Multidisciplinary Science Journal 8: e2026243 | 10.31893/multiscience.2026243 | Indonesia (East Java) | Construction WORKERS' perspective | No | 83 | 1-4 | Table 2, p.5 | Read from the PDF (Research_Papers/5_Masonry_Productivity_Delay) | Validation | Published online 2025. Decimal commas in the PDF converted to points.
A10 | Pinky Devi & Sindhu | 2025 | Delay analysis of infrastructure construction projects in India | Journal of The Institution of Engineers (India): Series A | 10.1007/s40030-025-00899-5 | India | Infrastructure (roads, bridges), NOT buildings | No | 72 | Not recorded | RII table | From the research notes (summary of the full text; lower confidence) | Validation | Only 2 tool risks overlap, too few for a rank correlation. Notes list the group 'material-related issues' as rank 1 although item values are higher; recheck the paper.
A21 | Ouansrimeang & Wisaeang | 2024 | Analyzing the critical delay factors for construction projects in the public sector using relative importance index and machine learning techniques | Journal of Infrastructure, Policy and Development 8(8): 6208 | 10.24294/jipd.v8i8.6208 | Thailand | 30 delayed public projects | No | 30 projects | Not recorded | Results section | From the research notes (full text read) | Validation | Labour issues: 0.773 in the abstract but 0.733 in the results text; 0.733 is used here.
HAS25 | Hassoon et al. | 2025 | (brickwork / housing skeleton tasks, Iraq) | Journal of Infrastructure Preservation and Resilience 6, art. 3 | 10.1186/s43065-025-00116-4 | Iraq | Brickwork and housing skeleton tasks | Yes | Not recorded | Not recorded | Abstract | From the research notes (abstract only) | Validation | Abstract gives only two values. Not in the tool's evidence store.

## RII_Data
Every RII value recorded, one row per factor as printed in the paper
Blue = copied from the paper. Green = looked up from Studies. Black = formula. Yellow = mapping judgement (Direct / Related / blank).
Study ID | Country | Role | Factor (as printed) | RII (0-1) | Rank in study | Tool risk | Mapping | Used by the model? | Note | z-score within study
M01 | India (Telangana) | Seed | Unsafe working conditions | 0.809 | 1 | R-SAFE | Direct | Yes |  | 2.2101
M01 | India (Telangana) | Seed | Poor work planning | 0.791 | 2 | R-PLAN | Direct | Yes |  | 1.5553
M01 | India (Telangana) | Seed | Unrealistic scheduling | 0.791 | 3 | R-PLAN | Direct | Yes |  | 1.5553
M01 | India (Telangana) | Seed | Little or no financial rewards | 0.777 | 4 | R-INC | Direct | Yes |  | 1.046
M01 | India (Telangana) | Seed | Material shortages | 0.777 | 5 | R-MAT | Direct | Yes |  | 1.046
M01 | India (Telangana) | Seed | Payment delay | 0.773 | 6 | R-PAY | Direct | Yes |  | 0.90043
M01 | India (Telangana) | Seed | Working at heights | 0.764 | 7 | R-SAFE | Direct | Yes |  | 0.573
M01 | India (Telangana) | Seed | Weather conditions | 0.764 | 8 | R-WX | Direct | Yes |  | 0.573
M01 | India (Telangana) | Seed | Lack of skill and experience of worker | 0.759 | 9 | R-SKILL | Direct | Yes |  | 0.3911
M01 | India (Telangana) | Seed | Poor or no supervision method | 0.759 | 10 | R-SUP | Direct | Yes |  | 0.3911
M01 | India (Telangana) | Seed | Incompetent supervisors | 0.759 | 11 | R-SUP | Direct | Yes |  | 0.3911
M01 | India (Telangana) | Seed | Accidents | 0.759 | 12 | R-ACC | Direct | Yes | an outcome of unsafe conditions, not the condition itself | 0.3911
M01 | India (Telangana) | Seed | Poor relation between labour and superintendents | 0.755 | 13 | R-COM | Related | No |  | 0.24557
M01 | India (Telangana) | Seed | Poor condition of equipment and tools | 0.75 | 14 | R-TOOL | Direct | Yes |  | 0.063667
M01 | India (Telangana) | Seed | Bad leadership skill | 0.75 | 15 | R-DIS | Direct | Yes |  | 0.063667
M01 | India (Telangana) | Seed | Working 7 days per week | 0.741 | 16 | R-OVT | Direct | Yes |  | -0.26376
M01 | India (Telangana) | Seed | Equipment and tools shortages | 0.741 | 17 | R-TOOL | Direct | Yes |  | -0.26376
M01 | India (Telangana) | Seed | Low labour morale/commitment | 0.736 | 18 | R-MOT | Direct | Yes |  | -0.44567
M01 | India (Telangana) | Seed | Rework | 0.736 | 19 | R-RWK | Direct | Yes |  | -0.44567
M01 | India (Telangana) | Seed | Lack of empowerment | 0.732 | 20 | R-MOT | Related | No |  | -0.59119
M01 | India (Telangana) | Seed | Change order during execution | 0.732 | 21 | R-DES | Direct | Yes |  | -0.59119
M01 | India (Telangana) | Seed | Low amount of pay | 0.727 | 22 | R-INC | Direct | Yes |  | -0.7731
M01 | India (Telangana) | Seed | High workforce absenteeism | 0.723 | 23 | R-LAB | Direct | Yes |  | -0.91862
M01 | India (Telangana) | Seed | Lack of labour surveillance | 0.714 | 24 | R-SUP | Direct | Yes |  | -1.246
M01 | India (Telangana) | Seed | Inadequate safety plan | 0.714 | 25 | R-SAFE | Related | No | a management cause, broader than the site condition | -1.246
M01 | India (Telangana) | Seed | Frequency of working overtime | 0.709 | 26 | R-OVT | Direct | Yes |  | -1.428
M01 | India (Telangana) | Seed | Effectiveness of management system | 0.709 | 27 | R-MGT | Direct | Yes |  | -1.428
M01 | India (Telangana) | Seed | Method of construction | 0.7 | 28 | R-MTH | Direct | Yes |  | -1.7554
A02 | India (Chennai) | Seed | Lack of experience (manpower) | 0.787 | 1 | R-SKILL | Direct | Yes | rank within Table 1 (manpower)
A02 | India (Chennai) | Seed | Absenteeism | 0.751 | 2 | R-LAB | Direct | Yes | rank within Table 1 (manpower)
A02 | India (Chennai) | Seed | Age | 0.73 |  | R-FAT | Related | No | Table 1 (manpower)
A02 | India (Chennai) | Seed | Misunderstanding among labourers | 0.68 |  | R-COM | Direct | Yes | Table 1 (manpower)
A02 | India (Chennai) | Seed | Accidents | 0.65 |  | R-ACC | Direct | Yes | Table 1; an outcome, not the condition
A02 | India (Chennai) | Seed | Personal problems | 0.61 |  | R-FAT | Direct | Yes | Table 1 (manpower)
A02 | India (Chennai) | Seed | Lack of required construction material | 0.78 | 1 | R-MAT | Direct | Yes | rank within Table 2 (resources)
A02 | India (Chennai) | Seed | Lack of tools/equipment | 0.76 |  | R-TOOL | Direct | Yes | Table 2 (resources)
A02 | India (Chennai) | Seed | Poor site condition | 0.751 |  | R-SITE | Direct | Yes | Table 2 (resources)
A02 | India (Chennai) | Seed | Material storage location | 0.7 |  | R-STO | Direct | Yes | Table 2 (resources)
A02 | India (Chennai) | Seed | Increase in price of material | 0.55 | 9 | R-PRC | Direct | Yes | rank within Table 2 (resources)
A02 | India (Chennai) | Seed | Payment delays | 0.7758 |  | R-PAY | Direct | Yes | Fig. 1, printed as 775.8 on a 1000 scale
A02 | India (Chennai) | Seed | Weather condition | 0.7 | 3 | R-WX | Direct | Yes | Fig. 1, printed as 700 on a 1000 scale; rank within Fig. 1
A02 | India (Chennai) | Seed | Shortage of water | 0.65 | 5 | R-WAT | Direct | Yes | Fig. 1; water is a mortar input but not brick/block supply
M06 | India | Seed | Availability of resources | 0.80199 | 1 | R-MAT | Related | No | covers material, labour and equipment together | 1.5873
M06 | India | Seed | Contractual disputes | 0.799 | 2 | R-CTR | Direct | Yes |  | 1.5272
M06 | India | Seed | Scope clarity of the project | 0.79005 | 3 | R-SCP | Direct | Yes |  | 1.3469
M06 | India | Seed | Design capability and frequent design changes | 0.78507 | 4 | R-DES | Direct | Yes |  | 1.2467
M06 | India | Seed | Rework | 0.77612 | 5 | R-RWK | Direct | Yes |  | 1.0664
M06 | India | Seed | Coordination between all stakeholders | 0.77413 | 6 | R-MGT | Direct | Yes |  | 1.0263
M06 | India | Seed | Project manager's authority to take financial decisions and select key team members | 0.77214 | 7 | R-MGT | Related | No |  | 0.98625
M06 | India | Seed | Timely payment of completed works | 0.77114 | 8 | R-PAY | Direct | Yes |  | 0.96622
M06 | India | Seed | Site clearance/availability | 0.77114 | 9 | R-SITE | Direct | Yes |  | 0.96622
M06 | India | Seed | Ability to handle the crisis by the PM | 0.77114 | 10 | R-MGT | Related | No |  | 0.96622
M06 | India | Seed | Use of inappropriate planning tools and techniques | 0.76318 | 11 | R-PLAN | Direct | Yes |  | 0.80594
M06 | India | Seed | Quality | 0.75423 | 12 | R-QLT | Related | No |  | 0.62562
M06 | India | Seed | Leadership qualities | 0.75224 | 13 | R-DIS | Related | No |  | 0.58555
M06 | India | Seed | Top management support to PM | 0.75224 | 14 | R-MGT | Related | No |  | 0.58555
M06 | India | Seed | Human resource and labour strike | 0.74925 | 15 | R-STR | Direct | Yes | strikes are narrower than absenteeism/shortage | 0.52544
M06 | India | Seed | Cost | 0.74428 | 16 | R-CST | Direct | Yes |  | 0.42527
M06 | India | Seed | Project coordination meetings | 0.7403 | 17 | R-MGT | Direct | Yes |  | 0.34513
M06 | India | Seed | Inadequate project formulation in the beginning | 0.73831 | 18 | R-SCP | Direct | Yes |  | 0.30503
M06 | India | Seed | Obsolete construction equipment, methods and technology | 0.73831 | 19 | R-TOOL | Related | No | includes methods and technology | 0.30503
M06 | India | Seed | Conflict of interest among team members | 0.73731 | 20 | R-CTR | Related | No | printed twice in the paper | 0.285
M06 | India | Seed | Customer/client satisfaction | 0.73035 | 21 | R-CLI | Related | No |  | 0.14475
M06 | India | Seed | Conflict of interest among team members (second entry) | 0.73035 | 22 | R-CTR | Related | No | printed twice in the paper | 0.14475
M06 | India | Seed | Availability of training and development for enhancing skills | 0.72736 | 23 | R-SKILL | Related | No | training availability, not labour skill itself | 0.084648
M06 | India | Seed | Selection of PM with proven track record | 0.72438 | 24 | R-MGT | Related | No |  | 0.024542
M06 | India | Seed | Supply chain | 0.7005 | 25 | R-MAT | Related | No | broader than material shortage | -0.4563
M06 | India | Seed | Willingness to adopt change | 0.7005 | 26 | R-MGT | Related | No |  | -0.4563
M06 | India | Seed | Claim genuineness | 0.69453 | 27 | R-CTR | Direct | Yes |  | -0.57653
M06 | India | Seed | Regular budget update | 0.69254 | 28 | R-CST | Direct | Yes |  | -0.6166
M06 | India | Seed | Social skills of key team managers | 0.69154 | 29 | R-COM | Related | No |  | -0.63664
M06 | India | Seed | Working hours | 0.68756 | 30 | R-OVT | Direct | Yes |  | -0.71678
M06 | India | Seed | Developing and maintaining a short and informal line of communication | 0.67861 | 31 | R-COM | Direct | Yes |  | -0.8971
M06 | India | Seed | Urgency emphasized by the owner while issuing tender | 0.67363 | 32 | R-CLI | Related | No |  | -0.99727
M06 | India | Seed | Ability to delegate authority | 0.66965 | 33 | R-MGT | Related | No |  | -1.0774
M06 | India | Seed | Political and economic environment | 0.66567 | 34 | R-ECO | Direct | Yes |  | -1.1576
M06 | India | Seed | Exceptional difference between client and architect | 0.66567 | 35 | R-CTR | Related | No |  | -1.1576
M06 | India | Seed | Interpersonal skills | 0.66269 | 36 | R-COM | Related | No |  | -1.2177
M06 | India | Seed | Climate conditions | 0.65672 | 37 | R-WX | Direct | Yes |  | -1.3379
M06 | India | Seed | Interest and inflation rates | 0.65672 | 38 | R-ECO | Direct | Yes |  | -1.3379
M06 | India | Seed | Availability of accurate historical information | 0.64179 | 39 | R-SCP | Related | No |  | -1.6384
M06 | India | Seed | Social environment | 0.59403 | 40 | R-SOC | Direct | Yes |  | -2.6001
A14 | Sri Lanka | Seed | Shortage of skilled subcontractors/suppliers | 0.8294 | 1 | R-MAT | Related | No | suppliers and subcontractors together
A14 | Sri Lanka | Seed | Shortage of labourers (skilled, semi-skilled, unskilled) | 0.8245 | 2 | R-LAB | Direct | Yes
A14 | Sri Lanka | Seed | Delay of delivering materials to the site | 0.8098 | 4 | R-MAT | Direct | Yes
A14 | Sri Lanka | Seed | Fluctuation of material prices in the market | 0.789 | 6 | R-PRC | Direct | Yes
A14 | Sri Lanka | Seed | Bad weather conditions | 0.6528 | 30 | R-WX | Direct | Yes
A15 | Sri Lanka | Seed | Skills shortage | 0.82 | 1 | R-SKILL | Direct | Yes
A15 | Sri Lanka | Seed | Lack of thinking abilities | 0.81 | 2 | R-SKILL | Related | No
A15 | Sri Lanka | Seed | Lack of work experience | 0.8 | 3 | R-SKILL | Direct | Yes
A15 | Sri Lanka | Seed | Lack of knowledge in construction works | 0.79 | 4 | R-SKILL | Direct | Yes
A15 | Sri Lanka | Seed | Poor labour discipline | 0.79 | 5 | R-DIS | Direct | Yes
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Inadequate workers' supervision | 0.816 | 2 | R-SUP | Direct | No |  | 1.4008
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | A shortage of skilled labour | 0.801 | 3 | R-SKILL | Direct | No |  | 1.2095
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Extent of change orders | 0.793 | 4 | R-DES | Direct | No |  | 1.1075
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Clarity of technical specifications | 0.791 | 5 | R-DES | Related | No | specification clarity, not drawings or changes | 1.082
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Coordination among design disciplines | 0.785 | 6 | R-DES | Related | No |  | 1.0055
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Lack of incentive schemes | 0.783 | 7 | R-INC | Direct | No |  | 0.98
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Economic conditions | 0.778 | 8 | R-ECO | Direct | No |  | 0.91623
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Material shortage at project site | 0.775 | 9 | R-MAT | Direct | No |  | 0.87798
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Proportion of work subcontracted | 0.761 | 10 | R-SUB | Direct | No |  | 0.69944
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Rework | 0.761 | 10 | R-RWK | Direct | No |  | 0.69944
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Quality and availability of drawings | 0.758 | 12 | R-DES | Direct | No |  | 0.66119
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Payment delay | 0.751 | 13 | R-PAY | Direct | No |  | 0.57192
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Remuneration scale | 0.738 | 14 | R-INC | Direct | No |  | 0.40614
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Stringent inspections | 0.732 | 15 | R-QLT | Direct | No |  | 0.32963
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Physical fatigue | 0.723 | 16 | R-FAT | Direct | No |  | 0.21486
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Inclement weather conditions | 0.715 | 17 | R-WX | Direct | No |  | 0.11284
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Poor workers' motivation | 0.709 | 18 | R-MOT | Direct | No |  | 0.036325
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Unrealistic deadline for project completion | 0.698 | 19 | R-PLAN | Direct | No |  | -0.10395
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Government policies | 0.698 | 19 | R-GOV | Direct | No |  | -0.10395
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Poor site management | 0.696 | 21 | R-PLAN | Related | No | management in general, not planning | -0.12946
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Working overtime | 0.696 | 21 | R-OVT | Direct | No |  | -0.12946
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Unavailability of suitable tools and equipment | 0.691 | 23 | R-TOOL | Direct | No |  | -0.19322
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Problem of communication | 0.682 | 24 | R-COM | Direct | No |  | -0.30799
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Unsuitability of storage location | 0.68 | 25 | R-STO | Direct | No |  | -0.33349
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Design complexity | 0.668 | 26 | R-MTH | Direct | No |  | -0.48652
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Construction method | 0.666 | 27 | R-MTH | Direct | No |  | -0.51202
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Absenteeism | 0.66 | 28 | R-LAB | Direct | No |  | -0.58854
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Working within a confined space | 0.659 | 29 | R-SITE | Related | No |  | -0.60129
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Inspection delay | 0.638 | 30 | R-QLT | Direct | No |  | -0.86909
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Accident | 0.632 | 31 | R-ACC | Direct | No | an outcome, not the condition | -0.9456
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Lack of labour recognition programmes | 0.555 | 33 | R-MOT | Related | No |  | -1.9275
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Project location | 0.555 | 33 | R-SITE | Related | No |  | -1.9275
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam) | Validation | Inadequate training | 0.459 | 35 | R-TRN | Direct | No |  | -3.1518
M15 | Brazil (Brasilia) | Validation | Rework | 0.75 | 1 | R-RWK | Direct | No |  | 1.4373
M15 | Brazil (Brasilia) | Validation | Low labor productivity | 0.73 | 2 | R-PRD | Direct | No |  | 1.2541
M15 | Brazil (Brasilia) | Validation | Lack of skilled labor | 0.725 | 3 | R-SKILL | Direct | No |  | 1.2083
M15 | Brazil (Brasilia) | Validation | Low qualification of labor | 0.705 | 4 | R-SKILL | Direct | No |  | 1.0251
M15 | Brazil (Brasilia) | Validation | Modifications to the project | 0.695 | 5 | R-DES | Direct | No |  | 0.93352
M15 | Brazil (Brasilia) | Validation | Failure to manage deadlines | 0.69 | 6 | R-PLAN | Related | No | deadline control rather than planning | 0.88772
M15 | Brazil (Brasilia) | Validation | Poor specification or lack of definition of the project | 0.69 | 6 | R-DES | Direct | No |  | 0.88772
M15 | Brazil (Brasilia) | Validation | Incompatibility of projects | 0.67 | 8 | R-DES | Related | No | clashes between design disciplines | 0.70453
M15 | Brazil (Brasilia) | Validation | Poor qualification in the contractor's technical staff | 0.65 | 9 | R-MGT | Related | No |  | 0.52134
M15 | Brazil (Brasilia) | Validation | Delay in delivery of material | 0.65 | 9 | R-MAT | Direct | No |  | 0.52134
M15 | Brazil (Brasilia) | Validation | Unrealistic schedule | 0.64 | 11 | R-PLAN | Direct | No |  | 0.42974
M15 | Brazil (Brasilia) | Validation | Timing failures due to overestimation of productivity | 0.63 | 12 | R-PLAN | Related | No | an estimating error | 0.33814
M15 | Brazil (Brasilia) | Validation | Delay in ordering materials | 0.615 | 13 | R-MAT | Direct | No |  | 0.20075
M15 | Brazil (Brasilia) | Validation | Conflict between parties (contractor and contractor) | 0.61 | 14 | R-CTR | Direct | No |  | 0.15495
M15 | Brazil (Brasilia) | Validation | Delay in delivery of material at the front of service (site handling) | 0.59 | 15 | R-MAT | Related | No | on-site handling, not supply | -0.028242
M15 | Brazil (Brasilia) | Validation | Delay in the mobilization of the work | 0.52 | 16 | R-MGT | Direct | No |  | -0.66942
M15 | Brazil (Brasilia) | Validation | Low efficiency and productivity of equipment | 0.51 | 17 | R-TOOL | Related | No | equipment output, not availability | -0.76102
M15 | Brazil (Brasilia) | Validation | Delay for defective material | 0.485 | 18 | R-DEF | Direct | No | a quality problem | -0.99001
M15 | Brazil (Brasilia) | Validation | Effects of climate on construction (heat, rain) | 0.475 | 19 | R-WX | Direct | No |  | -1.0816
M15 | Brazil (Brasilia) | Validation | Equipment shortage | 0.455 | 20 | R-TOOL | Direct | No |  | -1.2648
M15 | Brazil (Brasilia) | Validation | Accident during construction | 0.455 | 20 | R-ACC | Direct | No | an outcome, not the condition | -1.2648
M15 | Brazil (Brasilia) | Validation | Complexity of the project | 0.444 | 22 | R-MTH | Direct | No |  | -1.3656
M15 | Brazil (Brasilia) | Validation | Scarcity of building materials on the market | 0.435 | 23 | R-MAT | Direct | No |  | -1.448
M15 | Brazil (Brasilia) | Validation | Equipment defects | 0.415 | 24 | R-TOOL | Direct | No |  | -1.6312
M14 | Indonesia (East Java) | Validation | Low salary | 0.735 | 1 | R-INC | Direct | No |  | 1.3831
M14 | Indonesia (East Java) | Validation | Lack of supervision | 0.72 | 2 | R-SUP | Direct | No |  | 1.2434
M14 | Indonesia (East Java) | Validation | No incentives | 0.716 | 3 | R-INC | Direct | No |  | 1.2061
M14 | Indonesia (East Java) | Validation | Late payment | 0.716 | 4 | R-PAY | Direct | No |  | 1.2061
M14 | Indonesia (East Java) | Validation | Personal problems | 0.711 | 5 | R-FAT | Direct | No |  | 1.1595
M14 | Indonesia (East Java) | Validation | Changing jobs | 0.701 | 6 | R-MOT | Related | No |  | 1.0663
M14 | Indonesia (East Java) | Validation | Inadequate tools | 0.689 | 7 | R-TOOL | Direct | No |  | 0.95451
M14 | Indonesia (East Java) | Validation | Project scale | 0.66 | 8 | R-MTH | Related | No |  | 0.68428
M14 | Indonesia (East Java) | Validation | Types of work contracts | 0.66 | 9 | R-SUB | Direct | No |  | 0.68428
M14 | Indonesia (East Java) | Validation | Weather | 0.643 | 10 | R-WX | Direct | No |  | 0.52587
M14 | Indonesia (East Java) | Validation | Fatigue | 0.612 | 11 | R-FAT | Direct | No |  | 0.23701
M14 | Indonesia (East Java) | Validation | No consumption | 0.598 | 12 |  |  | No |  | 0.10655
M14 | Indonesia (East Java) | Validation | Lack of skills | 0.523 | 13 | R-SKILL | Direct | No |  | -0.59231
M14 | Indonesia (East Java) | Validation | Poor communication | 0.518 | 14 | R-COM | Direct | No |  | -0.6389
M14 | Indonesia (East Java) | Validation | Late material | 0.508 | 15 | R-MAT | Direct | No |  | -0.73209
M14 | Indonesia (East Java) | Validation | Project location | 0.508 | 16 | R-SITE | Related | No |  | -0.73209
M14 | Indonesia (East Java) | Validation | Job scheduling | 0.504 | 17 | R-PLAN | Related | No | scheduling in general | -0.76936
M14 | Indonesia (East Java) | Validation | Work method | 0.504 | 18 | R-MTH | Direct | No |  | -0.76936
M14 | Indonesia (East Java) | Validation | Compressed time | 0.475 | 19 | R-PLAN | Direct | No |  | -1.0396
M14 | Indonesia (East Java) | Validation | Worker dissatisfaction | 0.46 | 20 | R-MOT | Direct | No |  | -1.1794
M14 | Indonesia (East Java) | Validation | Inadequate safety | 0.46 | 21 | R-SAFE | Direct | No |  | -1.1794
M14 | Indonesia (East Java) | Validation | Lack of motivation | 0.458 | 22 | R-MOT | Direct | No |  | -1.198
M14 | Indonesia (East Java) | Validation | The owner/supervisor cannot decide | 0.412 | 23 | R-CLI | Direct | No |  | -1.6266
A10 | India | Validation | Late material deliveries | 0.652 |  | R-MAT | Direct | No
A10 | India | Validation | Material shortages | 0.619 |  | R-MAT | Direct | No
A10 | India | Validation | Weather conditions (external) | 0.616 |  | R-WX | Direct | No
A10 | India | Validation | Material-related issues (group) | 0.562 | 1 |  |  | No | factor group, not an item
A10 | India | Validation | Construction-site factors (group) | 0.555 |  |  |  | No | factor group, not an item
A10 | India | Validation | Contractor-related (group) | 0.506 |  |  |  | No | factor group, not an item
A21 | Thailand | Validation | Contractor financial issues | 0.777 | 1 | R-FIN | Direct | No | the contractor's own finances, not late payment to it
A21 | Thailand | Validation | Labour issues (shortage during harvest season or festivals) | 0.733 | 2 | R-LAB | Direct | No | 0.773 in the abstract, 0.733 in the results text
HAS25 | Iraq | Validation | Planning | 0.874 |  | R-PLAN | Direct | No
HAS25 | Iraq | Validation | Team size | 0.856 |  | R-LAB | Related | No | crew size, not absenteeism

## Seed_Calculation
Literature seed: how the model turns RII values into a place on the risk matrix
Each study cell = average of that study's DIRECT values for the risk. Seed mean = average across studies. Rank -> five equal bands -> class.
Risk ID | Risk | M01 | A02 | M06 | A14 | A15 | Studies with a value | Seed mean RII | Rank | Class (1-5) | Matrix cell (p × impact) | Level
R-MAT | Brick / block / mortar material shortage or late delivery | 0.777 | 0.78 |  | 0.8098 |  | 3 | 0.78893 | 1 | 5 | p5 × i5 | Extreme
R-TOOL | Tools and equipment delay | 0.7455 | 0.76 |  |  |  | 2 | 0.75275 | 12 | 4 | p4 × i4 | Extreme
R-LAB | Labour absenteeism or shortage | 0.723 | 0.751 |  | 0.8245 |  | 3 | 0.76617 | 7 | 4 | p4 × i4 | Extreme
R-SKILL | Unskilled or unqualified labour | 0.759 | 0.787 |  |  | 0.80333 | 3 | 0.78311 | 3 | 5 | p5 × i5 | Extreme
R-PLAN | Poor planning or unrealistic scheduling | 0.791 |  | 0.76318 |  |  | 2 | 0.77709 | 4 | 5 | p5 × i5 | Extreme
R-SAFE | Unsafe conditions or work at height | 0.7865 |  |  |  |  | 1 | 0.7865 | 2 | 5 | p5 × i5 | Extreme
R-WX | Rain / monsoon stoppage | 0.764 | 0.7 | 0.65672 | 0.6528 |  | 4 | 0.69338 | 24 | 2 | p2 × i2 | Low
R-RWK | Rework due to workmanship or defects | 0.736 |  | 0.77612 |  |  | 2 | 0.75606 | 11 | 4 | p4 × i4 | Extreme
R-PAY | Payment delay | 0.773 | 0.7758 | 0.77114 |  |  | 3 | 0.77331 | 5 | 5 | p5 × i5 | Extreme
R-DES | Design changes or incomplete documentation | 0.732 |  | 0.78507 |  |  | 2 | 0.75854 | 10 | 4 | p4 × i4 | Extreme
R-SUP | Inadequate supervision or monitoring of workers | 0.744 |  |  |  |  | 1 | 0.744 | 16 | 3 | p3 × i3 | Moderate
R-MOT | Low motivation, morale or labour turnover | 0.736 |  |  |  |  | 1 | 0.736 | 17 | 3 | p3 × i3 | Moderate
R-INC | Inadequate wages or incentives | 0.752 |  |  |  |  | 1 | 0.752 | 13 | 3 | p3 × i3 | Moderate
R-OVT | Overtime and long working hours | 0.725 |  | 0.68756 |  |  | 2 | 0.70628 | 20 | 2 | p2 × i2 | Low
R-FAT | Worker fatigue, age or personal problems |  | 0.61 |  |  |  | 1 | 0.61 | 29 | 1 | p1 × i1 | Low
R-COM | Poor communication or misunderstanding on site |  | 0.68 | 0.67861 |  |  | 2 | 0.6793 | 25 | 1 | p1 × i1 | Low
R-DIS | Poor labour discipline or weak site leadership | 0.75 |  |  |  | 0.79 | 2 | 0.77 | 6 | 5 | p5 × i5 | Extreme
R-TRN | Inadequate training of workers | [5 empty] | 0 |  |  |  | not seeded
R-PRD | Low labour productivity | [5 empty] | 0 |  |  |  | not seeded
R-STR | Labour strikes or disputes |  |  | 0.74925 |  |  | 1 | 0.74925 | 14 | 3 | p3 × i3 | Moderate
R-ACC | Accidents and injuries on site | 0.759 | 0.65 |  |  |  | 2 | 0.7045 | 21 | 2 | p2 × i2 | Low
R-MGT | Poor site management and coordination | 0.709 |  | 0.75721 |  |  | 2 | 0.73311 | 18 | 3 | p3 × i3 | Moderate
R-SUB | Subcontracting and contract-type problems | [5 empty] | 0 |  |  |  | not seeded
R-CTR | Contractual disputes and claims |  |  | 0.74677 |  |  | 1 | 0.74677 | 15 | 3 | p3 × i3 | Moderate
R-SCP | Unclear scope or inadequate project formulation |  |  | 0.76418 |  |  | 1 | 0.76418 | 8 | 4 | p4 × i4 | Extreme
R-CLI | Client decision delay or pressure | [5 empty] | 0 |  |  |  | not seeded
R-CST | Cost control and budget updating problems |  |  | 0.71841 |  |  | 1 | 0.71841 | 19 | 2 | p2 × i2 | Low
R-QLT | Inspection and quality-approval delays | [5 empty] | 0 |  |  |  | not seeded
R-DEF | Defective or poor-quality material | [5 empty] | 0 |  |  |  | not seeded
R-SITE | Poor site access, clearance or conditions |  | 0.751 | 0.77114 |  |  | 2 | 0.76107 | 9 | 4 | p4 × i4 | Extreme
R-STO | Poor material storage or handling |  | 0.7 |  |  |  | 1 | 0.7 | 23 | 2 | p2 × i2 | Low
R-PRC | Material price escalation |  | 0.55 |  | 0.789 |  | 2 | 0.6695 | 26 | 1 | p1 × i1 | Low
R-WAT | Water shortage |  | 0.65 |  |  |  | 1 | 0.65 | 28 | 1 | p1 × i1 | Low
R-MTH | Construction method or design complexity | 0.7 |  |  |  |  | 1 | 0.7 | 22 | 2 | p2 × i2 | Low
R-ECO | Economic conditions, inflation or interest rates |  |  | 0.66119 |  |  | 1 | 0.66119 | 27 | 1 | p1 × i1 | Low
R-GOV | Government policies or approvals | [5 empty] | 0 |  |  |  | not seeded
R-SOC | Social or community environment |  |  | 0.59403 |  |  | 1 | 0.59403 | 30 | 1 | p1 × i1 | Low
R-FIN | Contractor financial difficulties | [5 empty] | 0 |  |  |  | not seeded
| Risks seeded (n) | 30
| Highest mean RII | 0.78893
| Lowest mean RII | 0.59403
| Spread (highest - lowest) | 0.1949
| Spread without the lowest risk | 0.17893
How to read this sheet:
1. Study columns: AVERAGEIFS over RII_Data rows with that study, that risk, mapping = Direct and role = Seed. Two direct items in one study are averaged first, so every study counts once.
2. Seed mean RII = plain average of the study columns that have a value.
3. Rank 1 = highest mean. Class = 5 - INT((rank - 1) x 5 / n), n = number of seeded risks (cell below). The ranks are cut into five bands of about n/5 risks each; with n = 30, ranks 1-6 -> class 5, 7-12 -> 4, 13-18 -> 3, 19-24 -> 2, 25-30 -> 1. Risks with no seed-study value stay unranked.
4. The class is used for BOTH axes because an RII is an importance rating, not a probability and not days of delay. Level uses the app's thresholds: score <= 5 Low, <= 10 Moderate, <= 15 High, else Extreme.
5. In the app, a site-fact rule flag raises the probability class by one (max 5), and entering your own probability and delay replaces the seed completely.
6. Caution: most mean RIIs lie within a few hundredths of each other (see the spread rows). The bands make small differences look large, so treat the seed as a weak starting order.
7. Ties: equal means are ordered by risk ID, the same rule the app uses (R-MTH and R-STO tie at 0.700).

## Validation
Validation: does the seed ranking agree with studies the model did NOT use?
Spearman rank correlation between the seed mean RII and each held-out study, over the risks both cover (direct items only).
Study | Region / respondents | Risks in common (n) | Spearman rho | t | p (two-tailed) | Reading
M10 | Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam); Meta-analysis: pooled RII ('effect summary', random model) of 35 factors | 19 | 0.2817 | 1.2105 | 0.24264 | Weak agreement, not significant
M15 | Brazil (Brasilia); Private building companies; directors, managers, engineers | 11 | 0.62727 | 2.4163 | 0.038845 | Agrees (significant at 5%)
M14 | Indonesia (East Java); Construction WORKERS' perspective | 13 | -0.18132 | -0.6115 | 0.5533 | No clear relation
M10: Adebowale & Agumba 2023 (Middle East (10 studies: Malaysia, Palestine, Kuwait, Qatar, Saudi Arabia, Egypt, Bahrain, Oman, Yemen, Vietnam))
Risk ID | Risk | Seed mean RII | Study RII (direct, averaged) | Seed rank | Study rank | Rank difference
R-MAT | Brick / block / mortar material shortage or late delivery | 0.78893 | 0.775 | 1 | 5 | -4
R-TOOL | Tools and equipment delay | 0.75275 | 0.691 | 8 | 14 | -6
R-LAB | Labour absenteeism or shortage | 0.76617 | 0.66 | 5 | 18 | -13
R-SKILL | Unskilled or unqualified labour | 0.78311 | 0.801 | 2 | 2 | 0
R-PLAN | Poor planning or unrealistic scheduling | 0.77709 | 0.698 | 3 | 12 | -9
R-WX | Rain / monsoon stoppage | 0.69338 | 0.715 | 16 | 10 | 6
R-RWK | Rework due to workmanship or defects | 0.75606 | 0.761 | 7 | 6 | 1
R-PAY | Payment delay | 0.77331 | 0.751 | 4 | 8 | -4
R-DES | Design changes or incomplete documentation | 0.75854 | 0.7755 | 6 | 4 | 2
R-SUP | Inadequate supervision or monitoring of workers | 0.744 | 0.816 | 10 | 1 | 9
R-MOT | Low motivation, morale or labour turnover | 0.736 | 0.709 | 11 | 11 | 0
R-INC | Inadequate wages or incentives | 0.752 | 0.7605 | 9 | 7 | 2
R-OVT | Overtime and long working hours | 0.70628 | 0.696 | 12 | 13 | -1
R-FAT | Worker fatigue, age or personal problems | 0.61 | 0.723 | 19 | 9 | 10
R-COM | Poor communication or misunderstanding on site | 0.6793 | 0.682 | 17 | 15 | 2
R-ACC | Accidents and injuries on site | 0.7045 | 0.632 | 13 | 19 | -6
R-STO | Poor material storage or handling | 0.7 | 0.68 | 14.5 | 16 | -1.5
R-MTH | Construction method or design complexity | 0.7 | 0.667 | 14.5 | 17 | -2.5
R-ECO | Economic conditions, inflation or interest rates | 0.66119 | 0.778 | 18 | 3 | 15
| Spearman rho (CORREL of the ranks) | 0.2817
| n (risks in common) | 19
| t = rho x SQRT((n-2)/(1-rho^2)) | 1.2105
| p-value, two-tailed (t-distribution, n-2 df) | 0.24264
M15: de Almeida, Feitoza, Carvalho, Pina, Araujo et al. 2021 (Brazil (Brasilia))
Risk ID | Risk | Seed mean RII | Study RII (direct, averaged) | Seed rank | Study rank | Rank difference
R-MAT | Brick / block / mortar material shortage or late delivery | 0.78893 | 0.56667 | 1 | 6 | -5
R-TOOL | Tools and equipment delay | 0.75275 | 0.435 | 6 | 11 | -5
R-SKILL | Unskilled or unqualified labour | 0.78311 | 0.715 | 2 | 2 | 0
R-PLAN | Poor planning or unrealistic scheduling | 0.77709 | 0.64 | 3 | 4 | -1
R-WX | Rain / monsoon stoppage | 0.69338 | 0.475 | 11 | 8 | 3
R-RWK | Rework due to workmanship or defects | 0.75606 | 0.75 | 5 | 1 | 4
R-DES | Design changes or incomplete documentation | 0.75854 | 0.6925 | 4 | 3 | 1
R-ACC | Accidents and injuries on site | 0.7045 | 0.455 | 9 | 9 | 0
R-MGT | Poor site management and coordination | 0.73311 | 0.52 | 8 | 7 | 1
R-CTR | Contractual disputes and claims | 0.74677 | 0.61 | 7 | 5 | 2
R-MTH | Construction method or design complexity | 0.7 | 0.444 | 10 | 10 | 0
| Spearman rho (CORREL of the ranks) | 0.62727
| n (risks in common) | 11
| t = rho x SQRT((n-2)/(1-rho^2)) | 2.4163
| p-value, two-tailed (t-distribution, n-2 df) | 0.038845
M14: Loekito, Dani, Zulfikar, Triarso & Prasetyono 2026 (Indonesia (East Java))
Risk ID | Risk | Seed mean RII | Study RII (direct, averaged) | Seed rank | Study rank | Rank difference
R-MAT | Brick / block / mortar material shortage or late delivery | 0.78893 | 0.508 | 1 | 9 | -8
R-TOOL | Tools and equipment delay | 0.75275 | 0.689 | 6 | 4 | 2
R-SKILL | Unskilled or unqualified labour | 0.78311 | 0.523 | 3 | 7 | -4
R-PLAN | Poor planning or unrealistic scheduling | 0.77709 | 0.475 | 4 | 11 | -7
R-SAFE | Unsafe conditions or work at height | 0.7865 | 0.46 | 2 | 12 | -10
R-WX | Rain / monsoon stoppage | 0.69338 | 0.643 | 11 | 6 | 5
R-PAY | Payment delay | 0.77331 | 0.716 | 5 | 3 | 2
R-SUP | Inadequate supervision or monitoring of workers | 0.744 | 0.72 | 8 | 2 | 6
R-MOT | Low motivation, morale or labour turnover | 0.736 | 0.459 | 9 | 13 | -4
R-INC | Inadequate wages or incentives | 0.752 | 0.7255 | 7 | 1 | 6
R-FAT | Worker fatigue, age or personal problems | 0.61 | 0.6615 | 13 | 5 | 8
R-COM | Poor communication or misunderstanding on site | 0.6793 | 0.518 | 12 | 8 | 4
R-MTH | Construction method or design complexity | 0.7 | 0.504 | 10 | 10 | 0
| Spearman rho (CORREL of the ranks) | -0.18132
| n (risks in common) | 13
| t = rho x SQRT((n-2)/(1-rho^2)) | -0.6115
| p-value, two-tailed (t-distribution, n-2 df) | 0.5533
Held-out studies not tested (fewer than 4 risks in common, too few for a rank correlation):
A10 (India): 2 risk(s) in common: R-MAT, R-WX
A21 (Thailand): 1 risk(s) in common: R-LAB
HAS25 (Iraq): 1 risk(s) in common: R-PLAN
How to read this sheet:
rho = +1: same order as the seed; 0: unrelated; -1: opposite order. The more risks two studies share, the smaller the rho needed for significance (about 0.7 to 0.8 with 7 to 9 risks, about 0.45 with 20).
M10 pools 10 surveys (mostly managers and engineers); M15 asks managers; M14 asks site WORKERS. Who answers changes the ranking, so compare like with like.
This tests the RANKING only. It cannot test probabilities or days of delay; that needs site records (see docs/Site_Data_Collection_Form.docx).

## Other_indices
Values found in the literature but NOT used (different index or group-level only)
ID | Source | Index | Values | Why not used
A11 | Soundarya et al. (2025), An investigation study on residential buildings for cost overrun, Scientific Reports, DOI 10.1038/s41598-025-95984-x (Chennai, India) | Importance index II (frequency x severity), NOT RII | Overall lag in schedule 0.71 (rank 1); rework/extra work 0.55 (2); inadequate skilled labour 0.53 (3); inadequate design/specification 0.52 (4); climatic variation 0.37 (11); hike in materials cost 0.29 (12) | Different index; mixing it with RII would compare unlike scales.
P1-23 | Karthik & Rao (2019), Identifying the significant factors affecting masonry labour productivity in India, Int. J. Construction Management 22(3): 464-472, DOI 10.1080/15623599.2019.1631978 | RII, factor-group average only | Workforce-related factors: average RII 0.784 (120 site personnel, 38 factors) | Only a group average is available (abstract); item values not read.

## Standardised
Bringing every study to one level: within-study z-scores
z = (RII - mean RII of the study's factors) / SD of the study's factors. Mean 0 and SD 1 in every study, so scale and respondent differences drop out.
Study | Treatment (judgement) | Factors (n) | Mean RII | SD | Why
M01 | Truncated | 28 | 0.74825 | 0.027487 | paper lists only the 28 factors with RII > 0.7 (of 38): the lowest are cut off, so its z-scores are distorted; used only in Analysis B
A02 | Partial | 14 | 0.70534 | 0.07072 | only some factors recorded (top-ranked or selected): z-scores would be biased, so not standardised
M06 | Complete | 40 | 0.72316 | 0.049663 | all 40 factors printed
A14 | Partial | 5 | 0.7811 | 0.073422 | only some factors recorded (top-ranked or selected): z-scores would be biased, so not standardised
A15 | Partial | 5 | 0.802 | 0.013038 | only some factors recorded (top-ranked or selected): z-scores would be biased, so not standardised
M10 | Complete | 33 | 0.70615 | 0.078417 | 33 of 35 pooled factors captured
M15 | Complete | 24 | 0.59308 | 0.10917 | all 24 factors printed
M14 | Complete | 23 | 0.58657 | 0.10732 | all 23 factors printed
A10 | Partial | 6 | 0.585 | 0.053434 | only some factors recorded (top-ranked or selected): z-scores would be biased, so not standardised
A21 | Partial | 2 | 0.755 | 0.031113 | only some factors recorded (top-ranked or selected): z-scores would be biased, so not standardised
HAS25 | Partial | 2 | 0.865 | 0.012728 | only some factors recorded (top-ranked or selected): z-scores would be biased, so not standardised
Risk score = mean z of the study's DIRECT factors for the risk. Analysis A = the four complete studies; Analysis B adds M01.
Risk | Name | M06 | M10 | M14 | M15 | M01 | Studies (A) | Pooled z (A) | Rank (A) | Studies (B) | Pooled z (B) | Rank (B)
R-MAT | Brick / block / mortar material shortage or late delivery |  | 0.87798 | -0.73209 | -0.24197 | 1.046 | 3 | -0.032026 | 16 | 4 | 0.23747 | 15
R-TOOL | Tools and equipment delay |  | -0.19322 | 0.95451 | -1.448 | -0.10005 | 3 | -0.2289 | 20 | 4 | -0.19669 | 21
R-LAB | Labour absenteeism or shortage |  | -0.58854 |  |  | -0.91862 | 1 | -0.58854 | 26 | 2 | -0.75358 | 30
R-SKILL | Unskilled or unqualified labour |  | 1.2095 | -0.59231 | 1.1167 | 0.3911 | 3 | 0.57798 | 10 | 4 | 0.53126 | 10
R-PLAN | Poor planning or unrealistic scheduling | 0.80594 | -0.10395 | -1.0396 | 0.42974 | 1.5553 | 4 | 0.023034 | 14 | 5 | 0.32949 | 13
R-SAFE | Unsafe conditions or work at height |  |  | -1.1794 |  | 1.3916 | 1 | -1.1794 | 31 | 2 | 0.10611 | 16
R-WX | Rain / monsoon stoppage | -1.3379 | 0.11284 | 0.52587 | -1.0816 | 0.573 | 4 | -0.4452 | 24 | 5 | -0.24156 | 22
R-RWK | Rework due to workmanship or defects | 1.0664 | 0.69944 |  | 1.4373 | -0.44567 | 3 | 1.0677 | 3 | 4 | 0.68937 | 8
R-PAY | Payment delay | 0.96622 | 0.57192 | 1.2061 |  | 0.90043 | 3 | 0.91475 | 7 | 4 | 0.91117 | 3
R-DES | Design changes or incomplete documentation | 1.2467 | 0.88435 |  | 0.91062 | -0.59119 | 3 | 1.0139 | 4 | 4 | 0.61263 | 9
R-SUP | Inadequate supervision or monitoring of workers |  | 1.4008 | 1.2434 |  | -0.15462 | 2 | 1.3221 | 1 | 3 | 0.82986 | 4
R-MOT | Low motivation, morale or labour turnover |  | 0.036325 | -1.1887 |  | -0.44567 | 2 | -0.57618 | 25 | 3 | -0.53267 | 26
R-INC | Inadequate wages or incentives |  | 0.69307 | 1.2946 |  | 0.13643 | 2 | 0.99385 | 5 | 3 | 0.70804 | 6
R-OVT | Overtime and long working hours | -0.71678 | -0.12946 |  |  | -0.84586 | 2 | -0.42312 | 23 | 3 | -0.56403 | 27
R-FAT | Worker fatigue, age or personal problems |  | 0.21486 | 0.69826 |  |  | 2 | 0.45656 | 12 | 2 | 0.45656 | 12
R-COM | Poor communication or misunderstanding on site | -0.8971 | -0.30799 | -0.6389 |  |  | 3 | -0.61466 | 27 | 3 | -0.61466 | 29
R-DIS | Poor labour discipline or weak site leadership |  |  |  |  | 0.063667 | 0 |  |  | 1 | 0.063667 | 17
R-TRN | Inadequate training of workers |  | -3.1518 |  |  |  | 1 | -3.1518 | 34 | 1 | -3.1518 | 35
R-PRD | Low labour productivity |  |  |  | 1.2541 |  | 1 | 1.2541 | 2 | 1 | 1.2541 | 1
R-STR | Labour strikes or disputes | 0.52544 |  |  |  |  | 1 | 0.52544 | 11 | 1 | 0.52544 | 11
R-ACC | Accidents and injuries on site |  | -0.9456 |  | -1.2648 | 0.3911 | 2 | -1.1052 | 30 | 3 | -0.60643 | 28
R-MGT | Poor site management and coordination | 0.68572 |  |  | -0.66942 | -1.428 | 2 | 0.0081527 | 15 | 3 | -0.47055 | 25
R-SUB | Subcontracting and contract-type problems |  | 0.69944 | 0.68428 |  |  | 2 | 0.69186 | 9 | 2 | 0.69186 | 7
R-CTR | Contractual disputes and claims | 0.47534 |  |  | 0.15495 |  | 2 | 0.31515 | 13 | 2 | 0.31515 | 14
R-SCP | Unclear scope or inadequate project formulation | 0.82597 |  |  |  |  | 1 | 0.82597 | 8 | 1 | 0.82597 | 5
R-CLI | Client decision delay or pressure |  |  | -1.6266 |  |  | 1 | -1.6266 | 32 | 1 | -1.6266 | 33
R-CST | Cost control and budget updating problems | -0.095669 |  |  |  |  | 1 | -0.095669 | 17 | 1 | -0.095669 | 18
R-QLT | Inspection and quality-approval delays |  | -0.26973 |  |  |  | 1 | -0.26973 | 21 | 1 | -0.26973 | 23
R-DEF | Defective or poor-quality material |  |  |  | -0.99001 |  | 1 | -0.99001 | 29 | 1 | -0.99001 | 31
R-SITE | Poor site access, clearance or conditions | 0.96622 |  |  |  |  | 1 | 0.96622 | 6 | 1 | 0.96622 | 2
R-STO | Poor material storage or handling |  | -0.33349 |  |  |  | 1 | -0.33349 | 22 | 1 | -0.33349 | 24
R-PRC | Material price escalation | [5 empty] | 0 |  |  | 0
R-WAT | Water shortage | [5 empty] | 0 |  |  | 0
R-MTH | Construction method or design complexity |  | -0.49927 | -0.76936 | -1.3656 | -1.7554 | 3 | -0.87806 | 28 | 4 | -1.0974 | 32
R-ECO | Economic conditions, inflation or interest rates | -1.2477 | 0.91623 |  |  |  | 2 | -0.16574 | 19 | 2 | -0.16574 | 20
R-GOV | Government policies or approvals |  | -0.10395 |  |  |  | 1 | -0.10395 | 18 | 1 | -0.10395 | 19
R-SOC | Social or community environment | -2.6001 |  |  |  |  | 1 | -2.6001 | 33 | 1 | -2.6001 | 34
R-FIN | Contractor financial difficulties | [5 empty] | 0 |  |  | 0
How to read this sheet:
1. Different rating scales give different RII levels (1-4 studies average about 0.59, 1-5 studies about 0.72 to 0.75). Standardising removes that, so values from different studies can be averaged.
2. Rank agreement WITHIN pairs of studies does not change under standardisation (z keeps the order inside a study); what changes is the pooled value and its uncertainty.
3. Treatment (yellow) is a judgement: only studies whose full factor list is available can be standardised honestly. Change it and the sheet recalculates.
4. Compare Pooled z (A) and (B) with the seed order on Seed_Calculation. They disagree: see docs/Statistical_Analysis_Standardised.docx for the tests (scripts/stats_standardised.py).