RESEARCH PROPOSAL

TEAM PROJECT – FRONT / APPROVAL PAGE

PROPOSED RESEARCH TITLE

“An Integrated Rule-Based Expert System, Vectorized Monte Carlo Simulation, and Expected Monetary Value Framework for Predicting and Mitigating Construction Delays”

TEAM MEMBERS

| S. No. | Name of Student | Register / Roll No. | Signature |
| --- | --- | --- | --- |
| 1 | Harshil Sachde | P2366001 |  |
| 2 | Sarang Deore | P2366007 |  |
| 3 | Omkar Moze | P2366020 |  |

| Programme / Branch | B.Tech. Civil Engineering |
| --- | --- |
| Year / Semester | Year 4 Semester 1 |
| Institution / Department | School Of Engineering, NICMAR University Pune |
| Academic Year | 2026-27 |

SUPERVISOR DETAILS

| Name of Supervisor | Dr. Shashank B. S |
| --- | --- |
| Designation | Head of Department, School of Engineering |
| Department | School of Engineering _ |

SUPERVISOR APPROVAL

I have reviewed the proposed research topic, objectives, methodology and timeline and approve the team to proceed with the proposed work, subject to appropriate modifications during the project.

| Supervisor Signature | Name | Date |
| --- | --- | --- |
|  | Dr. Shashank B. S |  |

# RESEARCH PROPOSAL

## 1. Title of Research

Proposed Title: An Integrated Rule-Based Expert System, Vectorized Monte Carlo Simulation, and Expected Monetary Value Framework for Predicting and Mitigating Construction Delays

## 2. Research Problem / Background

Construction projects are frequently affected by schedule delays and cost overruns arising from resource constraints, weather, labour productivity variation, and financial risk factors. Traditional project-control practice relies on deterministic CPM/PERT scheduling and subjective risk registers, which cannot systematically link identified risk factors to quantified schedule and cost consequences or to actionable financial mitigation strategies. While rule-based expert systems, Monte Carlo simulation, and Expected Monetary Value (EMV) analysis have each been investigated individually for construction risk management, an integrated, offline decision-support tool combining all three — a deterministic rules engine for delay-cause diagnosis, a vectorized Monte Carlo engine for probabilistic schedule-impact simulation, and an EMV-based module for recommending cost-effective mitigation actions — is not readily available to practitioners, particularly in resource-constrained and academic settings without proprietary risk-software licences. This research addresses this gap by designing an offline desktop decision-support system that predicts construction delays through rule-based reasoning, quantifies the resulting schedule risk via computationally efficient Monte Carlo simulation, and recommends risk-mitigation actions by comparing their expected monetary value, thereby supporting faster, more informed, and reproducible risk-based decision-making for construction project managers.

## 3. Research Gap

Prior literature on construction delay analysis has largely treated cause identification (via surveys, relative-importance indices, and machine-learning classifiers), schedule-risk quantification (via Monte Carlo/PERT simulation), and cost-risk mitigation (via EMV, decision-tree, and contingency-estimation methods) as separate research streams, rarely integrating them into a single computational workflow. Rule-based/expert systems for delay prediction have seldom been coupled with a vectorized Monte Carlo engine capable of efficiently simulating thousands of schedule scenarios on standard hardware, and EMV-based mitigation selection is typically presented as a standalone financial exercise disconnected from a project's simulated schedule outcomes. Moreover, existing decision-support prototypes in the literature are largely academic proofs-of-concept validated on synthetic data and are not packaged as deployable, offline software usable by practitioners without specialised risk-analysis licences (e.g., @RISK, Primavera Risk Analysis). A gap therefore exists for an integrated, open, offline framework that links deterministic delay-cause diagnosis, probabilistic schedule-impact simulation, and EMV-based financial mitigation recommendation within a single decision-support application, validated against construction-specific literature and case data.

## 4. Aim of the Study

To design, develop, and validate an offline decision-support desktop application that predicts construction delay causes using a deterministic rule-based engine, quantifies their probable impact on project schedule through a vectorized Monte Carlo simulation engine, and recommends cost-effective financial mitigation strategies using Expected Monetary Value (EMV) analysis, in order to support proactive, data-driven risk management in construction projects.

## 5. Objectives

1. To identify and formalise, from literature and case data, the key managerial, financial, and schedule risk factors that cause construction delays, and encode them as a deterministic rule base for delay-risk prediction.

2. To design and implement a vectorized (array-based) Monte Carlo simulation engine capable of efficiently simulating schedule-risk outcomes (e.g., PERT/triangular activity-duration distributions) for a project network under multiple risk scenarios.

3. To develop an Expected Monetary Value (EMV) module that evaluates candidate risk-response/mitigation strategies against their probabilistic cost and schedule impact and recommends the most cost-effective option(s).

4. To integrate the rules engine, Monte Carlo engine, and EMV module into a single offline desktop decision-support application, and validate its predictions and recommendations against literature-derived and/or case-study construction project data.

# RESEARCH PROPOSAL – METHODOLOGY & WORK PLAN

## 6. Proposed Methodology

### 6.1 Materials / Data / Study Variables

Materials / specimens / datasets / case studies:

The study will use secondary data extracted and calibrated from open-access, peer-reviewed construction-management literature (delay-cause frequency/severity indices, PERT/triangular activity-duration parameters, risk-probability and cost-impact estimates, and reported contingency/EMV outcomes), supplemented, where feasible, with an illustrative case-study construction schedule (a representative building-project WBS/network) used to demonstrate and validate the integrated system.

The tools used for this research include:

• Python – core application logic, rules engine and offline desktop program

• NumPy / Pandas – vectorized Monte Carlo simulation and data handling

• PyQt / Tkinter – offline desktop application GUI

• SciPy – probability-distribution sampling (PERT/triangular/beta) for simulation

• Matplotlib / Seaborn – visualisation of schedule-risk and EMV results

• Microsoft Excel – preparation and calibration of literature-derived input data

### 6.2 Experimental / Analytical Variables

| Category | Variables / Details |
| --- | --- |
| Independent variables | Delay-cause factors (e.g., weather, labour productivity shortfall, material availability, financial constraints, design changes); activity-duration uncertainty parameters (optimistic / most-likely / pessimistic); risk probability and cost-impact estimates for candidate mitigation strategies. |
| Dependent variables | Predicted delay-risk category (low / medium / high); simulated project-completion-time distribution; Expected Monetary Value (EMV) and ranking of candidate mitigation strategies. |
| Control / reference condition | Baseline deterministic CPM/PERT schedule with no risk factors applied (no mitigation). |
| Number of case-study scenarios | One detailed case-study project network, benchmarked against risk parameters synthesised from 30 open-access, construction-specific peer-reviewed studies. |

### 6.3 Experimental / Analytical Programme

Stage 1 – Literature review, research-gap identification, and formalisation of delay-cause rules, risk-probability/impact parameters and EMV mitigation data from open-access literature.

Stage 2 – Design and development of the deterministic rules engine (rule base and inference logic) for delay-cause/risk-level prediction.

Stage 3 – Design and vectorized implementation of the Monte Carlo schedule-simulation engine (PERT/triangular activity distributions, network-level aggregation, convergence testing).

Stage 4 – Development of the EMV-based mitigation-recommendation module, integration of all three modules into a single offline desktop application, and validation against case-study/literature data.

### 6.4 Tests / Analysis / Characterisation

| Test / Analysis | Purpose | Standard / Method |
| --- | --- | --- |
| Rule-base validation | To check that the deterministic rules engine correctly classifies delay-risk levels | Comparison against literature-reported delay-cause rankings and case outcomes; confusion-matrix / accuracy check |
| Monte Carlo convergence and sensitivity analysis | To confirm simulation stability and examine which risk factors most affect schedule outcomes | Iteration-count vs. output-variance convergence check; comparison of simulated completion-time distribution (mean, P50/P80, standard deviation) against the deterministic CPM baseline |
| EMV module validation | To verify that recommended mitigation strategies are financially and schedule-wise sound | Expected Monetary Value computation and ranking, cross-checked against literature/case-study contingency and decision-tree benchmarks |
| Integration / system testing | To confirm the end-to-end pipeline (rules engine → Monte Carlo engine → EMV module) functions correctly within the offline desktop application | Functional and user-acceptance testing (UAT) on the case-study project dataset |

### 6.5 Data Analysis

Delay-cause data extracted from literature will first be screened and coded into IF–THEN rules with associated risk-severity weights, verified for internal consistency. Activity-duration risk parameters will be modelled using PERT (beta) or triangular distributions calibrated from literature-reported optimistic/most-likely/pessimistic estimates, and the Monte Carlo engine will be run for a sufficiently large number of iterations (e.g., 10,000+), vectorized using NumPy array operations rather than iterative loops, to obtain converged probability distributions of total project duration; convergence will be checked by monitoring the stabilisation of the mean and standard deviation of simulated completion times as iteration count increases. Rule-engine outputs (delay-risk category) and Monte Carlo outputs (P50/P80 schedule dates, contingency/duration statistics) will feed the EMV module, which will compute the expected monetary value of each candidate mitigation strategy as the probability-weighted sum of its cost and schedule outcomes, ranking strategies to recommend the option with the most favourable risk-adjusted EMV. Results will be cross-validated against literature-reported delay statistics, Monte Carlo schedule-risk studies, and EMV/contingency case studies identified in the literature review, and the integrated system's outputs will be benchmarked against a deterministic (non-probabilistic) baseline to demonstrate the value added by the probabilistic and financial-decision layers.

## 7. Expected Outcomes

1. A validated, literature-calibrated rule base linking managerial, financial, and schedule risk factors to construction delay-risk categories.

2. A vectorized Monte Carlo schedule-simulation engine capable of efficiently generating probabilistic project-completion-time distributions for a construction project network.

3. An EMV-based mitigation-recommendation module that ranks candidate risk-response strategies by expected monetary value.

4. A functioning, integrated, offline desktop decision-support application combining the three modules, validated against literature/case-study data, to support construction project managers in proactive delay-risk identification and cost-effective mitigation decisions.

## 8. Proposed Timeline

| Week | Dates | Principal Work |
| --- | --- | --- |
| Apr W1 | 30 Mar – 5 Apr | Literature review on construction delay causes, risk factors and existing rule-based/expert-system approaches |
| Apr W2 | 6 – 12 Apr | Literature review on Monte Carlo/PERT schedule-risk simulation techniques in construction |
| Apr W3 | 13 – 19 Apr | Literature review on Expected Monetary Value, contingency estimation and risk-mitigation decision methods |
| Apr W4 | 20 – 26 Apr | Identification of research gap; finalisation of research objectives and system architecture (rules engine + Monte Carlo engine + EMV module) |
| May W1 | 27 Apr – 3 May | Formalisation of delay-cause factors and risk-severity weights into a deterministic rule base (IF–THEN structure) |
| May W2 | 4 – 10 May | Design of rule-engine inference logic and delay-risk classification scheme (low / medium / high) |
| May W3 | 11 – 17 May | Development and unit testing of the deterministic rules engine module in Python |
| May W4 | 18 – 24 May | Validation of rule-engine outputs against literature-reported delay-cause rankings and case data |
| Jun W1 | 25 – 31 May | Compilation of PERT/triangular activity-duration parameters and project network data from literature and the case-study project |
| Jun W2 | 1 – 7 Jun | Design of the vectorized Monte Carlo simulation engine architecture (NumPy array-based iteration structure) |
| Jun W3 | 8 – 14 Jun | Implementation of the Monte Carlo engine: activity-duration sampling and network-level schedule aggregation |
| Jun W4 | 15 – 21 Jun | Convergence and sensitivity testing of the Monte Carlo engine (iteration count vs. output stability) |
| Jul W1 | 22 – 28 Jun | Validation of the simulated completion-time distribution against the deterministic CPM baseline |
| Jul W2 | 29 Jun – 5 Jul | Compilation of risk-response/mitigation strategy data (costs, probabilities, schedule impacts) from literature |
| Jul W3 | 6 – 12 Jul | Design of the EMV module: computation of expected monetary value for candidate mitigation strategies |
| Jul W4 | 13 – 19 Jul | Implementation and unit testing of the EMV module; ranking logic for mitigation recommendations |
| Jul W5 | 20 – 26 Jul | Validation of EMV module outputs against literature/case-study contingency and decision-tree benchmarks |
| Aug W1 | 27 Jul – 2 Aug | Design of integrated system architecture and data flow (rules engine → Monte Carlo engine → EMV module) |
| Aug W2 | 3 – 9 Aug | Development of the offline desktop application shell (GUI) and integration of the rules engine module |
| Aug W3 | 10 – 16 Aug | Integration of the Monte Carlo engine into the desktop application |
| Aug W4 | 17 – 23 Aug | Integration of the EMV module into the desktop application; end-to-end pipeline testing |
| Sep W1 | 24 – 30 Aug | System-level (integration/UAT) testing of the complete decision-support application on case-study data |
| Sep W2 | 31 Aug – 6 Sep | Refinement of the user interface, input/output reporting and result-visualisation features |
| Sep W3 | 7 – 13 Sep | Application of the integrated system to the case-study project; consolidation of results |
| Sep W4 | 14 – 20 Sep | Comparison of the integrated system's outputs against deterministic and literature-reported benchmarks; discussion of findings |
| Oct W1 | 21 – 27 Sep | Sensitivity/robustness checks and identification of system limitations |
| Oct W2 | 28 Sep – 4 Oct | Preparation of construction-management implications, recommendations and conclusions |
| Oct W3 | 5 – 11 Oct | Thesis/report preparation, formatting and proofreading |
| Oct W4 | 12 – 18 Oct | Final presentation, corrections and submission |

## 9. Key References

Alsugair, A. M., Al-Gahtani, K. S., Alsanabani, N. M., Alabduljabbar, A. A., & Almohsen, A. S. (2023). Artificial neural network model to predict final construction contract duration. Applied Sciences, 13(14), 8078. https://doi.org/10.3390/app13148078

Ammar, T., Abdel-Monem, M., & El-Dash, K. (2023). Appropriate budget contingency determination for construction projects: State-of-the-art. Alexandria Engineering Journal, 78, 88–103. https://doi.org/10.1016/j.aej.2023.07.035

Araújo-Rey, C., & Sebastián, M. A. (2021). An approach to the analysis of causes of delays in industrial construction projects through planning and statistical computing. Sustainability, 13(7), 3975. https://doi.org/10.3390/su13073975

Ariza Flores, V. A., Pinedo, D., Orellana, A., & Pinedo, A. (2026). Construction input price forecasting for probabilistic contingency estimation in a road infrastructure bridge case study. Buildings, 16(11), 2124. https://doi.org/10.3390/buildings16112124

Ashtari, M. A., Ansari, R., Hassannayebi, E., & Jeong, J. (2022). Cost overrun risk assessment and prediction in construction projects: A Bayesian network classifier approach. Buildings, 12(10), 1660. https://doi.org/10.3390/buildings12101660

Canesi, R., & Gallo, B. (2024). Risk assessment in sustainable infrastructure development projects: A tool for mitigating cost overruns. Land, 13(1), 41. https://doi.org/10.3390/land13010041

Chadee, A. A., Martin, H. H., Gallage, S., Banerjee, K. S., Roopan, R., Rathnayake, U., & Ray, I. (2023). Risk evaluation of cost overruns (COs) in public sector construction projects: A fuzzy synthetic evaluation. Buildings, 13(5), 1116. https://doi.org/10.3390/buildings13051116

Deng, J., & Jian, W. (2022). Estimating construction project duration and costs upon completion using Monte Carlo simulations and improved earned value management. Buildings, 12(12), 2173. https://doi.org/10.3390/buildings12122173

Egwim, C. N., Alaka, H., Toriola-Coker, L. O., Balogun, H., & Sunmola, F. (2021). Applied artificial intelligence for predicting construction projects delay. Machine Learning with Applications, 6, 100166. https://doi.org/10.1016/j.mlwa.2021.100166

El-Dash, K., Abdel-Monem, M., & Alshaer, K. T. (2022). Assessing risk factors affecting the accuracy of conceptual cost estimation in the Middle East. Buildings, 12(7), 950. https://doi.org/10.3390/buildings12070950

Erdenekhuu, N., Kocsi, B., & Máté, D. (2022). A risk-based analysis approach to sustainable construction by environmental impacts. Energies, 15(18), 6736. https://doi.org/10.3390/en15186736

Fitzsimmons, J. P., Lu, R., Hong, Y., & Brilakis, I. (2022). Construction schedule risk analysis – a hybrid machine learning approach. Journal of Information Technology in Construction, 27, 70–93. https://www.itcon.org/papers/2022_04-ITcon-Fitzsimmons.pdf

Hendradewa, A. P. (2019). Schedule risk analysis by different phases of construction project using CPM-PERT and Monte-Carlo simulation. IOP Conference Series: Materials Science and Engineering, 528, 012035. https://doi.org/10.1088/1757-899X/528/1/012035

Ivanović, M. Z., Nedeljković, Đ., Stojadinović, Z., Marinković, D., Ivanišević, N., & Simić, N. (2022). Detection and in-depth analysis of causes of delay in construction projects: Synergy between machine learning and expert knowledge. Sustainability, 14(22), 14927. https://doi.org/10.3390/su142214927

Koulinas, G. K., Xanthopoulos, A. S., Tsilipiras, T. T., & Koulouriotis, D. E. (2020). Schedule delay risk analysis in construction projects with a simulation-based expert system. Buildings, 10(8), 134. https://doi.org/10.3390/buildings10080134

Mahmoud, H., Ahmed, V., & Beheiry, S. (2021). Construction cash flow risk index. Journal of Risk and Financial Management, 14(6), 269. https://doi.org/10.3390/jrfm14060269

Merisalu, J., Sundell, J., & Rosén, L. (2021). A framework for risk-based cost–benefit analysis for decision support on hydrogeological risks in underground construction. Geosciences, 11(2), 82. https://doi.org/10.3390/geosciences11020082

Plebankiewicz, E., & Wieczorek, D. (2020). Prediction of cost overrun risk in construction projects. Sustainability, 12(22), 9341. https://doi.org/10.3390/su12229341

Safaeian, M., Fathollahi-Fard, A. M., Kabirifar, K., Yazdani, M., & Shapouri, M. (2022). Selecting appropriate risk response strategies considering utility function and budget constraints: A case study of a construction company in Iran. Buildings, 12(2), 98. https://doi.org/10.3390/buildings12020098

Senić, A., Ivanović, M., Dobrodolac, M., & Stojadinović, Z. (2025). Prioritization of preventive measures: A multi-criteria approach to risk mitigation in road infrastructure projects. Mathematics, 13(2), 278. https://doi.org/10.3390/math13020278

Senova, A., Tobisova, A., & Rozenberg, R. (2023). New approaches to project risk assessment utilizing the Monte Carlo method. Sustainability, 15(2), 1006. https://doi.org/10.3390/su15021006

Serrano-Gomez, L., & Munoz-Hernandez, J. I. (2019). Monte Carlo approach to fuzzy AHP risk analysis in renewable energy construction projects. PLOS ONE, 14(6), e0215943. https://doi.org/10.1371/journal.pone.0215943

Singh, A. K., Anjum, F., Shakor, P., Prasath Kumar, V. R., Chandra, S. S., Mohandes, S. R., & Awuzie, B. (2025). Construction delays due to weather in cold regions: A two-stage structural equation modeling and artificial neural network approach. Buildings, 15(11), 1916. https://doi.org/10.3390/buildings15111916

Sobieraj, J., & Metelski, D. (2022). Project risk in the context of construction schedules—combined Monte Carlo simulation and time-at-risk (TaR) approach: Insights from the Fort Bema housing estate complex. Applied Sciences, 12(3), 1044. https://doi.org/10.3390/app12031044

Starczyk-Kołbyk, A., & Jędras, I. (2025). Integrated risk assessment in construction contracts: Comparative evaluation of risk matrix and Monte Carlo simulation on a high-rise office building project. Applied Sciences, 15(17), 9371. https://doi.org/10.3390/app15179371

Yaseen, Z. M., Ali, Z. H., Salih, S. Q., & Al-Ansari, N. (2020). Prediction of risk delay in construction projects using a hybrid artificial intelligence model. Sustainability, 12(4), 1514. https://doi.org/10.3390/su12041514

Zagia, F., Kajewski, S., Motamedisedeh, O., Omrani, S., & Rose, T. (2026). Assessing the influence of risk maturity level on construction delay factors: A machine learning-based model. Buildings, 16(16), 3149. https://doi.org/10.3390/buildings16163149

Zavala, G., Flores, V. A., Santos, R., & Cano, J. B. (2025). Stochastic cost estimation in transportation infrastructure projects using Monte Carlo simulation and correlated risk variables. Future Transportation, 5(4), 176. https://doi.org/10.3390/futuretransp5040176

Zhang, S., & Wang, X. (2021). Dynamic probability analysis for construction schedule using subset simulation. Advances in Civil Engineering, 2021, 1567261. https://doi.org/10.1155/2021/1567261

Zorrilla, J., Seijo, S., Arenal, U., & Mena, J. R. (2026). AI-driven decision support system for proactive risk management in construction projects. Intelligent Infrastructure and Construction, 2(2), 4. https://doi.org/10.3390/iic2020004

Student Signature: __________________________

_____________________

_____________________

_____________________

Date: _____________________