Site Data Collection Form

Brick / block masonry: delay events, for checking the Bricks-ly risk tool against real sites

Fill in one form for each COMPLETED masonry activity. Three to five activities is a useful minimum. Use working days. If you do not know a figure, write "unknown" and never guess; the source column says how sure the figure is.

# Part A. Activity details

| Field | Your entry |
| --- | --- |
| Site / project name and location |  |
| Activity (e.g. brick masonry, ground-floor walls) |  |
| Wall quantity (m² or m³) |  |
| Brick or block type |  |
| Planned start date / finish date |  |
| PLANNED duration (working days) |  |
| Actual start date / finish date |  |
| ACTUAL duration (working days) |  |
| ACTUAL DELAY = actual − planned (working days) |  |
| Crew: number of masons / helpers |  |
| Season (dry / monsoon / summer / winter) |  |
| Who gave this information (site diary, engineer, supervisor) |  |

# Part B. Delay events (one row for each thing that lost time)

Risk type: use one of the ten risk names in Part C, or write "other". Source of the figure: site diary, daily progress report, engineer's estimate, or memory.

| # | Date(s) | What happened | Risk type | Working days lost | Source of the figure |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

# Part C. Risk check: did each one occur on this activity?

Tick or write Y or N for every row. The N answers matter as much as the Y answers: they show how often a risk does not occur.

| ID | Risk | Occurred? (Y/N) | Days lost (if Y) |
| --- | --- | --- | --- |
| R-MAT | Brick / block / mortar material shortage or late delivery |  |  |
| R-TOOL | Tools and equipment delay |  |  |
| R-LAB | Labour absenteeism or shortage |  |  |
| R-SKILL | Unskilled or unqualified labour |  |  |
| R-PLAN | Poor planning or unrealistic scheduling |  |  |
| R-SAFE | Unsafe conditions or work at height |  |  |
| R-WX | Rain / monsoon stoppage |  |  |
| R-RWK | Rework due to workmanship or defects |  |  |
| R-PAY | Payment delay |  |  |
| R-DES | Design changes or incomplete documentation |  |  |
| Other | Write it here: |  |  |

# Part D. Site conditions at the start (optional)

These match the site-fact rules in the tool, so the rules can be checked against what happened.

| Condition | Your entry |
| --- | --- |
| Bricks / blocks / mortar in stock at start (days of work) |  |
| Crew present vs crew planned (e.g. 6 of 8) |  |
| Rain expected during the activity? (Y/N) |  |
| Drawings and details complete at start? (Y/N) |  |
| Working at height / scaffolding needed? (Y/N) |  |
| Payment to labour or suppliers overdue at start? (Y/N) |  |

# How this form is used

- Risk identification: did the tool flag the risks that actually happened? (Parts B and C)

- Ranking: does the matrix order match the order of days lost? (Part B)

- Probabilities: across several activities, how often did each risk occur? (Part C)

- Total delay: for a later prediction step, did the actual delay fall in the predicted range? (Part A)

Best sources: site diary, daily progress report, contractor's planned-versus-actual schedule.