Worked Calculations: how Bricks-ly is carried out

Every step by hand, with real numbers from the project. The same numbers appear in the app and in RII_Masonry_Literature.xlsx.

# 0. The chain in one view

| Step | What is calculated | Result used next |
| --- | --- | --- |
| 1 | RII from survey counts (published papers) | One RII per factor |
| 2 | Match factors to our 38 library risks (Direct only) | RII values per risk and study |
| 3 | Average inside each study, then across studies | Seed mean RII per risk |
| 4 | Rank, then split into five equal bands | Seed class 1 to 5 |
| 5 | Place on the 5×5 matrix; rule flag adds one probability class | Matrix cell and level |
| 6 | When the user enters p and delay: PERT mean, impact ratio, classes | Matrix cell from entered numbers |
| 7 | Rule engine: site facts flag risks | Elevated flags, auto-added risks |
| 8 | Validation: Spearman correlation with held-out studies | Agreement of the ranking |
| 9 | Sensitivity: change inputs ±20% and see what moves | Stability of the matrix |
| 10 | Expert survey RII (primary data) and site comparison (phase 2) | Own evidence |

Steps 1 to 8 use real published values. Anything marked ILLUSTRATIVE (the example case, the survey example, the site example) uses placeholder numbers to show the method and is not evidence.

# 1. RII from survey counts

Respondents rate each factor from 1 (lowest) to 5 (highest). The count of respondents choosing each rating gives the RII.

RII = Σ(rating × number of respondents choosing it) / (highest rating × total respondents)

## Example: Karthik & Rao 2019 (M01), 44 respondents, Table 3

| Factor | Counts for ratings 1,2,3,4,5 | Σ(rating × count) | ÷ (5 × 44) | RII |
| --- | --- | --- | --- | --- |
| Unsafe working conditions | 2, 2, 4, 20, 16 | 2+4+12+80+80 = 178 | 178 / 220 | 0.809 |
| Material shortages | 2, 3, 6, 20, 13 | 2+6+18+80+65 = 171 | 171 / 220 | 0.777 |
| Payment delay | 2, 3, 6, 21, 12 | 2+6+18+84+60 = 170 | 170 / 220 | 0.773 |

These reproduce the RII values printed in the paper, which confirms the formula and the respondent count of 44 (each row of counts sums to 44).

# 2. Matching factors to the library risks

Each paper uses its own wording. A factor is matched to one of the 38 library risks as Direct (names the same cause) or Related (overlaps, but is broader, narrower or an outcome). Only Direct values from the five seed studies enter the seed.

| Study | Factor as printed | RII | Tool risk | Mapping |
| --- | --- | --- | --- | --- |
| M01 India | Material shortages | 0.777 | R-MAT | Direct |
| A02 India | Lack of required construction material | 0.780 | R-MAT | Direct |
| A14 Sri Lanka | Delay of delivering materials to the site | 0.810 | R-MAT | Direct |
| A14 Sri Lanka | Shortage of skilled subcontractors/suppliers | 0.829 | R-MAT | Related: not used (suppliers and subcontractors mixed) |
| M01 India | Accidents | 0.759 | R-SAFE | Related: not used (an outcome, not the condition) |

# 3. Seed mean RII (average inside each study first)

If a study has two Direct values for one risk, they are averaged first so that every study counts once.

## R-MAT: three studies, one value each

(0.777 + 0.780 + 0.810) / 3 = 0.7889

## R-SAFE: one study (M01), two Direct items

M01 study mean = (0.809 unsafe conditions + 0.764 working at heights) / 2 = 0.7865

Seed mean = 0.7865   (only one study, so the mean is that study's value)

## R-WX: four studies

(0.764 M01 + 0.700 A02 + 0.657 M06 + 0.653 A14) / 4 = 2.774 / 4 = 0.6934

M06 climate conditions 0.6567 and A14 bad weather 0.6528 are shown rounded.

# 4. Ranking and the five bands

Class = 5 − INT( (rank − 1) × 5 / n )     with n = 30 seeded risks

Rank 1 → 5 − INT(0) = 5.  Rank 6 → 5 − INT(5 × 5 / 30) = 5 − INT(0.83) = 5.  Rank 7 → 5 − INT(6 × 5 / 30) = 5 − INT(1.0) = 4.  Rank 24 (R-WX) → 5 − INT(23 × 5 / 30) = 5 − INT(3.83) = 2.  Rank 30 → 5 − INT(29 × 5 / 30) = 5 − INT(4.83) = 1.

| Risk | Seed mean RII | Rank | Class | Cell (class on both axes) | Level | Seed studies |
| --- | --- | --- | --- | --- | --- | --- |
| R-MAT | 0.7889 | 1 | 5 | p5 × i5 = 25 | Extreme | A02, A14, M01 |
| R-SAFE | 0.7865 | 2 | 5 | p5 × i5 = 25 | Extreme | M01 |
| R-SKILL | 0.7831 | 3 | 5 | p5 × i5 = 25 | Extreme | A02, A15, M01 |
| R-PLAN | 0.7771 | 4 | 5 | p5 × i5 = 25 | Extreme | M01, M06 |
| R-PAY | 0.7733 | 5 | 5 | p5 × i5 = 25 | Extreme | A02, M01, M06 |
| R-DIS | 0.7700 | 6 | 5 | p5 × i5 = 25 | Extreme | A15, M01 |
| R-LAB | 0.7662 | 7 | 4 | p4 × i4 = 16 | Extreme | A02, A14, M01 |
| R-SCP | 0.7642 | 8 | 4 | p4 × i4 = 16 | Extreme | M06 |
| R-SITE | 0.7611 | 9 | 4 | p4 × i4 = 16 | Extreme | A02, M06 |
| R-DES | 0.7585 | 10 | 4 | p4 × i4 = 16 | Extreme | M01, M06 |
| R-RWK | 0.7561 | 11 | 4 | p4 × i4 = 16 | Extreme | M01, M06 |
| R-TOOL | 0.7528 | 12 | 4 | p4 × i4 = 16 | Extreme | A02, M01 |
| R-INC | 0.7520 | 13 | 3 | p3 × i3 = 9 | Moderate | M01 |
| R-STR | 0.7493 | 14 | 3 | p3 × i3 = 9 | Moderate | M06 |
| R-CTR | 0.7468 | 15 | 3 | p3 × i3 = 9 | Moderate | M06 |
| R-SUP | 0.7440 | 16 | 3 | p3 × i3 = 9 | Moderate | M01 |
| R-MOT | 0.7360 | 17 | 3 | p3 × i3 = 9 | Moderate | M01 |
| R-MGT | 0.7331 | 18 | 3 | p3 × i3 = 9 | Moderate | M01, M06 |
| R-CST | 0.7184 | 19 | 2 | p2 × i2 = 4 | Low | M06 |
| R-OVT | 0.7063 | 20 | 2 | p2 × i2 = 4 | Low | M01, M06 |
| R-ACC | 0.7045 | 21 | 2 | p2 × i2 = 4 | Low | A02, M01 |
| R-MTH | 0.7000 | 22 | 2 | p2 × i2 = 4 | Low | M01 |
| R-STO | 0.7000 | 23 | 2 | p2 × i2 = 4 | Low | A02 |
| R-WX | 0.6934 | 24 | 2 | p2 × i2 = 4 | Low | A02, A14, M01, M06 |
| R-COM | 0.6793 | 25 | 1 | p1 × i1 = 1 | Low | A02, M06 |
| R-PRC | 0.6695 | 26 | 1 | p1 × i1 = 1 | Low | A02, A14 |
| R-ECO | 0.6612 | 27 | 1 | p1 × i1 = 1 | Low | M06 |
| R-WAT | 0.6500 | 28 | 1 | p1 × i1 = 1 | Low | A02 |
| R-FAT | 0.6100 | 29 | 1 | p1 × i1 = 1 | Low | A02 |
| R-SOC | 0.5940 | 30 | 1 | p1 × i1 = 1 | Low | M06 |

Level uses the matrix thresholds (an Assumption): score ≤ 5 Low, 6 to 10 Moderate, 11 to 15 High, 16 or more Extreme. For example 5 × 5 = 25 is Extreme and 3 × 3 = 9 is Moderate.

Caution to state aloud: the six risks in class 5 lie between 0.770 and 0.789 (a spread of 0.019), so the band edges split risks that are almost tied. 30 of the 38 library risks are seeded; eight (R-TRN, R-PRD, R-SUB, R-CLI, R-QLT, R-DEF, R-GOV, R-FIN) have no value from the seed studies and stay off the matrix until numbers are entered. The seed is a weak starting order, not a measurement.

# 5. Placing a risk with no numbers on the matrix

A library risk with no probability or delay entered still appears, at (seed class, seed class), with a dashed outline and the label literature seed. A rule flag raises the probability class by one (maximum 5).

| Risk | Seed class | Rule flag? | Matrix cell and level |
| --- | --- | --- | --- |
| R-WX | 2 | No | p2 × i2 = 4 → Low |
| R-WX | 2 | Yes (monsoon overlaps the work) | p3 × i2 = 6 → Moderate |
| R-LAB | 4 | Yes (6 workers needed, 5 available) | p5 × i4 = 20 → Extreme |
| R-MAT | 5 | Yes | p5 (capped at 5) × i5 = 25 → Extreme |

# 6. When the user enters numbers (ILLUSTRATIVE example case)

ILLUSTRATIVE: placeholder numbers built into the example, not evidence. Planned duration 16 working days; impact edges 0.02 / 0.05 / 0.10 / 0.20; probability edges 0.2 / 0.4 / 0.6 / 0.8.

Expected delay if it occurs (Beta-PERT, λ = 4) = (min + 4 × most likely + max) / 6

Impact ratio = expected delay / planned duration       Probability class from p, impact class from the ratio

## R-MAT (material shortage): p = 0.50, delay 1 / 3 / 8 days

Expected delay = (1 + 4×3 + 8) / 6 = 21 / 6 = 3.5 days

Impact ratio = 3.5 / 16 = 0.219  → above the last edge 0.20  → impact class 5

p = 0.50  → between 0.4 and 0.6  → probability class 3

Score = 3 × 5 = 15  → High

## R-LAB (labour absenteeism): p = 0.35, delay 1 / 2 / 6 days

Expected delay = (1 + 8 + 6) / 6 = 2.5 days     Ratio = 2.5 / 16 = 0.156  → between 0.10 and 0.20  → impact class 4

p = 0.35 → between 0.2 and 0.4 → class 2     Score = 2 × 4 = 8 → Moderate

| Risk | p | Delay min/likely/max | Expected delay | Ratio to 16 d | p class | Impact | Level |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-MAT | 0.50 | 1 / 3 / 8 | 3.50 | 0.219 | 3 | 5 | High (15) |
| R-LAB | 0.35 | 1 / 2 / 6 | 2.50 | 0.156 | 2 | 4 | Moderate (8) |
| R-RWK | 0.25 | 1 / 2 / 5 | 2.33 | 0.146 | 2 | 4 | Moderate (8) |
| R-WX | 0.20 | 1 / 2 / 7 | 2.67 | 0.167 | 2 | 4 | Moderate (8) |
| R-PLAN | 0.10 | 1 / 1 / 3 | 1.33 | 0.083 | 1 | 3 | Low (3) |
| R-SAFE | 0.30 | 1 / 2 / 6 | 2.50 | 0.156 | 2 | 4 | Moderate (8) |
| R-SKILL | 0.22 | 1 / 2 / 5 | 2.33 | 0.146 | 2 | 4 | Moderate (8) |

The class is a label for ordering. The continuous p and delay range stay in the register; the matrix is never used as a time or cost quantity.

# 7. Rule engine: how site facts flag risks

ILLUSTRATIVE site facts from the example case.

| Rule | Facts entered | Result |
| --- | --- | --- |
| RL-MAT: lead time > buffer | lead time 6 days, buffer 3 days → 6 > 3 | R-MAT elevated |
| RL-LAB: workers needed > available | needed 6, available 5 → 6 > 5 | R-LAB elevated |
| RL-MAT2: stock days < planned duration | stock 2 days, planned 16 days → 2 < 16 | R-MAT elevated (second rule) |
| RL-WX: monsoon overlap = true | monsoon_overlap true | R-WX elevated |
| RL-TOOL: tools shortage = true | tools_shortage false | Does not fire |

A flagged risk that is not in the register is added automatically with empty numbers; it then shows on the matrix from its literature seed (step 5) until real numbers are entered.

# 8. Validation: Spearman rank correlation against a held-out study

Compare our seed order with the order in a study the model did not use. Hand-worked example on the nine original core risks that Adebowale & Agumba 2023 (M10, a pooled analysis of 10 surveys) also cover. These nine have no tied values, so the shortcut formula is exact. Ranks here are within the nine.

| Risk | Seed rank (of 9) | M10 RII | M10 rank (of 9) | d = difference | d² |  |
| --- | --- | --- | --- | --- | --- | --- |
| R-MAT | 1 | 0.775 | 3 | −2 | 4 |  |
| R-TOOL | 8 | 0.691 | 8 | 0 | 0 |  |
| R-LAB | 5 | 0.660 | 9 | −4 | 16 |  |
| R-SKILL | 2 | 0.801 | 1 | 1 | 1 |  |
| R-PLAN | 3 | 0.698 | 7 | −4 | 16 |  |
| R-WX | 9 | 0.715 | 6 | 3 | 9 |  |
| R-RWK | 7 | 0.761 | 4 | 3 | 9 |  |
| R-PAY | 4 | 0.751 | 5 | −1 | 1 |  |
| R-DES | 6 | 0.776 | 2 | 4 | 16 | Σd² = 72 |

ρ = 1 − 6 × Σd² / (n × (n² − 1)) = 1 − 6 × 72 / (9 × 80) = 1 − 432 / 720 = 0.40

t = ρ × √((n − 2) / (1 − ρ²)) = 0.40 × √(7 / 0.84) = 1.155  → two-tailed p = 0.29 (7 degrees of freedom)

The same test on the full library (all risks that both the seed and the study cover; ties handled by average ranks, so computed by the script rather than by hand): M10 ρ = 0.28 (19 risks, p = 0.24); Brazil managers (M15) ρ = 0.63 (11 risks, p = 0.039); Indonesia workers (M14) ρ = −0.18 (13 risks, p = 0.55). Only M15 falls below 0.05, and one of three tests does not survive a multiple-test correction (threshold 0.017). Report it as a hint of agreement with manager-side surveys, not as a validation. On the original nine-to-seven-risk comparisons the results were M10 0.40, M15 0.36 and M14 −0.68, none significant.

# 9. Sensitivity: which risks change level when the inputs move?

ILLUSTRATIVE example case. Method: change one input by ±20% (others fixed) and recompute the class, using the same steps as section 6.

| Risk | Change | New value | Classes (p, impact) | Level |
| --- | --- | --- | --- | --- |
| R-MAT | none (base) | p 0.50, mean 3.50 d | 3, 5 | High (15) |
| R-MAT | p −20% | p 0.40 | 3, 5 | High (15), unchanged |
| R-MAT | p +20% | p 0.60 | 4, 5 | Extreme (20), moves up |
| R-MAT | delay −20% | mean 2.80 d (ratio 0.175) | 3, 4 | High (12), unchanged level, lower score |
| R-MAT | delay +20% | mean 4.20 d (ratio 0.263) | 3, 5 | High (15), unchanged |
| R-LAB | p +20% | p 0.42 | 3, 4 | High (12), moves up |
| R-LAB | p −20%, delay ±20% | — | 2, 4 | Moderate (8), unchanged |

Reading: R-MAT and R-LAB sit close to a class boundary on probability, so a 20% change in p can move their level. Risks far from a boundary stay put. A full table for all risks and both inputs is the next step; the same calculation can be run for every risk in the app.

# 10. Own evidence: expert survey and site comparison

## Expert survey RII (primary data)

ILLUSTRATIVE five-respondent example showing the arithmetic only; not real responses.

Importance ratings for one risk from 5 respondents: 4, 5, 3, 4, 4   → sum = 20

RII = 20 / (5 × 5) = 20 / 25 = 0.80

Risk index per respondent = frequency × impact (each 1 to 5, so 1 to 25); average over respondents, then rank the risks.

Compare the survey ranking with the seed ranking using the same Spearman steps as section 8.

## Site records (phase 2)

ILLUSTRATIVE numbers showing the formulas.

Hit rate (recall) = risks that occurred AND were flagged / risks that occurred  = 3 / 4 = 75%

Precision = risks flagged that occurred / risks flagged  = 3 / 5 = 60%

Probability check over several activities: a risk given p = 0.30 should occur in about 30% of activities (3 of 10).

Rank check: Spearman correlation between the matrix order and the order of days lost on site.

# 11. What is real and what is not

| Part | Numbers are | How to describe it |
| --- | --- | --- |
| Steps 1 to 4, 8 (RII, seed, validation) | Real, from 11 published studies | Secondary data analysis; ranking only |
| Step 5 (seed placement) | Derived from the real RII values | A relative ranking, not an estimate |
| Steps 6, 7, 9 (example case) | ILLUSTRATIVE placeholders | Shows how the tool computes; replace with user data |
| Step 10 (survey, site) | ILLUSTRATIVE for the method; real data to come | Plan for primary data and site validation |