## Test1_Hand
Test 1: one risk, one response. Hand calculation
ILLUSTRATIVE placeholders (Assumptions), not site data. Blue on yellow = input; black = formula; green = link to another sheet.
Input | Value | Unit / note
Planned duration T0 | 16 | days
Deadline | 20 | days
Delay cost Cd | 8000 | INR per day of delay
Liquidated damages LD | 5000 | INR per day after the deadline
PERT lambda | 4 | standard weight
Delay a (min) | 1 | days
Delay m (mode) | 3 | days
Delay b (max) | 8 | days
p, accept (no response) | 0.5 | probability R-MAT occurs
p, with M-BUF | 0.2 | probability after buffer stock
M-BUF cost | 6000 | INR
Derived quantity | Value | Formula
Threshold c = deadline - T0 (d) | 4 | delay beyond c breaks the deadline
Mean delay if it occurs, mu | 3.5 | (a + lambda*m + b)/(lambda + 2)
Variance of delay if it occurs | 1.6071 | (mu - a)(b - mu)/(lambda + 3)
Beta alpha | 2.1429 | 1 + lambda (m - a)/(b - a)
Beta beta | 3.8571 | 1 + lambda (b - m)/(b - a)
P(delay <= c ¦ occurs), F(c) | 0.66436 | Beta CDF at c
P(delay > c ¦ occurs) | 0.33564
E[(delay - c)+ ¦ occurs] (d) | 0.32159 | integral of 1 - F(x) from c to b (Simpson, sheet Integral)
Result by hand | Accept (no response) | With M-BUF | How
Probability of a delay | 0.5 | 0.2 | p
Expected delay (d) | 1.75 | 0.7 | p x mu
Expected delay cost (INR) | 14000 | 5600 | Cd x expected delay
P(finish after the deadline) | 0.16782 | 0.067127 | p x P(delay > c)
Expected days past the deadline | 0.1608 | 0.064318 | p x E[(delay - c)+]
Expected liquidated damages (INR) | 803.9801 | 321.592 | LD x expected days past deadline
Residual expected cost (INR) | 14803.9801 | 5921.592 | delay cost + LD
Response cost (INR) | 0 | 6000 | M-BUF cost
Total expected cost, TEC (INR) | 14803.9801 | 11921.592 | response cost + residual
TEC change vs accepting (INR) | 0 | -2882.388 | negative = cheaper than accepting
Exact P80 duration (d) | 19.7471 | 16 | invert P(T <= t) = (1-p) + p F(t - T0)
Exact P90 duration (d) | 20.6259 | 19.3826 | same
Exact P95 duration (d) | 21.2727 | 20.3749 | same
Hand decision | AUTHORIZE MITIGATION | M-BUF is cheaper in total expected cost by 2,882 INR

## Integral
Simpson integration of 1 - F(x) from c to b (40 intervals)
E[(delay - c)+] = integral from c to b of (1 - F(x)) dx, F = Beta-PERT cumulative distribution. Simpson weights 1, 4, 2, 4, ..., 4, 1.
i | x (days of delay) | S(x) = 1 - F(x) | Weight | Weight x S(x)
0 | 4 | 0.33564 | 1 | 0.33564
1 | 4.1 | 0.31158 | 4 | 1.2463
2 | 4.2 | 0.28839 | 2 | 0.57677
3 | 4.3 | 0.26609 | 4 | 1.0644
4 | 4.4 | 0.24472 | 2 | 0.48944
5 | 4.5 | 0.22431 | 4 | 0.89723
6 | 4.6 | 0.20487 | 2 | 0.40974
7 | 4.7 | 0.18642 | 4 | 0.74569
8 | 4.8 | 0.16897 | 2 | 0.33795
9 | 4.9 | 0.15253 | 4 | 0.61012
10 | 5 | 0.13709 | 2 | 0.27417
11 | 5.1 | 0.12264 | 4 | 0.49056
12 | 5.2 | 0.10918 | 2 | 0.21835
13 | 5.3 | 0.096685 | 4 | 0.38674
14 | 5.4 | 0.085146 | 2 | 0.17029
15 | 5.5 | 0.074534 | 4 | 0.29814
16 | 5.6 | 0.064826 | 2 | 0.12965
17 | 5.7 | 0.05599 | 4 | 0.22396
18 | 5.8 | 0.047994 | 2 | 0.095988
19 | 5.9 | 0.040802 | 4 | 0.16321
20 | 6 | 0.034378 | 2 | 0.068755
21 | 6.1 | 0.028679 | 4 | 0.11472
22 | 6.2 | 0.023665 | 2 | 0.04733
23 | 6.3 | 0.019292 | 4 | 0.077167
24 | 6.4 | 0.015514 | 2 | 0.031029
25 | 6.5 | 0.012287 | 4 | 0.049148
26 | 6.6 | 0.0095631 | 2 | 0.019126
27 | 6.7 | 0.0072962 | 4 | 0.029185
28 | 6.8 | 0.0054396 | 2 | 0.010879
29 | 6.9 | 0.0039471 | 4 | 0.015789
30 | 7 | 0.0027734 | 2 | 0.0055468
31 | 7.1 | 0.0018742 | 4 | 0.0074969
32 | 7.2 | 0.0012071 | 2 | 0.0024142
33 | 7.3 | 0.0007315 | 4 | 0.002926
34 | 7.4 | 0.00040932 | 2 | 0.00081865
35 | 7.5 | 0.00020543 | 4 | 0.00082171
36 | 7.6 | 8.8063e-05 | 2 | 0.00017613
37 | 7.7 | 2.9427e-05 | 4 | 0.00011771
38 | 7.8 | 6.2421e-06 | 2 | 1.2484e-05
39 | 7.9 | 4.3646e-07 | 4 | 1.7458e-06
40 | 8 | 0 | 1 | 0
|  |  | step h | 0.1
|  |  | Sum | 9.6478
|  |  | Integral = h/3 x sum | 0.32159

## Excel_Simulation
Monte Carlo in Excel: 2,000 draws (uniform numbers pasted from numpy seed 12345; everything else is a formula)
Excel simulation summary | Accept | With M-BUF
Draws | 2000 | 2000
P(delay occurs) | 0.512 | 0.189
Expected delay (d) | 1.7861 | 0.65757
P(finish after the deadline) | 0.1655 | 0.0625
P90 duration (d) | 20.6201 | 19.2112
Total expected cost (INR) | 15078.4258 | 11559.3577
Standard error of the mean cost (INR) | 385.0485 | 285.2722
Draw | U1 (occurrence) | U2 (delay) | Delay if occurs (d) =BETAINV(U2) | Occurs, accept | Duration, accept (d) | Cost, accept (INR) | Occurs, M-BUF | Duration, M-BUF (d) | Cost incl. M-BUF (INR)
1 | 0.22734 | 0.31676 | 2.7488 | 1 | 18.7488 | 21990.7328 | 0 | 16 | 6000
2 | 0.79737 | 0.67625 | 4.049 | 0 | 16 | 0 | 0 | 16 | 6000
3 | 0.39111 | 0.33281 | 2.8045 | 1 | 18.8045 | 22436.3966 | 0 | 16 | 6000
4 | 0.59831 | 0.18673 | 2.2755 | 0 | 16 | 0 | 0 | 16 | 6000
5 | 0.67276 | 0.9418 | 5.6741 | 0 | 16 | 0 | 0 | 16 | 6000
6 | 0.24825 | 0.94888 | 5.7597 | 1 | 21.7597 | 54875.852 | 0 | 16 | 6000
7 | 0.66724 | 0.095898 | 1.8844 | 0 | 16 | 0 | 0 | 16 | 6000
8 | 0.44184 | 0.88648 | 5.1669 | 1 | 21.1669 | 47170.1368 | 0 | 16 | 6000
9 | 0.69745 | 0.32647 | 2.7826 | 0 | 16 | 0 | 0 | 16 | 6000
10 | 0.73393 | 0.22013 | 2.4027 | 0 | 16 | 0 | 0 | 16 | 6000
11 | 0.081595 | 0.1599 | 2.1684 | 1 | 18.1684 | 17347.1998 | 1 | 18.1684 | 23347.1998
12 | 0.3401 | 0.46519 | 3.2607 | 1 | 19.2607 | 26085.6102 | 0 | 16 | 6000
13 | 0.26642 | 0.81578 | 4.7123 | 1 | 20.7123 | 41259.7974 | 0 | 16 | 6000
14 | 0.19329 | 0.12947 | 2.0397 | 1 | 18.0397 | 16317.6337 | 1 | 18.0397 | 22317.6337
15 | 0.091665 | 0.59857 | 3.7416 | 1 | 19.7416 | 29933.112 | 1 | 19.7416 | 35933.112
16 | 0.85474 | 0.60162 | 3.7532 | 0 | 16 | 0 | 0 | 16 | 6000
17 | 0.93199 | 0.72478 | 4.2586 | 0 | 16 | 0 | 0 | 16 | 6000
18 | 0.86055 | 0.92934 | 5.5388 | 0 | 16 | 0 | 0 | 16 | 6000
19 | 0.54619 | 0.93767 | 5.6273 | 0 | 16 | 0 | 0 | 16 | 6000
20 | 0.49499 | 0.27377 | 2.5978 | 1 | 18.5978 | 20782.0514 | 0 | 16 | 6000
21 | 0.45178 | 0.66504 | 4.0028 | 1 | 20.0028 | 32035.8854 | 0 | 16 | 6000
22 | 0.33089 | 0.90345 | 5.3012 | 1 | 21.3012 | 48915.1016 | 0 | 16 | 6000
23 | 0.25707 | 0.33983 | 2.8288 | 1 | 18.8288 | 22630.4139 | 0 | 16 | 6000
24 | 0.25885 | 0.35545 | 2.8827 | 1 | 18.8827 | 23061.2623 | 0 | 16 | 6000
25 | 0.0050223 | 0.6286 | 3.8572 | 1 | 19.8572 | 30857.3539 | 1 | 19.8572 | 36857.3539
26 | 0.28238 | 0.068088 | 1.7387 | 1 | 17.7387 | 13909.8251 | 0 | 16 | 6000
27 | 0.61683 | 0.17633 | 2.2345 | 0 | 16 | 0 | 0 | 16 | 6000
28 | 0.30439 | 0.44089 | 3.1765 | 1 | 19.1765 | 25411.7665 | 0 | 16 | 6000
29 | 0.1502 | 0.21793 | 2.3945 | 1 | 18.3945 | 19156.0285 | 1 | 18.3945 | 25156.0285
30 | 0.47433 | 0.47637 | 3.2996 | 1 | 19.2996 | 26397.1939 | 0 | 16 | 6000
31 | 0.25523 | 0.29757 | 2.6818 | 1 | 18.6818 | 21454.3283 | 0 | 16 | 6000
32 | 0.27907 | 0.26058 | 2.5506 | 1 | 18.5506 | 20404.8105 | 0 | 16 | 6000
33 | 0.48276 | 0.21198 | 2.3722 | 1 | 18.3722 | 18977.3871 | 0 | 16 | 6000
34 | 0.49563 | 0.24626 | 2.4989 | 1 | 18.4989 | 19991.0874 | 0 | 16 | 6000
35 | 0.83848 | 0.18013 | 2.2496 | 0 | 16 | 0 | 0 | 16 | 6000
36 | 0.86216 | 0.1783 | 2.2424 | 0 | 16 | 0 | 0 | 16 | 6000
37 | 0.75053 | 0.61112 | 3.7895 | 0 | 16 | 0 | 0 | 16 | 6000
38 | 0.20916 | 0.75987 | 4.4221 | 1 | 20.4221 | 37487.1577 | 0 | 16 | 6000
39 | 0.24926 | 0.085572 | 1.8326 | 1 | 17.8326 | 14660.7217 | 0 | 16 | 6000
40 | 0.61806 | 0.53697 | 3.5144 | 0 | 16 | 0 | 0 | 16 | 6000
41 | 0.63453 | 0.17437 | 2.2268 | 0 | 16 | 0 | 0 | 16 | 6000
42 | 0.24816 | 0.68482 | 4.0848 | 1 | 20.0848 | 33102.7406 | 0 | 16 | 6000
43 | 0.080872 | 0.87507 | 5.0837 | 1 | 21.0837 | 46088.0828 | 1 | 21.0837 | 52088.0828
44 | 0.42869 | 0.61839 | 3.8175 | 1 | 19.8175 | 30539.8852 | 0 | 16 | 6000
45 | 0.31311 | 0.17896 | 2.245 | 1 | 18.245 | 17959.8538 | 0 | 16 | 6000
46 | 0.0097121 | 0.21004 | 2.3649 | 1 | 18.3649 | 18918.9793 | 1 | 18.3649 | 24918.9793
47 | 0.87 | 0.97283 | 6.1287 | 0 | 16 | 0 | 0 | 16 | 6000
48 | 0.44179 | 0.37875 | 2.9628 | 1 | 18.9628 | 23702.1712 | 0 | 16 | 6000
49 | 0.27595 | 0.9661 | 6.008 | 1 | 22.008 | 58103.9084 | 0 | 16 | 6000
50 | 0.058203 | 0.40873 | 3.0657 | 1 | 19.0657 | 24525.9251 | 1 | 19.0657 | 30525.9251
51 | 0.16863 | 0.24014 | 2.4766 | 1 | 18.4766 | 19812.7659 | 1 | 18.4766 | 25812.7659
52 | 0.78001 | 0.20377 | 2.3411 | 0 | 16 | 0 | 0 | 16 | 6000
53 | 0.55205 | 0.36699 | 2.9224 | 0 | 16 | 0 | 0 | 16 | 6000
54 | 0.50728 | 0.33344 | 2.8067 | 0 | 16 | 0 | 0 | 16 | 6000
55 | 0.28272 | 0.28183 | 2.6263 | 1 | 18.6263 | 21010.7699 | 0 | 16 | 6000
56 | 0.085381 | 0.48181 | 3.3187 | 1 | 19.3187 | 26549.4762 | 1 | 19.3187 | 32549.4762
57 | 0.88334 | 0.94723 | 5.739 | 0 | 16 | 0 | 0 | 16 | 6000
58 | 0.027384 | 0.91775 | 5.4265 | 1 | 21.4265 | 50544.0726 | 1 | 21.4265 | 56544.0726
59 | 0.12152 | 0.74785 | 4.3647 | 1 | 20.3647 | 36741.2515 | 1 | 20.3647 | 42741.2515
60 | 0.89652 | 0.16793 | 2.201 | 0 | 16 | 0 | 0 | 16 | 6000
61 | 0.33146 | 0.37816 | 2.9607 | 1 | 18.9607 | 23685.8821 | 0 | 16 | 6000
62 | 0.34685 | 0.51626 | 3.4402 | 1 | 19.4402 | 27521.5269 | 0 | 16 | 6000
63 | 0.008994 | 0.42268 | 3.1137 | 1 | 19.1137 | 24909.5512 | 1 | 19.1137 | 30909.5512
64 | 0.87766 | 0.087405 | 1.842 | 0 | 16 | 0 | 0 | 16 | 6000
65 | 0.48408 | 0.48123 | 3.3166 | 1 | 19.3166 | 26533.0727 | 0 | 16 | 6000
66 | 0.78257 | 0.96456 | 5.9826 | 0 | 16 | 0 | 0 | 16 | 6000
67 | 0.7071 | 0.27374 | 2.5976 | 0 | 16 | 0 | 0 | 16 | 6000
68 | 0.67011 | 0.34753 | 2.8554 | 0 | 16 | 0 | 0 | 16 | 6000
69 | 0.76813 | 0.67577 | 4.047 | 0 | 16 | 0 | 0 | 16 | 6000
70 | 0.97753 | 0.86671 | 5.0256 | 0 | 16 | 0 | 0 | 16 | 6000
71 | 0.046108 | 0.29032 | 2.6563 | 1 | 18.6563 | 21250.6704 | 1 | 18.6563 | 27250.6704
72 | 0.86239 | 0.60085 | 3.7503 | 0 | 16 | 0 | 0 | 16 | 6000
73 | 0.34426 | 0.055603 | 1.6654 | 1 | 17.6654 | 13322.9513 | 0 | 16 | 6000
74 | 0.76287 | 0.0015188 | 1.1152 | 0 | 16 | 0 | 0 | 16 | 6000
75 | 0.092844 | 0.9935 | 6.7406 | 1 | 22.7406 | 67627.6397 | 1 | 22.7406 | 73627.6397
76 | 0.77601 | 0.86827 | 5.0363 | 0 | 16 | 0 | 0 | 16 | 6000
77 | 0.47716 | 0.16885 | 2.2047 | 1 | 18.2047 | 17637.5299 | 0 | 16 | 6000
78 | 0.53398 | 0.42583 | 3.1246 | 0 | 16 | 0 | 0 | 16 | 6000
79 | 0.16303 | 0.16588 | 2.1927 | 1 | 18.1927 | 17541.7316 | 1 | 18.1927 | 23541.7316
80 | 0.25815 | 0.94309 | 5.6891 | 1 | 21.6891 | 53958.7664 | 0 | 16 | 6000
81 | 0.98681 | 0.70367 | 4.1653 | 0 | 16 | 0 | 0 | 16 | 6000
82 | 0.72316 | 0.7325 | 4.2935 | 0 | 16 | 0 | 0 | 16 | 6000
83 | 0.5174 | 0.17743 | 2.2389 | 0 | 16 | 0 | 0 | 16 | 6000
84 | 0.87765 | 0.88039 | 5.1219 | 0 | 16 | 0 | 0 | 16 | 6000
85 | 0.70953 | 0.93343 | 5.5813 | 0 | 16 | 0 | 0 | 16 | 6000
86 | 0.98 | 0.50348 | 3.3949 | 0 | 16 | 0 | 0 | 16 | 6000
87 | 0.75757 | 0.61662 | 3.8106 | 0 | 16 | 0 | 0 | 16 | 6000
88 | 0.11489 | 0.31599 | 2.7462 | 1 | 18.7462 | 21969.3003 | 1 | 18.7462 | 27969.3003
89 | 0.067734 | 0.88687 | 5.1699 | 1 | 21.1699 | 47208.4337 | 1 | 21.1699 | 53208.4337
90 | 0.02207 | 0.53729 | 3.5155 | 1 | 19.5155 | 28124.093 | 1 | 19.5155 | 34124.093
91 | 0.17761 | 0.14699 | 2.1149 | 1 | 18.1149 | 16919.4902 | 1 | 18.1149 | 22919.4902
92 | 0.16584 | 0.87695 | 5.0971 | 1 | 21.0971 | 46262.1018 | 1 | 21.0971 | 52262.1018
93 | 0.49447 | 0.3409 | 2.8325 | 1 | 18.8325 | 22660.0383 | 0 | 16 | 6000
94 | 0.99921 | 0.54597 | 3.5469 | 0 | 16 | 0 | 0 | 16 | 6000
95 | 0.30333 | 0.37065 | 2.935 | 1 | 18.935 | 23479.63 | 0 | 16 | 6000
96 | 0.69587 | 0.12025 | 1.9987 | 0 | 16 | 0 | 0 | 16 | 6000
97 | 0.75822 | 0.88377 | 5.1467 | 0 | 16 | 0 | 0 | 16 | 6000
98 | 0.47513 | 0.4373 | 3.1641 | 1 | 19.1641 | 25312.823 | 0 | 16 | 6000
99 | 0.14311 | 0.42274 | 3.1139 | 1 | 19.1139 | 24911.3151 | 1 | 19.1139 | 30911.3151
100 | 0.76441 | 0.41398 | 3.0838 | 0 | 16 | 0 | 0 | 16 | 6000
101 | 0.61993 | 0.043779 | 1.589 | 0 | 16 | 0 | 0 | 16 | 6000
102 | 0.21973 | 0.20383 | 2.3413 | 1 | 18.3413 | 18730.5386 | 0 | 16 | 6000
103 | 0.98117 | 0.04455 | 1.5942 | 0 | 16 | 0 | 0 | 16 | 6000
104 | 0.21532 | 0.031399 | 1.4982 | 1 | 17.4982 | 11985.4229 | 0 | 16 | 6000
105 | 0.63954 | 0.65317 | 3.9546 | 0 | 16 | 0 | 0 | 16 | 6000
106 | 0.34552 | 0.036355 | 1.5362 | 1 | 17.5362 | 12289.4701 | 0 | 16 | 6000
107 | 0.43501 | 0.17133 | 2.2146 | 1 | 18.2146 | 17717.0952 | 0 | 16 | 6000
108 | 0.42672 | 0.37281 | 2.9424 | 1 | 18.9424 | 23538.9638 | 0 | 16 | 6000
109 | 0.22109 | 0.84164 | 4.8638 | 1 | 20.8638 | 43229.9965 | 0 | 16 | 6000
110 | 0.69262 | 0.47065 | 3.2797 | 0 | 16 | 0 | 0 | 16 | 6000
111 | 0.39969 | 0.10904 | 1.9473 | 1 | 17.9473 | 15578.2359 | 0 | 16 | 6000
112 | 0.60304 | 0.50415 | 3.3973 | 0 | 16 | 0 | 0 | 16 | 6000
113 | 0.90538 | 0.96891 | 6.0562 | 0 | 16 | 0 | 0 | 16 | 6000
114 | 0.8096 | 0.8667 | 5.0255 | 0 | 16 | 0 | 0 | 16 | 6000
115 | 0.49579 | 0.37378 | 2.9457 | 1 | 18.9457 | 23565.6772 | 0 | 16 | 6000
116 | 0.47899 | 0.53124 | 3.4938 | 1 | 19.4938 | 27950.1185 | 0 | 16 | 6000
117 | 0.8177 | 0.15101 | 2.1317 | 0 | 16 | 0 | 0 | 16 | 6000
118 | 0.60056 | 0.90599 | 5.3225 | 0 | 16 | 0 | 0 | 16 | 6000
119 | 0.22246 | 0.28786 | 2.6477 | 1 | 18.6477 | 21181.2934 | 0 | 16 | 6000
120 | 0.84221 | 0.65187 | 3.9494 | 0 | 16 | 0 | 0 | 16 | 6000
121 | 0.96546 | 0.64208 | 3.9103 | 0 | 16 | 0 | 0 | 16 | 6000
122 | 0.94933 | 0.82685 | 4.7755 | 0 | 16 | 0 | 0 | 16 | 6000
123 | 0.67467 | 0.18999 | 2.2881 | 0 | 16 | 0 | 0 | 16 | 6000
124 | 0.21353 | 0.86303 | 5.0008 | 1 | 21.0008 | 45010.0809 | 0 | 16 | 6000
125 | 0.33392 | 0.68644 | 4.0916 | 1 | 20.0916 | 33191.0829 | 0 | 16 | 6000
126 | 0.43538 | 0.45935 | 3.2404 | 1 | 19.2404 | 25923.1453 | 0 | 16 | 6000
127 | 0.010575 | 0.82232 | 4.7494 | 1 | 20.7494 | 41742.2152 | 1 | 20.7494 | 47742.2152
128 | 0.31145 | 0.33713 | 2.8195 | 1 | 18.8195 | 22555.9169 | 0 | 16 | 6000
129 | 0.071602 | 0.62463 | 3.8417 | 1 | 19.8417 | 30733.2574 | 1 | 19.8417 | 36733.2574
130 | 0.77861 | 0.51104 | 3.4217 | 0 | 16 | 0 | 0 | 16 | 6000
131 | 0.47771 | 0.77211 | 4.4821 | 1 | 20.4821 | 38267.0793 | 0 | 16 | 6000
132 | 0.096723 | 0.54092 | 3.5286 | 1 | 19.5286 | 28228.958 | 1 | 19.5286 | 34228.958
133 | 0.74888 | 0.36631 | 2.92 | 0 | 16 | 0 | 0 | 16 | 6000
134 | 0.87613 | 0.45682 | 3.2316 | 0 | 16 | 0 | 0 | 16 | 6000
135 | 0.1159 | 0.97689 | 6.2119 | 1 | 22.2119 | 60755.3213 | 1 | 22.2119 | 66755.3213
136 | 0.4559 | 0.75279 | 4.3881 | 1 | 20.3881 | 37045.419 | 0 | 16 | 6000
137 | 0.078253 | 0.80884 | 4.6738 | 1 | 20.6738 | 40759.3708 | 1 | 20.6738 | 46759.3708
138 | 0.152 | 0.12496 | 2.0198 | 1 | 18.0198 | 16158.1626 | 1 | 18.0198 | 22158.1626
139 | 0.27644 | 0.42471 | 3.1207 | 1 | 19.1207 | 24965.4365 | 0 | 16 | 6000
140 | 0.48529 | 0.42829 | 3.133 | 1 | 19.133 | 25064.2188 | 0 | 16 | 6000
141 | 0.03454 | 0.59703 | 3.7358 | 1 | 19.7358 | 29886.5786 | 1 | 19.7358 | 35886.5786
142 | 0.74196 | 0.97875 | 6.2536 | 0 | 16 | 0 | 0 | 16 | 6000
143 | 0.55416 | 0.93187 | 5.5649 | 0 | 16 | 0 | 0 | 16 | 6000
144 | 0.95197 | 0.2124 | 2.3737 | 0 | 16 | 0 | 0 | 16 | 6000
145 | 0.06638 | 0.16966 | 2.208 | 1 | 18.208 | 17663.6609 | 1 | 18.208 | 23663.6609
146 | 0.74443 | 0.26097 | 2.552 | 0 | 16 | 0 | 0 | 16 | 6000
147 | 0.11224 | 0.94339 | 5.6926 | 1 | 21.6926 | 54004.1037 | 1 | 21.6926 | 60004.1037
148 | 0.68359 | 0.95818 | 5.8852 | 0 | 16 | 0 | 0 | 16 | 6000
149 | 0.32951 | 0.19226 | 2.2969 | 1 | 18.2969 | 18375.456 | 0 | 16 | 6000
150 | 0.13679 | 0.94338 | 5.6925 | 1 | 21.6925 | 54002.5911 | 1 | 21.6925 | 60002.5911
151 | 0.16417 | 0.80235 | 4.6385 | 1 | 20.6385 | 40300.615 | 1 | 20.6385 | 46300.615
152 | 0.21168 | 0.86292 | 5 | 1 | 21 | 45000.4767 | 0 | 16 | 6000
153 | 0.056675 | 0.38142 | 2.9719 | 1 | 18.9719 | 23775.4662 | 1 | 18.9719 | 29775.4662
154 | 0.40193 | 0.97624 | 6.198 | 1 | 22.198 | 60574.2778 | 0 | 16 | 6000
155 | 0.89773 | 0.38445 | 2.9824 | 0 | 16 | 0 | 0 | 16 | 6000
156 | 0.42468 | 0.71515 | 4.2156 | 1 | 20.2156 | 34802.3834 | 0 | 16 | 6000
157 | 0.64011 | 0.89415 | 5.2259 | 0 | 16 | 0 | 0 | 16 | 6000
158 | 0.68719 | 0.51531 | 3.4368 | 0 | 16 | 0 | 0 | 16 | 6000
159 | 0.90068 | 0.33099 | 2.7982 | 0 | 16 | 0 | 0 | 16 | 6000
160 | 0.36745 | 0.35143 | 2.8688 | 1 | 18.8688 | 22950.6602 | 0 | 16 | 6000
161 | 0.48951 | 0.034729 | 1.524 | 1 | 17.524 | 12191.9803 | 0 | 16 | 6000
162 | 0.45291 | 0.31662 | 2.7484 | 1 | 18.7484 | 21986.8143 | 0 | 16 | 6000
163 | 0.24319 | 0.24743 | 2.5031 | 1 | 18.5031 | 20024.9547 | 0 | 16 | 6000
164 | 0.79754 | 0.38559 | 2.9863 | 0 | 16 | 0 | 0 | 16 | 6000
165 | 0.98074 | 0.41275 | 3.0796 | 0 | 16 | 0 | 0 | 16 | 6000
166 | 0.69771 | 0.30537 | 2.7091 | 0 | 16 | 0 | 0 | 16 | 6000
167 | 0.8265 | 0.21307 | 2.3763 | 0 | 16 | 0 | 0 | 16 | 6000
168 | 0.27519 | 0.29252 | 2.6641 | 1 | 18.6641 | 21312.4733 | 0 | 16 | 6000
169 | 0.12936 | 0.7506 | 4.3777 | 1 | 20.3777 | 36909.9953 | 1 | 20.3777 | 42909.9953
170 | 0.43152 | 0.12595 | 2.0242 | 1 | 18.0242 | 16193.2815 | 0 | 16 | 6000
171 | 0.53621 | 0.48832 | 3.3415 | 0 | 16 | 0 | 0 | 16 | 6000
172 | 0.50525 | 0.7125 | 4.2039 | 0 | 16 | 0 | 0 | 16 | 6000
173 | 0.066532 | 0.49194 | 3.3542 | 1 | 19.3542 | 26833.6737 | 1 | 19.3542 | 32833.6737
174 | 0.051604 | 0.97609 | 6.1948 | 1 | 22.1948 | 60532.8188 | 1 | 22.1948 | 66532.8188
175 | 0.6599 | 0.16919 | 2.206 | 0 | 16 | 0 | 0 | 16 | 6000
176 | 0.91956 | 0.17499 | 2.2292 | 0 | 16 | 0 | 0 | 16 | 6000
177 | 0.35459 | 0.047488 | 1.6138 | 1 | 17.6138 | 12910.5001 | 0 | 16 | 6000
178 | 0.37126 | 0.73141 | 4.2886 | 1 | 20.2886 | 35751.3521 | 0 | 16 | 6000
179 | 0.12187 | 0.77698 | 4.5065 | 1 | 20.5065 | 38584.3729 | 1 | 20.5065 | 44584.3729
180 | 0.42708 | 0.80233 | 4.6384 | 1 | 20.6384 | 40298.9176 | 0 | 16 | 6000
181 | 0.17393 | 0.90235 | 5.292 | 1 | 21.292 | 48795.5949 | 1 | 21.292 | 54795.5949
182 | 0.72726 | 0.048221 | 1.6186 | 0 | 16 | 0 | 0 | 16 | 6000
183 | 0.47925 | 0.065531 | 1.7242 | 1 | 17.7242 | 13793.6375 | 0 | 16 | 6000
184 | 0.72246 | 0.36326 | 2.9095 | 0 | 16 | 0 | 0 | 16 | 6000
185 | 0.77415 | 0.88253 | 5.1376 | 0 | 16 | 0 | 0 | 16 | 6000
186 | 0.17636 | 0.81038 | 4.6822 | 1 | 20.6822 | 40869.2041 | 1 | 20.6822 | 46869.2041
187 | 0.38576 | 0.38228 | 2.9749 | 1 | 18.9749 | 23799.1614 | 0 | 16 | 6000
188 | 0.65432 | 0.97413 | 6.1543 | 0 | 16 | 0 | 0 | 16 | 6000
189 | 0.68249 | 0.22106 | 2.4062 | 0 | 16 | 0 | 0 | 16 | 6000
190 | 0.00043709 | 0.11139 | 1.9582 | 1 | 17.9582 | 15665.8727 | 1 | 17.9582 | 21665.8727
191 | 0.29469 | 0.06893 | 1.7435 | 1 | 17.7435 | 13947.7208 | 0 | 16 | 6000
192 | 0.066307 | 0.94634 | 5.7281 | 1 | 21.7281 | 54465.5789 | 1 | 21.7281 | 60465.5789
193 | 0.15167 | 0.33392 | 2.8084 | 1 | 18.8084 | 22467.1247 | 1 | 18.8084 | 28467.1247
194 | 0.96583 | 0.5337 | 3.5026 | 0 | 16 | 0 | 0 | 16 | 6000
195 | 0.69268 | 0.2876 | 2.6467 | 0 | 16 | 0 | 0 | 16 | 6000
196 | 0.66606 | 0.16306 | 2.1813 | 0 | 16 | 0 | 0 | 16 | 6000
197 | 0.34609 | 0.90661 | 5.3278 | 1 | 21.3278 | 49260.7827 | 0 | 16 | 6000
198 | 0.72955 | 0.46222 | 3.2504 | 0 | 16 | 0 | 0 | 16 | 6000
199 | 0.45789 | 0.74229 | 4.3387 | 1 | 20.3387 | 36402.8666 | 0 | 16 | 6000
200 | 0.39785 | 0.4325 | 3.1475 | 1 | 19.1475 | 25180.2478 | 0 | 16 | 6000
201 | 0.56771 | 0.55975 | 3.5971 | 0 | 16 | 0 | 0 | 16 | 6000
202 | 0.46044 | 0.6045 | 3.7642 | 1 | 19.7642 | 30113.2589 | 0 | 16 | 6000
203 | 0.14987 | 0.73891 | 4.323 | 1 | 20.323 | 36198.7893 | 1 | 20.323 | 42198.7893
204 | 0.16255 | 0.80859 | 4.6724 | 1 | 20.6724 | 40741.7875 | 1 | 20.6724 | 46741.7875
205 | 0.5727 | 0.93582 | 5.607 | 0 | 16 | 0 | 0 | 16 | 6000
206 | 0.41736 | 0.65837 | 3.9756 | 1 | 19.9756 | 31804.8474 | 0 | 16 | 6000
207 | 0.07346 | 0.30343 | 2.7023 | 1 | 18.7023 | 21618.731 | 1 | 18.7023 | 27618.731
208 | 0.16221 | 0.66849 | 4.0169 | 1 | 20.0169 | 32219.7294 | 1 | 20.0169 | 38219.7294
209 | 0.12109 | 0.49849 | 3.3773 | 1 | 19.3773 | 27018.0687 | 1 | 19.3773 | 33018.0687
210 | 0.25267 | 0.16784 | 2.2006 | 1 | 18.2006 | 17604.9325 | 0 | 16 | 6000
211 | 0.81335 | 0.24382 | 2.49 | 0 | 16 | 0 | 0 | 16 | 6000
212 | 0.079872 | 0.39242 | 3.0097 | 1 | 19.0097 | 24077.7341 | 1 | 19.0097 | 30077.7341
213 | 0.21072 | 0.71402 | 4.2106 | 1 | 20.2106 | 34737.6767 | 0 | 16 | 6000
214 | 0.6187 | 0.94894 | 5.7604 | 0 | 16 | 0 | 0 | 16 | 6000
215 | 0.85134 | 0.3061 | 2.7117 | 0 | 16 | 0 | 0 | 16 | 6000
216 | 0.86098 | 0.25299 | 2.5233 | 0 | 16 | 0 | 0 | 16 | 6000
217 | 0.85345 | 0.145 | 2.1065 | 0 | 16 | 0 | 0 | 16 | 6000
218 | 0.92863 | 0.56445 | 3.6144 | 0 | 16 | 0 | 0 | 16 | 6000
219 | 0.45746 | 0.40295 | 3.0459 | 1 | 19.0459 | 24366.8558 | 0 | 16 | 6000
220 | 0.37747 | 0.15723 | 2.1575 | 1 | 18.1575 | 17259.8263 | 0 | 16 | 6000
221 | 0.6312 | 0.35586 | 2.8841 | 0 | 16 | 0 | 0 | 16 | 6000
222 | 0.88044 | 0.12367 | 2.014 | 0 | 16 | 0 | 0 | 16 | 6000
223 | 0.46798 | 0.58535 | 3.6919 | 1 | 19.6919 | 29535.1942 | 0 | 16 | 6000
224 | 0.72897 | 0.65522 | 3.9629 | 0 | 16 | 0 | 0 | 16 | 6000
225 | 0.42653 | 0.73154 | 4.2892 | 1 | 20.2892 | 35759.0666 | 0 | 16 | 6000
226 | 0.70999 | 0.38158 | 2.9725 | 0 | 16 | 0 | 0 | 16 | 6000
227 | 0.42801 | 0.35451 | 2.8794 | 1 | 18.8794 | 23035.3342 | 0 | 16 | 6000
228 | 0.77753 | 0.14298 | 2.098 | 0 | 16 | 0 | 0 | 16 | 6000
229 | 0.81552 | 0.58812 | 3.7023 | 0 | 16 | 0 | 0 | 16 | 6000
230 | 0.37115 | 0.94241 | 5.6812 | 1 | 21.6812 | 53855.224 | 0 | 16 | 6000
231 | 0.95781 | 0.96861 | 6.0508 | 0 | 16 | 0 | 0 | 16 | 6000
232 | 0.1009 | 0.49056 | 3.3494 | 1 | 19.3494 | 26794.8622 | 1 | 19.3494 | 32794.8622
233 | 0.92084 | 0.0088664 | 1.2677 | 0 | 16 | 0 | 0 | 16 | 6000
234 | 0.29996 | 0.45951 | 3.2409 | 1 | 19.2409 | 25927.5081 | 0 | 16 | 6000
235 | 0.27804 | 0.57152 | 3.6404 | 1 | 19.6404 | 29123.4758 | 0 | 16 | 6000
236 | 0.53621 | 0.84411 | 4.879 | 0 | 16 | 0 | 0 | 16 | 6000
237 | 0.23953 | 0.75608 | 4.4038 | 1 | 20.4038 | 37249.7091 | 0 | 16 | 6000
238 | 0.49351 | 0.96527 | 5.9942 | 1 | 21.9942 | 57924.8701 | 0 | 16 | 6000
239 | 0.85829 | 0.020562 | 1.4037 | 0 | 16 | 0 | 0 | 16 | 6000
240 | 0.39956 | 0.25505 | 2.5307 | 1 | 18.5307 | 20245.6065 | 0 | 16 | 6000
241 | 0.48805 | 0.99621 | 6.9121 | 1 | 22.9121 | 69857.2408 | 0 | 16 | 6000
242 | 0.57924 | 0.069021 | 1.744 | 0 | 16 | 0 | 0 | 16 | 6000
243 | 0.74737 | 0.20084 | 2.3299 | 0 | 16 | 0 | 0 | 16 | 6000
244 | 0.46275 | 0.63594 | 3.886 | 1 | 19.886 | 31087.745 | 0 | 16 | 6000
245 | 0.9128 | 0.34128 | 2.8338 | 0 | 16 | 0 | 0 | 16 | 6000
246 | 0.66504 | 0.035322 | 1.5285 | 0 | 16 | 0 | 0 | 16 | 6000
247 | 0.062426 | 0.42541 | 3.1231 | 1 | 19.1231 | 24984.9284 | 1 | 19.1231 | 30984.9284
248 | 0.58982 | 0.28337 | 2.6318 | 0 | 16 | 0 | 0 | 16 | 6000
249 | 0.74266 | 0.32088 | 2.7632 | 0 | 16 | 0 | 0 | 16 | 6000
250 | 0.27021 | 0.69592 | 4.1319 | 1 | 20.1319 | 33714.9085 | 0 | 16 | 6000
251 | 0.70861 | 0.97619 | 6.1968 | 0 | 16 | 0 | 0 | 16 | 6000
252 | 0.13274 | 0.096358 | 1.8866 | 1 | 17.8866 | 15093.1303 | 1 | 17.8866 | 21093.1303
253 | 0.83174 | 0.27625 | 2.6066 | 0 | 16 | 0 | 0 | 16 | 6000
254 | 0.90621 | 0.5716 | 3.6407 | 0 | 16 | 0 | 0 | 16 | 6000
255 | 0.60172 | 0.0047058 | 1.1974 | 0 | 16 | 0 | 0 | 16 | 6000
256 | 0.56638 | 0.8705 | 5.0516 | 0 | 16 | 0 | 0 | 16 | 6000
257 | 0.99382 | 0.3806 | 2.9691 | 0 | 16 | 0 | 0 | 16 | 6000
258 | 0.16797 | 0.90381 | 5.3041 | 1 | 21.3041 | 48953.8379 | 1 | 21.3041 | 54953.8379
259 | 0.41438 | 0.45228 | 3.2159 | 1 | 19.2159 | 25727.0258 | 0 | 16 | 6000
260 | 0.46917 | 0.54744 | 3.5522 | 1 | 19.5522 | 28417.7936 | 0 | 16 | 6000
261 | 0.060639 | 0.015223 | 1.3483 | 1 | 17.3483 | 10786.1638 | 1 | 17.3483 | 16786.1638
262 | 0.76709 | 0.63263 | 3.8729 | 0 | 16 | 0 | 0 | 16 | 6000
263 | 0.39416 | 0.65453 | 3.9601 | 1 | 19.9601 | 31680.7265 | 0 | 16 | 6000
264 | 0.71279 | 0.29113 | 2.6592 | 0 | 16 | 0 | 0 | 16 | 6000
265 | 0.39198 | 0.24741 | 2.503 | 1 | 18.503 | 20024.3992 | 0 | 16 | 6000
266 | 0.13812 | 0.5918 | 3.7161 | 1 | 19.7161 | 29728.7752 | 1 | 19.7161 | 35728.7752
267 | 0.73765 | 0.60785 | 3.777 | 0 | 16 | 0 | 0 | 16 | 6000
268 | 0.2554 | 0.64141 | 3.9076 | 1 | 19.9076 | 31260.8888 | 0 | 16 | 6000
269 | 0.41106 | 0.44654 | 3.196 | 1 | 19.196 | 25568.1485 | 0 | 16 | 6000
270 | 0.013042 | 0.77904 | 4.5168 | 1 | 20.5168 | 38718.967 | 1 | 20.5168 | 44718.967
271 | 0.89741 | 0.2916 | 2.6608 | 0 | 16 | 0 | 0 | 16 | 6000
272 | 0.36186 | 0.49149 | 3.3526 | 1 | 19.3526 | 26820.9742 | 0 | 16 | 6000
273 | 0.39779 | 0.36941 | 2.9307 | 1 | 18.9307 | 23445.5597 | 0 | 16 | 6000
274 | 0.74597 | 0.65356 | 3.9562 | 0 | 16 | 0 | 0 | 16 | 6000
275 | 0.32085 | 0.63457 | 3.8806 | 1 | 19.8806 | 31044.576 | 0 | 16 | 6000
276 | 0.68352 | 0.44007 | 3.1737 | 0 | 16 | 0 | 0 | 16 | 6000
277 | 0.26076 | 0.86291 | 4.9999 | 1 | 20.9999 | 44999.2381 | 0 | 16 | 6000
278 | 0.0057428 | 0.7193 | 4.234 | 1 | 20.234 | 35042.2609 | 1 | 20.234 | 41042.2609
279 | 0.80897 | 0.21095 | 2.3683 | 0 | 16 | 0 | 0 | 16 | 6000
280 | 0.57 | 0.98209 | 6.3348 | 0 | 16 | 0 | 0 | 16 | 6000
281 | 0.30159 | 0.61518 | 3.8051 | 1 | 19.8051 | 30440.6946 | 0 | 16 | 6000
282 | 0.41371 | 0.44102 | 3.1769 | 1 | 19.1769 | 25415.4703 | 0 | 16 | 6000
283 | 0.75271 | 0.54515 | 3.5439 | 0 | 16 | 0 | 0 | 16 | 6000
284 | 0.27745 | 0.74142 | 4.3346 | 1 | 20.3346 | 36350.1629 | 0 | 16 | 6000
285 | 0.55925 | 0.30793 | 2.7181 | 0 | 16 | 0 | 0 | 16 | 6000
286 | 0.59707 | 0.74224 | 4.3384 | 0 | 16 | 0 | 0 | 16 | 6000
287 | 0.064013 | 0.16544 | 2.1909 | 1 | 18.1909 | 17527.5194 | 1 | 18.1909 | 23527.5194
288 | 0.35265 | 0.24925 | 2.5097 | 1 | 18.5097 | 20077.8023 | 0 | 16 | 6000
289 | 0.56638 | 0.049073 | 1.6242 | 0 | 16 | 0 | 0 | 16 | 6000
290 | 0.91762 | 0.73542 | 4.3069 | 0 | 16 | 0 | 0 | 16 | 6000
291 | 0.41958 | 0.15191 | 2.1355 | 1 | 18.1355 | 17083.7999 | 0 | 16 | 6000
292 | 0.062738 | 0.7392 | 4.3243 | 1 | 20.3243 | 36216.5059 | 1 | 20.3243 | 42216.5059
293 | 0.5665 | 0.41506 | 3.0875 | 0 | 16 | 0 | 0 | 16 | 6000
294 | 0.31392 | 0.05417 | 1.6565 | 1 | 17.6565 | 13252.1543 | 0 | 16 | 6000
295 | 0.75842 | 0.21081 | 2.3678 | 0 | 16 | 0 | 0 | 16 | 6000
296 | 0.26771 | 0.23288 | 2.45 | 1 | 18.45 | 19599.662 | 0 | 16 | 6000
297 | 0.56637 | 0.29037 | 2.6565 | 0 | 16 | 0 | 0 | 16 | 6000
298 | 0.10874 | 0.87274 | 5.0673 | 1 | 21.0673 | 45874.7796 | 1 | 21.0673 | 51874.7796
299 | 0.17331 | 0.21599 | 2.3872 | 1 | 18.3872 | 19097.9621 | 1 | 18.3872 | 25097.9621
300 | 0.74044 | 0.45918 | 3.2398 | 0 | 16 | 0 | 0 | 16 | 6000
301 | 0.93474 | 0.89473 | 5.2305 | 0 | 16 | 0 | 0 | 16 | 6000
302 | 0.56083 | 0.16389 | 2.1847 | 0 | 16 | 0 | 0 | 16 | 6000
303 | 0.30781 | 0.66372 | 3.9974 | 1 | 19.9974 | 31978.9271 | 0 | 16 | 6000
304 | 0.29723 | 0.51284 | 3.4281 | 1 | 19.4281 | 27424.4768 | 0 | 16 | 6000
305 | 0.12228 | 0.56112 | 3.6021 | 1 | 19.6021 | 28817.0794 | 1 | 19.6021 | 34817.0794
306 | 0.9418 | 0.62245 | 3.8332 | 0 | 16 | 0 | 0 | 16 | 6000
307 | 0.28707 | 0.11574 | 1.9782 | 1 | 17.9782 | 15825.9909 | 0 | 16 | 6000
308 | 0.59809 | 0.55158 | 3.5673 | 0 | 16 | 0 | 0 | 16 | 6000
309 | 0.75527 | 0.0018604 | 1.1268 | 0 | 16 | 0 | 0 | 16 | 6000
310 | 0.15201 | 0.615 | 3.8044 | 1 | 19.8044 | 30435.2741 | 1 | 19.8044 | 36435.2741
311 | 0.57451 | 0.70251 | 4.1603 | 0 | 16 | 0 | 0 | 16 | 6000
312 | 0.89394 | 0.76803 | 4.4619 | 0 | 16 | 0 | 0 | 16 | 6000
313 | 0.61065 | 0.99413 | 6.7751 | 0 | 16 | 0 | 0 | 16 | 6000
314 | 0.33676 | 0.24087 | 2.4792 | 1 | 18.4792 | 19833.921 | 0 | 16 | 6000
315 | 0.26858 | 0.62827 | 3.8558 | 1 | 19.8558 | 30846.7793 | 0 | 16 | 6000
316 | 0.11951 | 0.4079 | 3.0629 | 1 | 19.0629 | 24503.0701 | 1 | 19.0629 | 30503.0701
317 | 0.34432 | 0.11925 | 1.9942 | 1 | 17.9942 | 15953.4387 | 0 | 16 | 6000
318 | 0.82904 | 0.83388 | 4.8169 | 0 | 16 | 0 | 0 | 16 | 6000
319 | 0.2514 | 0.08914 | 1.8508 | 1 | 17.8508 | 14806.031 | 0 | 16 | 6000
320 | 0.62723 | 0.204 | 2.342 | 0 | 16 | 0 | 0 | 16 | 6000
321 | 0.58351 | 0.39069 | 3.0038 | 0 | 16 | 0 | 0 | 16 | 6000
322 | 0.86069 | 0.31175 | 2.7314 | 0 | 16 | 0 | 0 | 16 | 6000
323 | 0.51978 | 0.082079 | 1.8145 | 0 | 16 | 0 | 0 | 16 | 6000
324 | 0.36445 | 0.90288 | 5.2964 | 1 | 21.2964 | 48853.4873 | 0 | 16 | 6000
325 | 0.14537 | 0.75286 | 4.3885 | 1 | 20.3885 | 37049.9971 | 1 | 20.3885 | 43049.9971
326 | 0.45036 | 0.56433 | 3.6139 | 1 | 19.6139 | 28911.4867 | 0 | 16 | 6000
327 | 0.89452 | 0.90125 | 5.283 | 0 | 16 | 0 | 0 | 16 | 6000
328 | 0.43584 | 0.9938 | 6.7563 | 1 | 22.7563 | 67832.1176 | 0 | 16 | 6000
329 | 0.28444 | 0.22285 | 2.4129 | 1 | 18.4129 | 19302.9308 | 0 | 16 | 6000
330 | 0.61622 | 0.59041 | 3.7109 | 0 | 16 | 0 | 0 | 16 | 6000
331 | 0.52069 | 0.30706 | 2.715 | 0 | 16 | 0 | 0 | 16 | 6000
332 | 0.43337 | 0.54645 | 3.5486 | 1 | 19.5486 | 28389.0866 | 0 | 16 | 6000
333 | 0.026587 | 0.064964 | 1.721 | 1 | 17.721 | 13767.6049 | 1 | 17.721 | 19767.6049
334 | 0.038602 | 0.83895 | 4.8474 | 1 | 20.8474 | 43016.8208 | 1 | 20.8474 | 49016.8208
335 | 0.6199 | 0.31329 | 2.7368 | 0 | 16 | 0 | 0 | 16 | 6000
336 | 0.57447 | 0.87727 | 5.0994 | 0 | 16 | 0 | 0 | 16 | 6000
337 | 0.099607 | 0.1963 | 2.3125 | 1 | 18.3125 | 18500.2611 | 1 | 18.3125 | 24500.2611
338 | 0.32982 | 0.45818 | 3.2363 | 1 | 19.2363 | 25890.7536 | 0 | 16 | 6000
339 | 0.35804 | 0.84845 | 4.9061 | 1 | 20.9061 | 43779.747 | 0 | 16 | 6000
340 | 0.54551 | 0.076429 | 1.7846 | 0 | 16 | 0 | 0 | 16 | 6000
341 | 0.26301 | 0.5072 | 3.408 | 1 | 19.408 | 27264.2314 | 0 | 16 | 6000
342 | 0.75897 | 0.62873 | 3.8577 | 0 | 16 | 0 | 0 | 16 | 6000
343 | 0.99616 | 0.3225 | 2.7688 | 0 | 16 | 0 | 0 | 16 | 6000
344 | 0.61991 | 0.95923 | 5.9005 | 0 | 16 | 0 | 0 | 16 | 6000
345 | 0.44759 | 0.16107 | 2.1732 | 1 | 18.1732 | 17385.4894 | 0 | 16 | 6000
346 | 0.22978 | 0.40282 | 3.0454 | 1 | 19.0454 | 24363.2779 | 0 | 16 | 6000
347 | 0.12472 | 0.47515 | 3.2954 | 1 | 19.2954 | 26363.1973 | 1 | 19.2954 | 32363.1973
348 | 0.97002 | 0.87822 | 5.1062 | 0 | 16 | 0 | 0 | 16 | 6000
349 | 0.59623 | 0.93698 | 5.6197 | 0 | 16 | 0 | 0 | 16 | 6000
350 | 0.62857 | 0.08069 | 1.8072 | 0 | 16 | 0 | 0 | 16 | 6000
351 | 0.6545 | 0.58837 | 3.7032 | 0 | 16 | 0 | 0 | 16 | 6000
352 | 0.64557 | 0.25942 | 2.5464 | 0 | 16 | 0 | 0 | 16 | 6000
353 | 0.73274 | 0.53369 | 3.5025 | 0 | 16 | 0 | 0 | 16 | 6000
354 | 0.96702 | 0.12844 | 2.0352 | 0 | 16 | 0 | 0 | 16 | 6000
355 | 0.52549 | 0.85286 | 4.9342 | 0 | 16 | 0 | 0 | 16 | 6000
356 | 0.16717 | 0.77194 | 4.4813 | 1 | 20.4813 | 38256.2985 | 1 | 20.4813 | 44256.2985
357 | 0.93456 | 0.73795 | 4.3186 | 0 | 16 | 0 | 0 | 16 | 6000
358 | 0.65327 | 0.21635 | 2.3886 | 0 | 16 | 0 | 0 | 16 | 6000
359 | 0.92834 | 0.082339 | 1.8159 | 0 | 16 | 0 | 0 | 16 | 6000
360 | 0.36574 | 0.055742 | 1.6662 | 1 | 17.6662 | 13329.7867 | 0 | 16 | 6000
361 | 0.4672 | 0.73685 | 4.3135 | 1 | 20.3135 | 36075.3844 | 0 | 16 | 6000
362 | 0.50188 | 0.23398 | 2.454 | 0 | 16 | 0 | 0 | 16 | 6000
363 | 0.63091 | 0.73844 | 4.3208 | 0 | 16 | 0 | 0 | 16 | 6000
364 | 0.25364 | 0.32825 | 2.7888 | 1 | 18.7888 | 22310.0817 | 0 | 16 | 6000
365 | 0.20635 | 0.45334 | 3.2196 | 1 | 19.2196 | 25756.4463 | 0 | 16 | 6000
366 | 0.058872 | 0.41676 | 3.0933 | 1 | 19.0933 | 24746.5595 | 1 | 19.0933 | 30746.5595
367 | 0.084499 | 0.26056 | 2.5505 | 1 | 18.5505 | 20404.277 | 1 | 18.5505 | 26404.277
368 | 0.99108 | 0.069339 | 1.7458 | 0 | 16 | 0 | 0 | 16 | 6000
369 | 0.29509 | 0.38044 | 2.9686 | 1 | 18.9686 | 23748.5296 | 0 | 16 | 6000
370 | 0.83059 | 0.11352 | 1.9681 | 0 | 16 | 0 | 0 | 16 | 6000
371 | 0.92781 | 0.72176 | 4.245 | 0 | 16 | 0 | 0 | 16 | 6000
372 | 0.89861 | 0.81964 | 4.7341 | 0 | 16 | 0 | 0 | 16 | 6000
373 | 0.5877 | 0.053026 | 1.6494 | 0 | 16 | 0 | 0 | 16 | 6000
374 | 0.90351 | 0.58333 | 3.6843 | 0 | 16 | 0 | 0 | 16 | 6000
375 | 0.16947 | 0.95293 | 5.8123 | 1 | 21.8123 | 55559.3758 | 1 | 21.8123 | 61559.3758
376 | 0.16389 | 0.19552 | 2.3095 | 1 | 18.3095 | 18476.1831 | 1 | 18.3095 | 24476.1831
377 | 0.60539 | 0.73777 | 4.3177 | 0 | 16 | 0 | 0 | 16 | 6000
378 | 0.13203 | 0.39407 | 3.0154 | 1 | 19.0154 | 24123.0451 | 1 | 19.0154 | 30123.0451
379 | 0.44869 | 0.4577 | 3.2347 | 1 | 19.2347 | 25877.3714 | 0 | 16 | 6000
380 | 0.47904 | 0.45189 | 3.2145 | 1 | 19.2145 | 25716.1931 | 0 | 16 | 6000
381 | 0.017498 | 0.93476 | 5.5956 | 1 | 21.5956 | 52742.5261 | 1 | 21.5956 | 58742.5261
382 | 0.57746 | 0.70608 | 4.1758 | 0 | 16 | 0 | 0 | 16 | 6000
383 | 0.6628 | 0.95679 | 5.8652 | 0 | 16 | 0 | 0 | 16 | 6000
384 | 0.55369 | 0.35264 | 2.873 | 0 | 16 | 0 | 0 | 16 | 6000
385 | 0.75284 | 0.18199 | 2.2569 | 0 | 16 | 0 | 0 | 16 | 6000
386 | 0.59431 | 0.73873 | 4.3222 | 0 | 16 | 0 | 0 | 16 | 6000
387 | 0.56933 | 0.84111 | 4.8606 | 0 | 16 | 0 | 0 | 16 | 6000
388 | 0.1434 | 0.8145 | 4.7051 | 1 | 20.7051 | 41166.8245 | 1 | 20.7051 | 47166.8245
389 | 0.94259 | 0.84972 | 4.9142 | 0 | 16 | 0 | 0 | 16 | 6000
390 | 0.3806 | 0.15304 | 2.1402 | 1 | 18.1402 | 17121.2194 | 0 | 16 | 6000
391 | 0.59641 | 0.25988 | 2.5481 | 0 | 16 | 0 | 0 | 16 | 6000
392 | 0.70132 | 0.31564 | 2.7449 | 0 | 16 | 0 | 0 | 16 | 6000
393 | 0.7193 | 0.39036 | 3.0026 | 0 | 16 | 0 | 0 | 16 | 6000
394 | 0.47559 | 0.91075 | 5.3635 | 1 | 21.3635 | 49725.3114 | 0 | 16 | 6000
395 | 0.3981 | 0.052681 | 1.6472 | 1 | 17.6472 | 13177.7132 | 0 | 16 | 6000
396 | 0.96193 | 0.16507 | 2.1895 | 0 | 16 | 0 | 0 | 16 | 6000
397 | 0.29178 | 0.76509 | 4.4474 | 1 | 20.4474 | 37816.8023 | 0 | 16 | 6000
398 | 0.00051244 | 0.758 | 4.413 | 1 | 20.413 | 37369.6328 | 1 | 20.413 | 43369.6328
399 | 0.49203 | 0.66944 | 4.0208 | 1 | 20.0208 | 32270.6738 | 0 | 16 | 6000
400 | 0.33626 | 0.30321 | 2.7016 | 1 | 18.7016 | 21612.6291 | 0 | 16 | 6000
401 | 0.95525 | 0.8944 | 5.2279 | 0 | 16 | 0 | 0 | 16 | 6000
402 | 0.63892 | 0.34871 | 2.8595 | 0 | 16 | 0 | 0 | 16 | 6000
403 | 0.09997 | 0.066274 | 1.7285 | 1 | 17.7285 | 13827.6124 | 1 | 17.7285 | 19827.6124
404 | 0.27371 | 0.7349 | 4.3045 | 1 | 20.3045 | 35958.5993 | 0 | 16 | 6000
405 | 0.25837 | 0.25816 | 2.5419 | 1 | 18.5419 | 20335.2791 | 0 | 16 | 6000
406 | 0.52756 | 0.7692 | 4.4677 | 0 | 16 | 0 | 0 | 16 | 6000
407 | 0.98153 | 0.96032 | 5.9166 | 0 | 16 | 0 | 0 | 16 | 6000
408 | 0.56993 | 0.6459 | 3.9255 | 0 | 16 | 0 | 0 | 16 | 6000
409 | 0.33359 | 0.14904 | 2.1235 | 1 | 18.1235 | 16988.0427 | 0 | 16 | 6000
410 | 0.62913 | 0.15362 | 2.1426 | 0 | 16 | 0 | 0 | 16 | 6000
411 | 0.8901 | 0.14757 | 2.1174 | 0 | 16 | 0 | 0 | 16 | 6000
412 | 0.66796 | 0.053968 | 1.6553 | 0 | 16 | 0 | 0 | 16 | 6000
413 | 0.68724 | 0.1975 | 2.3171 | 0 | 16 | 0 | 0 | 16 | 6000
414 | 0.65518 | 0.83976 | 4.8524 | 0 | 16 | 0 | 0 | 16 | 6000
415 | 0.025803 | 0.34667 | 2.8524 | 1 | 18.8524 | 22819.2089 | 1 | 18.8524 | 28819.2089
416 | 0.1306 | 0.2697 | 2.5833 | 1 | 18.5833 | 20666.0282 | 1 | 18.5833 | 26666.0282
417 | 0.34964 | 0.97104 | 6.0947 | 1 | 22.0947 | 59230.9255 | 0 | 16 | 6000
418 | 0.36441 | 0.69049 | 4.1088 | 1 | 20.1088 | 33414.1191 | 0 | 16 | 6000
419 | 0.27072 | 0.24741 | 2.5031 | 1 | 18.5031 | 20024.6011 | 0 | 16 | 6000
420 | 0.39274 | 0.61505 | 3.8046 | 1 | 19.8046 | 30436.8138 | 0 | 16 | 6000
421 | 0.58958 | 0.39999 | 3.0357 | 0 | 16 | 0 | 0 | 16 | 6000
422 | 0.1822 | 0.83281 | 4.8106 | 1 | 20.8106 | 42537.5626 | 1 | 20.8106 | 48537.5626
423 | 0.55826 | 0.59368 | 3.7232 | 0 | 16 | 0 | 0 | 16 | 6000
424 | 0.72879 | 0.21155 | 2.3706 | 0 | 16 | 0 | 0 | 16 | 6000
425 | 0.95104 | 0.79134 | 4.5801 | 0 | 16 | 0 | 0 | 16 | 6000
426 | 0.79552 | 0.74791 | 4.365 | 0 | 16 | 0 | 0 | 16 | 6000
427 | 0.20495 | 0.65187 | 3.9494 | 1 | 19.9494 | 31594.9423 | 0 | 16 | 6000
428 | 0.2435 | 0.52917 | 3.4863 | 1 | 19.4863 | 27890.7403 | 0 | 16 | 6000
429 | 0.89114 | 0.53382 | 3.503 | 0 | 16 | 0 | 0 | 16 | 6000
430 | 0.066218 | 0.74461 | 4.3495 | 1 | 20.3495 | 36543.5406 | 1 | 20.3495 | 42543.5406
431 | 0.97474 | 0.78102 | 4.5269 | 0 | 16 | 0 | 0 | 16 | 6000
432 | 0.66458 | 0.075777 | 1.7811 | 0 | 16 | 0 | 0 | 16 | 6000
433 | 0.28526 | 0.049773 | 1.6287 | 1 | 17.6287 | 13029.5912 | 0 | 16 | 6000
434 | 0.40857 | 0.63655 | 3.8884 | 1 | 19.8884 | 31107.0172 | 0 | 16 | 6000
435 | 0.82056 | 0.37984 | 2.9665 | 0 | 16 | 0 | 0 | 16 | 6000
436 | 0.37234 | 0.19628 | 2.3124 | 1 | 18.3124 | 18499.5482 | 0 | 16 | 6000
437 | 0.051069 | 0.69053 | 4.109 | 1 | 20.109 | 33416.535 | 1 | 20.109 | 39416.535
438 | 0.43695 | 0.57673 | 3.6598 | 1 | 19.6598 | 29278.0281 | 0 | 16 | 6000
439 | 0.70085 | 0.40007 | 3.036 | 0 | 16 | 0 | 0 | 16 | 6000
440 | 0.84985 | 0.48068 | 3.3147 | 0 | 16 | 0 | 0 | 16 | 6000
441 | 0.5392 | 0.81571 | 4.7119 | 0 | 16 | 0 | 0 | 16 | 6000
442 | 0.29944 | 0.73182 | 4.2904 | 1 | 20.2904 | 35775.5337 | 0 | 16 | 6000
443 | 0.27135 | 0.7613 | 4.429 | 1 | 20.429 | 37577.208 | 0 | 16 | 6000
444 | 0.61294 | 0.95627 | 5.858 | 0 | 16 | 0 | 0 | 16 | 6000
445 | 0.47383 | 0.72728 | 4.2698 | 1 | 20.2698 | 35507.7615 | 0 | 16 | 6000
446 | 0.064339 | 0.71574 | 4.2182 | 1 | 20.2182 | 34836.459 | 1 | 20.2182 | 40836.459
447 | 0.54122 | 0.23083 | 2.4424 | 0 | 16 | 0 | 0 | 16 | 6000
448 | 0.80153 | 0.19709 | 2.3155 | 0 | 16 | 0 | 0 | 16 | 6000
449 | 0.50434 | 0.64459 | 3.9202 | 0 | 16 | 0 | 0 | 16 | 6000
450 | 0.088783 | 0.56689 | 3.6234 | 1 | 19.6234 | 28986.9769 | 1 | 19.6234 | 34986.9769
451 | 0.11424 | 0.91197 | 5.3743 | 1 | 21.3743 | 49865.2645 | 1 | 21.3743 | 55865.2645
452 | 0.2242 | 0.57407 | 3.6499 | 1 | 19.6499 | 29199.1896 | 0 | 16 | 6000
453 | 0.93832 | 0.44559 | 3.1927 | 0 | 16 | 0 | 0 | 16 | 6000
454 | 0.011119 | 0.3816 | 2.9725 | 1 | 18.9725 | 23780.3718 | 1 | 18.9725 | 29780.3718
455 | 0.59363 | 0.54124 | 3.5298 | 0 | 16 | 0 | 0 | 16 | 6000
456 | 0.96275 | 0.094435 | 1.8772 | 0 | 16 | 0 | 0 | 16 | 6000
457 | 0.11467 | 0.38039 | 2.9684 | 1 | 18.9684 | 23747.2612 | 1 | 18.9684 | 29747.2612
458 | 0.43616 | 0.81632 | 4.7153 | 1 | 20.7153 | 41299.2156 | 0 | 16 | 6000
459 | 0.17419 | 0.022901 | 1.4258 | 1 | 17.4258 | 11406.2643 | 1 | 17.4258 | 17406.2643
460 | 0.70072 | 0.44638 | 3.1955 | 0 | 16 | 0 | 0 | 16 | 6000
461 | 0.04087 | 0.92995 | 5.545 | 1 | 21.545 | 52085.6468 | 1 | 21.545 | 58085.6468
462 | 0.045396 | 0.47734 | 3.303 | 1 | 19.303 | 26424.3377 | 1 | 19.303 | 32424.3377
463 | 0.36096 | 0.95443 | 5.8325 | 1 | 21.8325 | 55822.5045 | 0 | 16 | 6000
464 | 0.42198 | 0.2106 | 2.367 | 1 | 18.367 | 18935.9358 | 0 | 16 | 6000
465 | 0.86048 | 0.52191 | 3.4603 | 0 | 16 | 0 | 0 | 16 | 6000
466 | 0.15945 | 0.13606 | 2.0684 | 1 | 18.0684 | 16546.9354 | 1 | 18.0684 | 22546.9354
467 | 0.60039 | 0.060697 | 1.6961 | 0 | 16 | 0 | 0 | 16 | 6000
468 | 0.34621 | 0.68188 | 4.0725 | 1 | 20.0725 | 32942.3231 | 0 | 16 | 6000
469 | 0.71575 | 0.65804 | 3.9743 | 0 | 16 | 0 | 0 | 16 | 6000
470 | 0.14039 | 0.01922 | 1.3905 | 1 | 17.3905 | 11124.0258 | 1 | 17.3905 | 17124.0258
471 | 0.64826 | 0.37951 | 2.9654 | 0 | 16 | 0 | 0 | 16 | 6000
472 | 0.55153 | 0.1275 | 2.031 | 0 | 16 | 0 | 0 | 16 | 6000
473 | 0.14116 | 0.16489 | 2.1887 | 1 | 18.1887 | 17509.894 | 1 | 18.1887 | 23509.894
474 | 0.71232 | 0.20588 | 2.3491 | 0 | 16 | 0 | 0 | 16 | 6000
475 | 0.21185 | 0.81693 | 4.7188 | 1 | 20.7188 | 41344.2578 | 0 | 16 | 6000
476 | 0.37332 | 0.80984 | 4.6793 | 1 | 20.6793 | 40830.5345 | 0 | 16 | 6000
477 | 0.50168 | 0.57643 | 3.6586 | 0 | 16 | 0 | 0 | 16 | 6000
478 | 0.35729 | 0.47003 | 3.2775 | 1 | 19.2775 | 26220.2733 | 0 | 16 | 6000
479 | 0.40354 | 0.54442 | 3.5413 | 1 | 19.5413 | 28330.3217 | 0 | 16 | 6000
480 | 0.89219 | 0.61979 | 3.8229 | 0 | 16 | 0 | 0 | 16 | 6000
481 | 0.58086 | 0.62959 | 3.861 | 0 | 16 | 0 | 0 | 16 | 6000
482 | 0.016748 | 0.23053 | 2.4413 | 1 | 18.4413 | 19530.3709 | 1 | 18.4413 | 25530.3709
483 | 0.41453 | 0.97646 | 6.2028 | 1 | 22.2028 | 60635.7882 | 0 | 16 | 6000
484 | 0.74157 | 0.91162 | 5.3711 | 0 | 16 | 0 | 0 | 16 | 6000
485 | 0.55697 | 0.86932 | 5.0435 | 0 | 16 | 0 | 0 | 16 | 6000
486 | 0.46525 | 0.90653 | 5.3271 | 1 | 21.3271 | 49251.7815 | 0 | 16 | 6000
487 | 0.99205 | 0.66496 | 4.0024 | 0 | 16 | 0 | 0 | 16 | 6000
488 | 0.48111 | 0.71106 | 4.1976 | 1 | 20.1976 | 34568.3248 | 0 | 16 | 6000
489 | 0.95112 | 0.46368 | 3.2554 | 0 | 16 | 0 | 0 | 16 | 6000
490 | 0.69018 | 0.047401 | 1.6132 | 0 | 16 | 0 | 0 | 16 | 6000
491 | 0.58193 | 0.30395 | 2.7042 | 0 | 16 | 0 | 0 | 16 | 6000
492 | 0.76617 | 0.29201 | 2.6623 | 0 | 16 | 0 | 0 | 16 | 6000
493 | 0.60161 | 0.49827 | 3.3765 | 0 | 16 | 0 | 0 | 16 | 6000
494 | 0.99739 | 0.87145 | 5.0583 | 0 | 16 | 0 | 0 | 16 | 6000
495 | 0.087872 | 0.91322 | 5.3853 | 1 | 21.3853 | 50009.1352 | 1 | 21.3853 | 56009.1352
496 | 0.76635 | 0.11141 | 1.9583 | 0 | 16 | 0 | 0 | 16 | 6000
497 | 0.7475 | 0.92001 | 5.4475 | 0 | 16 | 0 | 0 | 16 | 6000
498 | 0.30019 | 0.55561 | 3.582 | 1 | 19.582 | 28656.0303 | 0 | 16 | 6000
499 | 0.15272 | 0.36868 | 2.9282 | 1 | 18.9282 | 23425.3742 | 1 | 18.9282 | 29425.3742
500 | 0.49288 | 0.43232 | 3.1469 | 1 | 19.1469 | 25175.3564 | 0 | 16 | 6000
501 | 0.189 | 0.98205 | 6.3339 | 1 | 22.3339 | 62341.0102 | 1 | 22.3339 | 68341.0102
502 | 0.018553 | 0.17641 | 2.2349 | 1 | 18.2349 | 17879.0615 | 1 | 18.2349 | 23879.0615
503 | 0.29904 | 0.2486 | 2.5074 | 1 | 18.5074 | 20058.9317 | 0 | 16 | 6000
504 | 0.060251 | 0.40278 | 3.0453 | 1 | 19.0453 | 24362.3771 | 1 | 19.0453 | 30362.3771
505 | 0.23971 | 0.33287 | 2.8047 | 1 | 18.8047 | 22437.8305 | 0 | 16 | 6000
506 | 0.10751 | 0.86473 | 5.0122 | 1 | 21.0122 | 45158.7145 | 1 | 21.0122 | 51158.7145
507 | 0.78604 | 0.014772 | 1.3432 | 0 | 16 | 0 | 0 | 16 | 6000
508 | 0.031746 | 0.6662 | 4.0075 | 1 | 20.0075 | 32097.689 | 1 | 20.0075 | 38097.689
509 | 0.27048 | 0.35548 | 2.8828 | 1 | 18.8828 | 23062.094 | 0 | 16 | 6000
510 | 0.48514 | 0.94511 | 5.7131 | 1 | 21.7131 | 54270.4111 | 0 | 16 | 6000
511 | 0.12031 | 0.35923 | 2.8957 | 1 | 18.8957 | 23165.5425 | 1 | 18.8957 | 29165.5425
512 | 0.76248 | 0.58898 | 3.7055 | 0 | 16 | 0 | 0 | 16 | 6000
513 | 0.36584 | 0.51071 | 3.4205 | 1 | 19.4205 | 27363.9201 | 0 | 16 | 6000
514 | 0.035472 | 0.34873 | 2.8595 | 1 | 18.8595 | 22876.1091 | 1 | 18.8595 | 28876.1091
515 | 0.69394 | 0.017256 | 1.3703 | 0 | 16 | 0 | 0 | 16 | 6000
516 | 0.48741 | 0.17382 | 2.2246 | 1 | 18.2246 | 17796.5488 | 0 | 16 | 6000
517 | 0.18882 | 0.3015 | 2.6956 | 1 | 18.6956 | 21564.6515 | 1 | 18.6956 | 27564.6515
518 | 0.21516 | 0.11283 | 1.9649 | 1 | 17.9649 | 15718.8819 | 0 | 16 | 6000
519 | 0.28434 | 0.76454 | 4.4448 | 1 | 20.4448 | 37782.2447 | 0 | 16 | 6000
520 | 0.58333 | 0.77314 | 4.4872 | 0 | 16 | 0 | 0 | 16 | 6000
521 | 0.83783 | 0.71578 | 4.2184 | 0 | 16 | 0 | 0 | 16 | 6000
522 | 0.20443 | 0.38227 | 2.9748 | 1 | 18.9748 | 23798.7952 | 0 | 16 | 6000
523 | 0.29824 | 0.75071 | 4.3782 | 1 | 20.3782 | 36917.0197 | 0 | 16 | 6000
524 | 0.61708 | 0.6302 | 3.8634 | 0 | 16 | 0 | 0 | 16 | 6000
525 | 0.86893 | 0.23769 | 2.4676 | 0 | 16 | 0 | 0 | 16 | 6000
526 | 0.27073 | 0.65559 | 3.9644 | 1 | 19.9644 | 31715.0047 | 0 | 16 | 6000
527 | 0.84926 | 0.011106 | 1.2986 | 0 | 16 | 0 | 0 | 16 | 6000
528 | 0.91214 | 0.26754 | 2.5755 | 0 | 16 | 0 | 0 | 16 | 6000
529 | 0.32428 | 0.64163 | 3.9085 | 1 | 19.9085 | 31267.7404 | 0 | 16 | 6000
530 | 0.91588 | 0.065965 | 1.7267 | 0 | 16 | 0 | 0 | 16 | 6000
531 | 0.46824 | 0.81095 | 4.6854 | 1 | 20.6854 | 40910.6496 | 0 | 16 | 6000
532 | 0.4962 | 0.60139 | 3.7523 | 1 | 19.7523 | 30018.6075 | 0 | 16 | 6000
533 | 0.71494 | 0.62799 | 3.8548 | 0 | 16 | 0 | 0 | 16 | 6000
534 | 0.014323 | 0.88915 | 5.1871 | 1 | 21.1871 | 47432.9363 | 1 | 21.1871 | 53432.9363
535 | 0.24495 | 0.42807 | 3.1323 | 1 | 19.1323 | 25058.0473 | 0 | 16 | 6000
536 | 0.84419 | 0.3502 | 2.8646 | 0 | 16 | 0 | 0 | 16 | 6000
537 | 0.43716 | 0.6065 | 3.7718 | 1 | 19.7718 | 30174.5203 | 0 | 16 | 6000
538 | 0.35035 | 0.27818 | 2.6134 | 1 | 18.6134 | 20907.2848 | 0 | 16 | 6000
539 | 0.52137 | 0.17884 | 2.2445 | 0 | 16 | 0 | 0 | 16 | 6000
540 | 0.39549 | 0.21292 | 2.3757 | 1 | 18.3757 | 19005.751 | 0 | 16 | 6000
541 | 0.12354 | 0.97063 | 6.0872 | 1 | 22.0872 | 59134.2051 | 1 | 22.0872 | 65134.2051
542 | 0.82358 | 0.95854 | 5.8904 | 0 | 16 | 0 | 0 | 16 | 6000
543 | 0.41735 | 0.2605 | 2.5503 | 1 | 18.5503 | 20402.6056 | 0 | 16 | 6000
544 | 0.89996 | 0.25536 | 2.5318 | 0 | 16 | 0 | 0 | 16 | 6000
545 | 0.42913 | 0.62103 | 3.8277 | 1 | 19.8277 | 30621.4642 | 0 | 16 | 6000
546 | 0.21206 | 0.48566 | 3.3321 | 1 | 19.3321 | 26657.1312 | 0 | 16 | 6000
547 | 0.791 | 0.59982 | 3.7464 | 0 | 16 | 0 | 0 | 16 | 6000
548 | 0.33345 | 0.1431 | 2.0985 | 1 | 18.0985 | 16787.9454 | 0 | 16 | 6000
549 | 0.44741 | 0.46572 | 3.2625 | 1 | 19.2625 | 26100.2411 | 0 | 16 | 6000
550 | 0.27733 | 0.38908 | 2.9982 | 1 | 18.9982 | 23985.948 | 0 | 16 | 6000
551 | 0.37966 | 0.10983 | 1.951 | 1 | 17.951 | 15607.8148 | 0 | 16 | 6000
552 | 0.90481 | 0.7964 | 4.6067 | 0 | 16 | 0 | 0 | 16 | 6000
553 | 0.60547 | 0.25597 | 2.534 | 0 | 16 | 0 | 0 | 16 | 6000
554 | 0.55519 | 0.36634 | 2.9201 | 0 | 16 | 0 | 0 | 16 | 6000
555 | 0.21181 | 0.28028 | 2.6209 | 1 | 18.6209 | 20966.846 | 0 | 16 | 6000
556 | 0.57782 | 0.29955 | 2.6887 | 0 | 16 | 0 | 0 | 16 | 6000
557 | 0.63923 | 0.85941 | 4.9768 | 0 | 16 | 0 | 0 | 16 | 6000
558 | 0.73916 | 0.88493 | 5.1553 | 0 | 16 | 0 | 0 | 16 | 6000
559 | 0.88273 | 0.75264 | 4.3874 | 0 | 16 | 0 | 0 | 16 | 6000
560 | 0.48631 | 0.21818 | 2.3954 | 1 | 18.3954 | 19163.5209 | 0 | 16 | 6000
561 | 0.054681 | 0.38427 | 2.9817 | 1 | 18.9817 | 23853.8628 | 1 | 18.9817 | 29853.8628
562 | 0.11732 | 0.11679 | 1.983 | 1 | 17.983 | 15864.0561 | 1 | 17.983 | 21864.0561
563 | 0.29777 | 0.3415 | 2.8346 | 1 | 18.8346 | 22676.7345 | 0 | 16 | 6000
564 | 0.97664 | 0.14077 | 2.0886 | 0 | 16 | 0 | 0 | 16 | 6000
565 | 0.62215 | 0.030616 | 1.4919 | 0 | 16 | 0 | 0 | 16 | 6000
566 | 0.84392 | 0.10926 | 1.9483 | 0 | 16 | 0 | 0 | 16 | 6000
567 | 0.38877 | 0.4917 | 3.3534 | 1 | 19.3534 | 26826.8142 | 0 | 16 | 6000
568 | 0.7917 | 0.47874 | 3.308 | 0 | 16 | 0 | 0 | 16 | 6000
569 | 0.27563 | 0.797 | 4.6099 | 1 | 20.6099 | 39928.4179 | 0 | 16 | 6000
570 | 0.20052 | 0.9654 | 5.9964 | 1 | 21.9964 | 57952.8048 | 0 | 16 | 6000
571 | 0.64809 | 0.024633 | 1.4414 | 0 | 16 | 0 | 0 | 16 | 6000
572 | 0.95856 | 0.86316 | 5.0017 | 0 | 16 | 0 | 0 | 16 | 6000
573 | 0.20269 | 0.98082 | 6.3027 | 1 | 22.3027 | 61934.9818 | 0 | 16 | 6000
574 | 0.42031 | 0.97778 | 6.2316 | 1 | 22.2316 | 61010.5895 | 0 | 16 | 6000
575 | 0.51562 | 0.40639 | 3.0577 | 0 | 16 | 0 | 0 | 16 | 6000
576 | 0.3707 | 0.74306 | 4.3423 | 1 | 20.3423 | 36449.6838 | 0 | 16 | 6000
577 | 0.76963 | 0.81882 | 4.7295 | 0 | 16 | 0 | 0 | 16 | 6000
578 | 0.77085 | 0.14707 | 2.1153 | 0 | 16 | 0 | 0 | 16 | 6000
579 | 0.051847 | 0.30124 | 2.6947 | 1 | 18.6947 | 21557.3973 | 1 | 18.6947 | 27557.3973
580 | 0.33065 | 0.38784 | 2.994 | 1 | 18.994 | 23951.9784 | 0 | 16 | 6000
581 | 0.56937 | 0.2737 | 2.5975 | 0 | 16 | 0 | 0 | 16 | 6000
582 | 0.97572 | 0.37762 | 2.9589 | 0 | 16 | 0 | 0 | 16 | 6000
583 | 0.21613 | 0.39963 | 3.0345 | 1 | 19.0345 | 24275.6193 | 0 | 16 | 6000
584 | 0.448 | 0.54895 | 3.5577 | 1 | 19.5577 | 28461.8287 | 0 | 16 | 6000
585 | 0.18773 | 0.44692 | 3.1973 | 1 | 19.1973 | 25578.7127 | 1 | 19.1973 | 31578.7127
586 | 0.94009 | 0.13157 | 2.0489 | 0 | 16 | 0 | 0 | 16 | 6000
587 | 0.80062 | 0.24342 | 2.4885 | 0 | 16 | 0 | 0 | 16 | 6000
588 | 0.32881 | 0.89028 | 5.1958 | 1 | 21.1958 | 47545.7581 | 0 | 16 | 6000
589 | 0.46196 | 0.92702 | 5.5154 | 1 | 21.5154 | 51700.7272 | 0 | 16 | 6000
590 | 0.01371 | 0.55259 | 3.571 | 1 | 19.571 | 28567.886 | 1 | 19.571 | 34567.886
591 | 0.074472 | 0.50516 | 3.4008 | 1 | 19.4008 | 27206.6383 | 1 | 19.4008 | 33206.6383
592 | 0.75695 | 0.14284 | 2.0974 | 0 | 16 | 0 | 0 | 16 | 6000
593 | 0.221 | 0.84057 | 4.8573 | 1 | 20.8573 | 43144.4286 | 0 | 16 | 6000
594 | 0.7515 | 0.57081 | 3.6378 | 0 | 16 | 0 | 0 | 16 | 6000
595 | 0.58892 | 0.19624 | 2.3123 | 0 | 16 | 0 | 0 | 16 | 6000
596 | 0.51601 | 0.89859 | 5.2613 | 0 | 16 | 0 | 0 | 16 | 6000
597 | 0.43263 | 0.071014 | 1.7551 | 1 | 17.7551 | 14040.6093 | 0 | 16 | 6000
598 | 0.94071 | 0.78118 | 4.5277 | 0 | 16 | 0 | 0 | 16 | 6000
599 | 0.074234 | 0.41871 | 3.1 | 1 | 19.1 | 24800.2957 | 1 | 19.1 | 30800.2957
600 | 0.15237 | 0.88401 | 5.1485 | 1 | 21.1485 | 46930.5958 | 1 | 21.1485 | 52930.5958
601 | 0.65449 | 0.92972 | 5.5427 | 0 | 16 | 0 | 0 | 16 | 6000
602 | 0.46976 | 0.99017 | 6.5894 | 1 | 22.5894 | 65661.6307 | 0 | 16 | 6000
603 | 0.076119 | 0.23287 | 2.4499 | 1 | 18.4499 | 19599.2978 | 1 | 18.4499 | 25599.2978
604 | 0.80813 | 0.59079 | 3.7123 | 0 | 16 | 0 | 0 | 16 | 6000
605 | 0.92072 | 0.37347 | 2.9446 | 0 | 16 | 0 | 0 | 16 | 6000
606 | 0.0023011 | 0.46828 | 3.2714 | 1 | 19.2714 | 26171.4345 | 1 | 19.2714 | 32171.4345
607 | 0.13818 | 0.15757 | 2.1589 | 1 | 18.1589 | 17270.9222 | 1 | 18.1589 | 23270.9222
608 | 0.21447 | 0.20233 | 2.3356 | 1 | 18.3356 | 18684.862 | 0 | 16 | 6000
609 | 0.42168 | 0.5642 | 3.6134 | 1 | 19.6134 | 28907.5264 | 0 | 16 | 6000
610 | 0.82658 | 0.028393 | 1.4738 | 0 | 16 | 0 | 0 | 16 | 6000
611 | 0.061903 | 0.34444 | 2.8447 | 1 | 18.8447 | 22757.8744 | 1 | 18.8447 | 28757.8744
612 | 0.42091 | 0.098318 | 1.8962 | 1 | 17.8962 | 15169.6334 | 0 | 16 | 6000
613 | 0.76871 | 0.25452 | 2.5288 | 0 | 16 | 0 | 0 | 16 | 6000
614 | 0.98773 | 0.65283 | 3.9532 | 0 | 16 | 0 | 0 | 16 | 6000
615 | 0.067631 | 0.90712 | 5.3321 | 1 | 21.3321 | 49317.0433 | 1 | 21.3321 | 55317.0433
616 | 0.45159 | 0.80336 | 4.644 | 1 | 20.644 | 40371.4681 | 0 | 16 | 6000
617 | 0.72235 | 0.28845 | 2.6497 | 0 | 16 | 0 | 0 | 16 | 6000
618 | 0.49376 | 0.049808 | 1.6289 | 1 | 17.6289 | 13031.3972 | 0 | 16 | 6000
619 | 0.039742 | 0.33742 | 2.8205 | 1 | 18.8205 | 22563.8765 | 1 | 18.8205 | 28563.8765
620 | 0.91753 | 0.73511 | 4.3055 | 0 | 16 | 0 | 0 | 16 | 6000
621 | 0.76463 | 0.42189 | 3.111 | 0 | 16 | 0 | 0 | 16 | 6000
622 | 0.95725 | 0.56636 | 3.6214 | 0 | 16 | 0 | 0 | 16 | 6000
623 | 0.60495 | 0.89449 | 5.2286 | 0 | 16 | 0 | 0 | 16 | 6000
624 | 0.23439 | 0.22179 | 2.4089 | 1 | 18.4089 | 19271.4039 | 0 | 16 | 6000
625 | 0.54774 | 0.54422 | 3.5406 | 0 | 16 | 0 | 0 | 16 | 6000
626 | 0.63366 | 0.10141 | 1.9111 | 0 | 16 | 0 | 0 | 16 | 6000
627 | 0.28107 | 0.25762 | 2.54 | 1 | 18.54 | 20319.6238 | 0 | 16 | 6000
628 | 0.48855 | 0.58863 | 3.7042 | 1 | 19.7042 | 29633.4147 | 0 | 16 | 6000
629 | 0.43125 | 0.88735 | 5.1735 | 1 | 21.1735 | 47255.716 | 0 | 16 | 6000
630 | 0.4115 | 0.53636 | 3.5122 | 1 | 19.5122 | 28097.4503 | 0 | 16 | 6000
631 | 0.12178 | 0.50085 | 3.3856 | 1 | 19.3856 | 27084.7968 | 1 | 19.3856 | 33084.7968
632 | 0.95187 | 0.89252 | 5.2132 | 0 | 16 | 0 | 0 | 16 | 6000
633 | 0.012524 | 0.98326 | 6.3657 | 1 | 22.3657 | 62754.4699 | 1 | 22.3657 | 68754.4699
634 | 0.55755 | 0.81685 | 4.7183 | 0 | 16 | 0 | 0 | 16 | 6000
635 | 0.2317 | 0.065504 | 1.7241 | 1 | 17.7241 | 13792.4142 | 0 | 16 | 6000
636 | 0.88939 | 0.48897 | 3.3438 | 0 | 16 | 0 | 0 | 16 | 6000
637 | 0.2622 | 0.26197 | 2.5556 | 1 | 18.5556 | 20444.6584 | 0 | 16 | 6000
638 | 0.38176 | 0.22079 | 2.4052 | 1 | 18.4052 | 19241.4609 | 0 | 16 | 6000
639 | 0.24772 | 0.60496 | 3.7659 | 1 | 19.7659 | 30127.5511 | 0 | 16 | 6000
640 | 0.92336 | 0.64556 | 3.9241 | 0 | 16 | 0 | 0 | 16 | 6000
641 | 0.5351 | 0.16101 | 2.173 | 0 | 16 | 0 | 0 | 16 | 6000
642 | 0.006299 | 0.85492 | 4.9474 | 1 | 20.9474 | 44316.686 | 1 | 20.9474 | 50316.686
643 | 0.85783 | 0.87235 | 5.0645 | 0 | 16 | 0 | 0 | 16 | 6000
644 | 0.17498 | 0.026254 | 1.4556 | 1 | 17.4556 | 11645.1089 | 1 | 17.4556 | 17645.1089
645 | 0.47767 | 0.45248 | 3.2166 | 1 | 19.2166 | 25732.4508 | 0 | 16 | 6000
646 | 0.51228 | 0.71703 | 4.2239 | 0 | 16 | 0 | 0 | 16 | 6000
647 | 0.86381 | 0.49281 | 3.3573 | 0 | 16 | 0 | 0 | 16 | 6000
648 | 0.77584 | 0.0056155 | 1.2148 | 0 | 16 | 0 | 0 | 16 | 6000
649 | 0.21224 | 0.24665 | 2.5003 | 1 | 18.5003 | 20002.3715 | 0 | 16 | 6000
650 | 0.3896 | 0.86151 | 4.9906 | 1 | 20.9906 | 44877.9689 | 0 | 16 | 6000
651 | 0.17417 | 0.83517 | 4.8246 | 1 | 20.8246 | 42720.1758 | 1 | 20.8246 | 48720.1758
652 | 0.15877 | 0.15694 | 2.1563 | 1 | 18.1563 | 17250.3751 | 1 | 18.1563 | 23250.3751
653 | 0.36174 | 0.47647 | 3.3 | 1 | 19.3 | 26399.9645 | 0 | 16 | 6000
654 | 0.8592 | 0.59032 | 3.7105 | 0 | 16 | 0 | 0 | 16 | 6000
655 | 0.2897 | 0.15237 | 2.1374 | 1 | 18.1374 | 17099.1094 | 0 | 16 | 6000
656 | 0.57142 | 0.76961 | 4.4697 | 0 | 16 | 0 | 0 | 16 | 6000
657 | 0.44195 | 0.2261 | 2.4249 | 1 | 18.4249 | 19399.3783 | 0 | 16 | 6000
658 | 0.30244 | 0.45066 | 3.2103 | 1 | 19.2103 | 25682.0763 | 0 | 16 | 6000
659 | 0.87317 | 0.90965 | 5.3539 | 0 | 16 | 0 | 0 | 16 | 6000
660 | 0.10546 | 0.071695 | 1.7588 | 1 | 17.7588 | 14070.6895 | 1 | 17.7588 | 20070.6895
661 | 0.28546 | 0.0016974 | 1.1214 | 1 | 17.1214 | 8971.3559 | 0 | 16 | 6000
662 | 0.52424 | 0.95715 | 5.8704 | 0 | 16 | 0 | 0 | 16 | 6000
663 | 0.76548 | 0.31181 | 2.7316 | 0 | 16 | 0 | 0 | 16 | 6000
664 | 0.019315 | 0.64782 | 3.9331 | 1 | 19.9331 | 31465.1428 | 1 | 19.9331 | 37465.1428
665 | 0.73723 | 0.86558 | 5.0179 | 0 | 16 | 0 | 0 | 16 | 6000
666 | 0.86055 | 0.73404 | 4.3006 | 0 | 16 | 0 | 0 | 16 | 6000
667 | 0.55174 | 0.38159 | 2.9725 | 0 | 16 | 0 | 0 | 16 | 6000
668 | 0.32893 | 0.7894 | 4.57 | 1 | 20.57 | 39409.8471 | 0 | 16 | 6000
669 | 0.6001 | 0.91751 | 5.4242 | 0 | 16 | 0 | 0 | 16 | 6000
670 | 0.76521 | 0.23562 | 2.46 | 0 | 16 | 0 | 0 | 16 | 6000
671 | 0.11903 | 0.0088526 | 1.2675 | 1 | 17.2675 | 10140.3288 | 1 | 17.2675 | 16140.3288
672 | 0.077038 | 0.36317 | 2.9092 | 1 | 18.9092 | 23273.9167 | 1 | 18.9092 | 29273.9167
673 | 0.92471 | 0.32477 | 2.7767 | 0 | 16 | 0 | 0 | 16 | 6000
674 | 0.030452 | 0.84722 | 4.8984 | 1 | 20.8984 | 43679.6255 | 1 | 20.8984 | 49679.6255
675 | 0.4521 | 0.53265 | 3.4988 | 1 | 19.4988 | 27990.6363 | 0 | 16 | 6000
676 | 0.63909 | 0.099598 | 1.9024 | 0 | 16 | 0 | 0 | 16 | 6000
677 | 0.51974 | 0.28861 | 2.6503 | 0 | 16 | 0 | 0 | 16 | 6000
678 | 0.24475 | 0.026987 | 1.4619 | 1 | 17.4619 | 11695.4355 | 0 | 16 | 6000
679 | 0.48366 | 0.045443 | 1.6002 | 1 | 17.6002 | 12801.7662 | 0 | 16 | 6000
680 | 0.087114 | 0.59672 | 3.7347 | 1 | 19.7347 | 29877.2103 | 1 | 19.7347 | 35877.2103
681 | 0.62799 | 0.8623 | 4.9959 | 0 | 16 | 0 | 0 | 16 | 6000
682 | 0.91615 | 0.49361 | 3.3601 | 0 | 16 | 0 | 0 | 16 | 6000
683 | 0.82331 | 0.17917 | 2.2458 | 0 | 16 | 0 | 0 | 16 | 6000
684 | 0.5402 | 0.92644 | 5.5097 | 0 | 16 | 0 | 0 | 16 | 6000
685 | 0.064572 | 0.78917 | 4.5688 | 1 | 20.5688 | 39394.2982 | 1 | 20.5688 | 45394.2982
686 | 0.16074 | 0.042928 | 1.5831 | 1 | 17.5831 | 12665.0038 | 1 | 17.5831 | 18665.0038
687 | 0.53632 | 0.87281 | 5.0677 | 0 | 16 | 0 | 0 | 16 | 6000
688 | 0.33314 | 0.22804 | 2.4321 | 1 | 18.4321 | 19456.9621 | 0 | 16 | 6000
689 | 0.31255 | 0.22718 | 2.4289 | 1 | 18.4289 | 19431.3743 | 0 | 16 | 6000
690 | 0.51831 | 0.10617 | 1.9338 | 0 | 16 | 0 | 0 | 16 | 6000
691 | 0.17825 | 0.7785 | 4.5141 | 1 | 20.5141 | 38683.9217 | 1 | 20.5141 | 44683.9217
692 | 0.22081 | 0.67207 | 4.0317 | 1 | 20.0317 | 32411.8262 | 0 | 16 | 6000
693 | 0.44787 | 0.11052 | 1.9542 | 1 | 17.9542 | 15633.4852 | 0 | 16 | 6000
694 | 0.36348 | 0.21753 | 2.393 | 1 | 18.393 | 19143.957 | 0 | 16 | 6000
695 | 0.7712 | 0.89704 | 5.2488 | 0 | 16 | 0 | 0 | 16 | 6000
696 | 0.68792 | 0.49665 | 3.3708 | 0 | 16 | 0 | 0 | 16 | 6000
697 | 0.9729 | 0.19332 | 2.301 | 0 | 16 | 0 | 0 | 16 | 6000
698 | 0.080858 | 0.21288 | 2.3756 | 1 | 18.3756 | 19004.4036 | 1 | 18.3756 | 25004.4036
699 | 0.4869 | 0.74375 | 4.3455 | 1 | 20.3455 | 36491.5587 | 0 | 16 | 6000
700 | 0.096091 | 0.9421 | 5.6775 | 1 | 21.6775 | 53807.9198 | 1 | 21.6775 | 59807.9198
701 | 0.49866 | 0.80654 | 4.6612 | 1 | 20.6612 | 40595.8304 | 0 | 16 | 6000
702 | 0.69887 | 0.090389 | 1.857 | 0 | 16 | 0 | 0 | 16 | 6000
703 | 0.82608 | 0.33834 | 2.8237 | 0 | 16 | 0 | 0 | 16 | 6000
704 | 0.54654 | 0.623 | 3.8353 | 0 | 16 | 0 | 0 | 16 | 6000
705 | 0.34578 | 0.25386 | 2.5264 | 1 | 18.5264 | 20211.1932 | 0 | 16 | 6000
706 | 0.41018 | 0.73188 | 4.2907 | 1 | 20.2907 | 35779.1324 | 0 | 16 | 6000
707 | 0.65284 | 0.48979 | 3.3466 | 0 | 16 | 0 | 0 | 16 | 6000
708 | 0.8149 | 0.19287 | 2.2993 | 0 | 16 | 0 | 0 | 16 | 6000
709 | 0.88966 | 0.39621 | 3.0227 | 0 | 16 | 0 | 0 | 16 | 6000
710 | 0.021511 | 0.53492 | 3.507 | 1 | 19.507 | 28055.9086 | 1 | 19.507 | 34055.9086
711 | 0.47286 | 0.27249 | 2.5932 | 1 | 18.5932 | 20745.6215 | 0 | 16 | 6000
712 | 0.53485 | 0.69984 | 4.1487 | 0 | 16 | 0 | 0 | 16 | 6000
713 | 0.93558 | 0.035561 | 1.5303 | 0 | 16 | 0 | 0 | 16 | 6000
714 | 0.58115 | 0.96331 | 5.9627 | 0 | 16 | 0 | 0 | 16 | 6000
715 | 0.34685 | 0.91286 | 5.3821 | 1 | 21.3821 | 49967.5667 | 0 | 16 | 6000
716 | 0.33636 | 0.73759 | 4.3169 | 1 | 20.3169 | 36119.8935 | 0 | 16 | 6000
717 | 0.41002 | 0.63563 | 3.8847 | 1 | 19.8847 | 31077.7926 | 0 | 16 | 6000
718 | 0.66989 | 0.14414 | 2.1029 | 0 | 16 | 0 | 0 | 16 | 6000
719 | 0.18299 | 0.51507 | 3.436 | 1 | 19.436 | 27487.8337 | 1 | 19.436 | 33487.8337
720 | 0.15922 | 0.82916 | 4.789 | 1 | 20.789 | 42257.2818 | 1 | 20.789 | 48257.2818
721 | 0.64411 | 0.080227 | 1.8048 | 0 | 16 | 0 | 0 | 16 | 6000
722 | 0.86555 | 0.79996 | 4.6257 | 0 | 16 | 0 | 0 | 16 | 6000
723 | 0.85973 | 0.0060566 | 1.2228 | 0 | 16 | 0 | 0 | 16 | 6000
724 | 0.096384 | 0.15184 | 2.1352 | 1 | 18.1352 | 17081.6581 | 1 | 18.1352 | 23081.6581
725 | 0.086717 | 0.64753 | 3.932 | 1 | 19.932 | 31455.8139 | 1 | 19.932 | 37455.8139
726 | 0.96161 | 0.72818 | 4.2739 | 0 | 16 | 0 | 0 | 16 | 6000
727 | 0.062088 | 0.89732 | 5.2511 | 1 | 21.2511 | 48264.0157 | 1 | 21.2511 | 54264.0157
728 | 0.34252 | 0.46436 | 3.2578 | 1 | 19.2578 | 26062.3706 | 0 | 16 | 6000
729 | 0.71798 | 0.58883 | 3.7049 | 0 | 16 | 0 | 0 | 16 | 6000
730 | 0.87049 | 0.19659 | 2.3136 | 0 | 16 | 0 | 0 | 16 | 6000
731 | 0.2267 | 0.13601 | 2.0682 | 1 | 18.0682 | 16545.4885 | 0 | 16 | 6000
732 | 0.25321 | 0.51694 | 3.4426 | 1 | 19.4426 | 27540.9585 | 0 | 16 | 6000
733 | 0.11266 | 0.87905 | 5.1122 | 1 | 21.1122 | 46458.4244 | 1 | 21.1122 | 52458.4244
734 | 0.81067 | 0.7655 | 4.4495 | 0 | 16 | 0 | 0 | 16 | 6000
735 | 0.95668 | 0.56109 | 3.602 | 0 | 16 | 0 | 0 | 16 | 6000
736 | 0.6928 | 0.28178 | 2.6262 | 0 | 16 | 0 | 0 | 16 | 6000
737 | 0.91725 | 0.84755 | 4.9005 | 0 | 16 | 0 | 0 | 16 | 6000
738 | 0.6421 | 0.19301 | 2.2998 | 0 | 16 | 0 | 0 | 16 | 6000
739 | 0.58125 | 0.36212 | 2.9056 | 0 | 16 | 0 | 0 | 16 | 6000
740 | 0.20081 | 0.47839 | 3.3067 | 1 | 19.3067 | 26453.5868 | 0 | 16 | 6000
741 | 0.62679 | 0.87571 | 5.0882 | 0 | 16 | 0 | 0 | 16 | 6000
742 | 0.38367 | 0.19709 | 2.3156 | 1 | 18.3156 | 18524.4351 | 0 | 16 | 6000
743 | 0.30534 | 0.57299 | 3.6459 | 1 | 19.6459 | 29167.1537 | 0 | 16 | 6000
744 | 0.62825 | 0.33433 | 2.8098 | 0 | 16 | 0 | 0 | 16 | 6000
745 | 0.84071 | 0.4232 | 3.1155 | 0 | 16 | 0 | 0 | 16 | 6000
746 | 0.55917 | 0.80299 | 4.6419 | 0 | 16 | 0 | 0 | 16 | 6000
747 | 0.88428 | 0.47241 | 3.2858 | 0 | 16 | 0 | 0 | 16 | 6000
748 | 0.031723 | 0.75545 | 4.4008 | 1 | 20.4008 | 37210.2851 | 1 | 20.4008 | 43210.2851
749 | 0.16151 | 0.58134 | 3.6769 | 1 | 19.6769 | 29415.2393 | 1 | 19.6769 | 35415.2393
750 | 0.89469 | 0.60875 | 3.7804 | 0 | 16 | 0 | 0 | 16 | 6000
751 | 0.86348 | 0.42433 | 3.1194 | 0 | 16 | 0 | 0 | 16 | 6000
752 | 0.11078 | 0.42747 | 3.1302 | 1 | 19.1302 | 25041.4574 | 1 | 19.1302 | 31041.4574
753 | 0.83151 | 0.25663 | 2.5364 | 0 | 16 | 0 | 0 | 16 | 6000
754 | 0.95792 | 0.14739 | 2.1166 | 0 | 16 | 0 | 0 | 16 | 6000
755 | 0.69721 | 0.79854 | 4.6181 | 0 | 16 | 0 | 0 | 16 | 6000
756 | 0.23968 | 0.74365 | 4.345 | 1 | 20.345 | 36485.551 | 0 | 16 | 6000
757 | 0.91599 | 0.33023 | 2.7956 | 0 | 16 | 0 | 0 | 16 | 6000
758 | 0.26153 | 0.31111 | 2.7292 | 1 | 18.7292 | 21833.2837 | 0 | 16 | 6000
759 | 0.50644 | 0.88631 | 5.1656 | 0 | 16 | 0 | 0 | 16 | 6000
760 | 0.33375 | 0.95703 | 5.8686 | 1 | 21.8686 | 56292.2234 | 0 | 16 | 6000
761 | 0.77518 | 0.56943 | 3.6327 | 0 | 16 | 0 | 0 | 16 | 6000
762 | 0.68235 | 0.96452 | 5.982 | 0 | 16 | 0 | 0 | 16 | 6000
763 | 0.12812 | 0.48905 | 3.3441 | 1 | 19.3441 | 26752.4053 | 1 | 19.3441 | 32752.4053
764 | 0.32339 | 0.92921 | 5.5375 | 1 | 21.5375 | 51987.4231 | 0 | 16 | 6000
765 | 0.51293 | 0.33947 | 2.8276 | 0 | 16 | 0 | 0 | 16 | 6000
766 | 0.1044 | 0.88118 | 5.1277 | 1 | 21.1277 | 46659.7027 | 1 | 21.1277 | 52659.7027
767 | 0.12613 | 0.52492 | 3.4711 | 1 | 19.4711 | 27768.8943 | 1 | 19.4711 | 33768.8943
768 | 0.82218 | 0.66926 | 4.0201 | 0 | 16 | 0 | 0 | 16 | 6000
769 | 0.83219 | 0.58525 | 3.6915 | 0 | 16 | 0 | 0 | 16 | 6000
770 | 0.74313 | 0.58046 | 3.6736 | 0 | 16 | 0 | 0 | 16 | 6000
771 | 0.47017 | 0.78586 | 4.5517 | 1 | 20.5517 | 39171.9393 | 0 | 16 | 6000
772 | 0.32193 | 0.17772 | 2.2401 | 1 | 18.2401 | 17920.6165 | 0 | 16 | 6000
773 | 0.11654 | 0.093047 | 1.8703 | 1 | 17.8703 | 14962.5455 | 1 | 17.8703 | 20962.5455
774 | 0.70272 | 0.26825 | 2.5781 | 0 | 16 | 0 | 0 | 16 | 6000
775 | 0.91168 | 0.15299 | 2.14 | 0 | 16 | 0 | 0 | 16 | 6000
776 | 0.50522 | 0.80158 | 4.6343 | 0 | 16 | 0 | 0 | 16 | 6000
777 | 0.71105 | 0.022746 | 1.4244 | 0 | 16 | 0 | 0 | 16 | 6000
778 | 0.75771 | 0.95342 | 5.8188 | 0 | 16 | 0 | 0 | 16 | 6000
779 | 0.2315 | 0.83167 | 4.8038 | 1 | 20.8038 | 42449.649 | 0 | 16 | 6000
780 | 0.56973 | 0.23146 | 2.4447 | 0 | 16 | 0 | 0 | 16 | 6000
781 | 0.9782 | 0.91608 | 5.4111 | 0 | 16 | 0 | 0 | 16 | 6000
782 | 0.79775 | 0.0022244 | 1.1381 | 0 | 16 | 0 | 0 | 16 | 6000
783 | 0.66604 | 0.44573 | 3.1932 | 0 | 16 | 0 | 0 | 16 | 6000
784 | 0.26577 | 0.85217 | 4.9297 | 1 | 20.9297 | 44086.4049 | 0 | 16 | 6000
785 | 0.16929 | 0.12349 | 2.0132 | 1 | 18.0132 | 16105.9767 | 1 | 18.0132 | 22105.9767
786 | 0.60229 | 0.63337 | 3.8759 | 0 | 16 | 0 | 0 | 16 | 6000
787 | 0.78009 | 0.29126 | 2.6596 | 0 | 16 | 0 | 0 | 16 | 6000
788 | 0.66094 | 0.73319 | 4.2967 | 0 | 16 | 0 | 0 | 16 | 6000
789 | 0.96491 | 0.99302 | 6.7154 | 0 | 16 | 0 | 0 | 16 | 6000
790 | 0.75492 | 0.28976 | 2.6543 | 0 | 16 | 0 | 0 | 16 | 6000
791 | 0.44067 | 0.26116 | 2.5527 | 1 | 18.5527 | 20421.5228 | 0 | 16 | 6000
792 | 0.37926 | 0.15648 | 2.1544 | 1 | 18.1544 | 17234.9462 | 0 | 16 | 6000
793 | 0.70123 | 0.15656 | 2.1547 | 0 | 16 | 0 | 0 | 16 | 6000
794 | 0.77955 | 0.41358 | 3.0824 | 0 | 16 | 0 | 0 | 16 | 6000
795 | 0.44594 | 0.95927 | 5.9011 | 1 | 21.9011 | 56713.6836 | 0 | 16 | 6000
796 | 0.70185 | 0.047327 | 1.6128 | 0 | 16 | 0 | 0 | 16 | 6000
797 | 0.82998 | 0.59207 | 3.7171 | 0 | 16 | 0 | 0 | 16 | 6000
798 | 0.79534 | 0.51776 | 3.4455 | 0 | 16 | 0 | 0 | 16 | 6000
799 | 0.55315 | 0.77104 | 4.4768 | 0 | 16 | 0 | 0 | 16 | 6000
800 | 0.60347 | 0.13757 | 2.0749 | 0 | 16 | 0 | 0 | 16 | 6000
801 | 0.7845 | 0.32574 | 2.78 | 0 | 16 | 0 | 0 | 16 | 6000
802 | 0.20598 | 0.56385 | 3.6122 | 1 | 19.6122 | 28897.4288 | 0 | 16 | 6000
803 | 0.30138 | 0.8113 | 4.6874 | 1 | 20.6874 | 40935.8633 | 0 | 16 | 6000
804 | 0.78041 | 0.96186 | 5.94 | 0 | 16 | 0 | 0 | 16 | 6000
805 | 0.092859 | 0.72004 | 4.2373 | 1 | 20.2373 | 35085.1868 | 1 | 20.2373 | 41085.1868
806 | 0.3242 | 0.88921 | 5.1876 | 1 | 21.1876 | 47439.1528 | 0 | 16 | 6000
807 | 0.038364 | 0.36601 | 2.919 | 1 | 18.919 | 23352.0988 | 1 | 18.919 | 29352.0988
808 | 0.40452 | 0.70907 | 4.1888 | 1 | 20.1888 | 34454.8634 | 0 | 16 | 6000
809 | 0.16861 | 0.75419 | 4.3948 | 1 | 20.3948 | 37132.1371 | 1 | 20.3948 | 43132.1371
810 | 0.087422 | 0.54271 | 3.5351 | 1 | 19.5351 | 28280.6773 | 1 | 19.5351 | 34280.6773
811 | 0.8678 | 0.59763 | 3.7381 | 0 | 16 | 0 | 0 | 16 | 6000
812 | 0.65499 | 0.73728 | 4.3155 | 0 | 16 | 0 | 0 | 16 | 6000
813 | 0.3075 | 0.41584 | 3.0902 | 1 | 19.0902 | 24721.2698 | 0 | 16 | 6000
814 | 0.5776 | 0.36712 | 2.9228 | 0 | 16 | 0 | 0 | 16 | 6000
815 | 0.3131 | 0.98212 | 6.3357 | 1 | 22.3357 | 62363.6882 | 0 | 16 | 6000
816 | 0.0018839 | 0.27755 | 2.6112 | 1 | 18.6112 | 20889.3782 | 1 | 18.6112 | 26889.3782
817 | 0.15422 | 0.41836 | 3.0988 | 1 | 19.0988 | 24790.7163 | 1 | 19.0988 | 30790.7163
818 | 0.87838 | 0.63054 | 3.8647 | 0 | 16 | 0 | 0 | 16 | 6000
819 | 0.93576 | 0.091521 | 1.8627 | 0 | 16 | 0 | 0 | 16 | 6000
820 | 0.98529 | 0.83545 | 4.8263 | 0 | 16 | 0 | 0 | 16 | 6000
821 | 0.88569 | 0.45199 | 3.2149 | 0 | 16 | 0 | 0 | 16 | 6000
822 | 0.10206 | 0.72419 | 4.2559 | 1 | 20.2559 | 35326.4289 | 1 | 20.2559 | 41326.4289
823 | 0.099916 | 0.99114 | 6.6291 | 1 | 22.6291 | 66178.851 | 1 | 22.6291 | 72178.851
824 | 0.14748 | 0.47933 | 3.31 | 1 | 19.31 | 26480.074 | 1 | 19.31 | 32480.074
825 | 0.45442 | 0.13915 | 2.0817 | 1 | 18.0817 | 16653.2251 | 0 | 16 | 6000
826 | 0.14947 | 0.43948 | 3.1716 | 1 | 19.1716 | 25372.927 | 1 | 19.1716 | 31372.927
827 | 0.32941 | 0.53878 | 3.5209 | 1 | 19.5209 | 28167.2107 | 0 | 16 | 6000
828 | 0.57489 | 0.73146 | 4.2888 | 0 | 16 | 0 | 0 | 16 | 6000
829 | 0.61673 | 0.46371 | 3.2556 | 0 | 16 | 0 | 0 | 16 | 6000
830 | 0.55937 | 0.67549 | 4.0458 | 0 | 16 | 0 | 0 | 16 | 6000
831 | 0.25853 | 0.73384 | 4.2997 | 1 | 20.2997 | 35895.9537 | 0 | 16 | 6000
832 | 0.67587 | 0.65155 | 3.9481 | 0 | 16 | 0 | 0 | 16 | 6000
833 | 0.26695 | 0.30627 | 2.7123 | 1 | 18.7123 | 21698.1342 | 0 | 16 | 6000
834 | 0.66801 | 0.054983 | 1.6616 | 0 | 16 | 0 | 0 | 16 | 6000
835 | 0.33056 | 0.38301 | 2.9774 | 1 | 18.9774 | 23819.0926 | 0 | 16 | 6000
836 | 0.12657 | 0.63178 | 3.8696 | 1 | 19.8696 | 30956.7549 | 1 | 19.8696 | 36956.7549
837 | 0.98588 | 0.92327 | 5.4786 | 0 | 16 | 0 | 0 | 16 | 6000
838 | 0.067427 | 0.53368 | 3.5025 | 1 | 19.5025 | 28020.1221 | 1 | 19.5025 | 34020.1221
839 | 0.34048 | 0.98131 | 6.3151 | 1 | 22.3151 | 62095.8395 | 0 | 16 | 6000
840 | 0.64638 | 0.80312 | 4.6427 | 0 | 16 | 0 | 0 | 16 | 6000
841 | 0.029267 | 0.56374 | 3.6118 | 1 | 19.6118 | 28894.2285 | 1 | 19.6118 | 34894.2285
842 | 0.23353 | 0.38978 | 3.0006 | 1 | 19.0006 | 24005.1643 | 0 | 16 | 6000
843 | 0.48289 | 0.66678 | 4.0099 | 1 | 20.0099 | 32128.4916 | 0 | 16 | 6000
844 | 0.391 | 0.82754 | 4.7796 | 1 | 20.7796 | 42134.5944 | 0 | 16 | 6000
845 | 0.3611 | 0.24706 | 2.5018 | 1 | 18.5018 | 20014.1863 | 0 | 16 | 6000
846 | 0.48829 | 0.88333 | 5.1434 | 1 | 21.1434 | 46864.4883 | 0 | 16 | 6000
847 | 0.97166 | 0.1167 | 1.9826 | 0 | 16 | 0 | 0 | 16 | 6000
848 | 0.16373 | 0.075676 | 1.7805 | 1 | 17.7805 | 14244.3874 | 1 | 17.7805 | 20244.3874
849 | 0.14782 | 0.88835 | 5.181 | 1 | 21.181 | 47353.6231 | 1 | 21.181 | 53353.6231
850 | 0.7153 | 0.78624 | 4.5537 | 0 | 16 | 0 | 0 | 16 | 6000
851 | 0.7636 | 0.32685 | 2.7839 | 0 | 16 | 0 | 0 | 16 | 6000
852 | 0.40115 | 0.34733 | 2.8547 | 1 | 18.8547 | 22837.4366 | 0 | 16 | 6000
853 | 0.52177 | 0.081136 | 1.8096 | 0 | 16 | 0 | 0 | 16 | 6000
854 | 0.52338 | 0.44196 | 3.1802 | 0 | 16 | 0 | 0 | 16 | 6000
855 | 0.57439 | 0.92128 | 5.4595 | 0 | 16 | 0 | 0 | 16 | 6000
856 | 0.93812 | 0.40958 | 3.0687 | 0 | 16 | 0 | 0 | 16 | 6000
857 | 0.094895 | 0.97266 | 6.1255 | 1 | 22.1255 | 59631.4085 | 1 | 22.1255 | 65631.4085
858 | 0.16341 | 0.91146 | 5.3698 | 1 | 21.3698 | 49806.8618 | 1 | 21.3698 | 55806.8618
859 | 0.11823 | 0.44817 | 3.2016 | 1 | 19.2016 | 25613.155 | 1 | 19.2016 | 31613.155
860 | 0.29193 | 0.26378 | 2.5621 | 1 | 18.5621 | 20496.5607 | 0 | 16 | 6000
861 | 0.51426 | 0.52436 | 3.4691 | 0 | 16 | 0 | 0 | 16 | 6000
862 | 0.78254 | 0.5325 | 3.4983 | 0 | 16 | 0 | 0 | 16 | 6000
863 | 0.96251 | 0.6722 | 4.0322 | 0 | 16 | 0 | 0 | 16 | 6000
864 | 0.54651 | 0.83904 | 4.848 | 0 | 16 | 0 | 0 | 16 | 6000
865 | 0.95008 | 0.19791 | 2.3187 | 0 | 16 | 0 | 0 | 16 | 6000
866 | 0.92895 | 0.89635 | 5.2433 | 0 | 16 | 0 | 0 | 16 | 6000
867 | 0.5954 | 0.53575 | 3.51 | 0 | 16 | 0 | 0 | 16 | 6000
868 | 0.46467 | 0.72862 | 4.2759 | 1 | 20.2759 | 35586.4349 | 0 | 16 | 6000
869 | 0.5955 | 0.56762 | 3.6261 | 0 | 16 | 0 | 0 | 16 | 6000
870 | 0.89853 | 0.89509 | 5.2333 | 0 | 16 | 0 | 0 | 16 | 6000
871 | 0.99651 | 0.41916 | 3.1016 | 0 | 16 | 0 | 0 | 16 | 6000
872 | 0.71104 | 0.086522 | 1.8375 | 0 | 16 | 0 | 0 | 16 | 6000
873 | 0.993 | 0.50578 | 3.403 | 0 | 16 | 0 | 0 | 16 | 6000
874 | 0.35684 | 0.696 | 4.1323 | 1 | 20.1323 | 33719.3167 | 0 | 16 | 6000
875 | 0.42724 | 0.56369 | 3.6116 | 1 | 19.6116 | 28892.7383 | 0 | 16 | 6000
876 | 0.52121 | 0.74031 | 4.3295 | 0 | 16 | 0 | 0 | 16 | 6000
877 | 0.44757 | 0.051546 | 1.64 | 1 | 17.64 | 13120.2971 | 0 | 16 | 6000
878 | 0.92059 | 0.8713 | 5.0572 | 0 | 16 | 0 | 0 | 16 | 6000
879 | 0.39157 | 0.6623 | 3.9916 | 1 | 19.9916 | 31932.6659 | 0 | 16 | 6000
880 | 0.67621 | 0.65008 | 3.9422 | 0 | 16 | 0 | 0 | 16 | 6000
881 | 0.74092 | 0.12539 | 2.0217 | 0 | 16 | 0 | 0 | 16 | 6000
882 | 0.27553 | 0.61902 | 3.8199 | 1 | 19.8199 | 30559.0903 | 0 | 16 | 6000
883 | 0.83726 | 0.70321 | 4.1633 | 0 | 16 | 0 | 0 | 16 | 6000
884 | 0.1793 | 0.24032 | 2.4772 | 1 | 18.4772 | 19817.9275 | 1 | 18.4772 | 25817.9275
885 | 0.66043 | 0.83413 | 4.8184 | 0 | 16 | 0 | 0 | 16 | 6000
886 | 0.55945 | 0.4385 | 3.1682 | 0 | 16 | 0 | 0 | 16 | 6000
887 | 0.16555 | 0.10117 | 1.91 | 1 | 17.91 | 15279.9896 | 1 | 17.91 | 21279.9896
888 | 0.30841 | 0.71235 | 4.2033 | 1 | 20.2033 | 34642.3424 | 0 | 16 | 6000
889 | 0.16916 | 0.43032 | 3.14 | 1 | 19.14 | 25120.1157 | 1 | 19.14 | 31120.1157
890 | 0.96356 | 0.81776 | 4.7235 | 0 | 16 | 0 | 0 | 16 | 6000
891 | 0.89537 | 0.58845 | 3.7035 | 0 | 16 | 0 | 0 | 16 | 6000
892 | 0.77378 | 0.50491 | 3.3999 | 0 | 16 | 0 | 0 | 16 | 6000
893 | 0.39685 | 0.76744 | 4.459 | 1 | 20.459 | 37966.9455 | 0 | 16 | 6000
894 | 0.55663 | 0.32606 | 2.7812 | 0 | 16 | 0 | 0 | 16 | 6000
895 | 0.63012 | 0.96276 | 5.9541 | 0 | 16 | 0 | 0 | 16 | 6000
896 | 0.074951 | 0.38156 | 2.9724 | 1 | 18.9724 | 23779.5127 | 1 | 18.9724 | 29779.5127
897 | 0.60396 | 0.91231 | 5.3772 | 0 | 16 | 0 | 0 | 16 | 6000
898 | 0.39993 | 0.19376 | 2.3027 | 1 | 18.3027 | 18421.8599 | 0 | 16 | 6000
899 | 0.17321 | 0.46782 | 3.2698 | 1 | 19.2698 | 26158.7628 | 1 | 19.2698 | 32158.7628
900 | 0.34342 | 0.050557 | 1.6337 | 1 | 17.6337 | 13069.856 | 0 | 16 | 6000
901 | 0.25048 | 0.96098 | 5.9266 | 1 | 21.9266 | 57046.3328 | 0 | 16 | 6000
902 | 0.41398 | 0.41982 | 3.1038 | 1 | 19.1038 | 24830.7691 | 0 | 16 | 6000
903 | 0.22555 | 0.38763 | 2.9933 | 1 | 18.9933 | 23946.0833 | 0 | 16 | 6000
904 | 0.5581 | 0.18552 | 2.2707 | 0 | 16 | 0 | 0 | 16 | 6000
905 | 0.58899 | 0.84214 | 4.8669 | 0 | 16 | 0 | 0 | 16 | 6000
906 | 0.44401 | 0.19961 | 2.3252 | 1 | 18.3252 | 18601.7835 | 0 | 16 | 6000
907 | 0.34467 | 0.95954 | 5.9051 | 1 | 21.9051 | 56765.6871 | 0 | 16 | 6000
908 | 0.59876 | 0.8329 | 4.8111 | 0 | 16 | 0 | 0 | 16 | 6000
909 | 0.87994 | 0.56005 | 3.5982 | 0 | 16 | 0 | 0 | 16 | 6000
910 | 0.67063 | 0.40553 | 3.0547 | 0 | 16 | 0 | 0 | 16 | 6000
911 | 0.34847 | 0.47708 | 3.3021 | 1 | 19.3021 | 26417.1915 | 0 | 16 | 6000
912 | 0.39142 | 0.55925 | 3.5953 | 1 | 19.5953 | 28762.2808 | 0 | 16 | 6000
913 | 0.98725 | 0.8001 | 4.6264 | 0 | 16 | 0 | 0 | 16 | 6000
914 | 0.89718 | 0.26156 | 2.5541 | 0 | 16 | 0 | 0 | 16 | 6000
915 | 0.32327 | 0.96419 | 5.9766 | 1 | 21.9766 | 57695.7484 | 0 | 16 | 6000
916 | 0.38525 | 0.55958 | 3.5965 | 1 | 19.5965 | 28772.0368 | 0 | 16 | 6000
917 | 0.0389 | 0.89372 | 5.2225 | 1 | 21.2225 | 47893.0112 | 1 | 21.2225 | 53893.0112
918 | 0.78124 | 0.7871 | 4.5581 | 0 | 16 | 0 | 0 | 16 | 6000
919 | 0.12382 | 0.14375 | 2.1012 | 1 | 18.1012 | 16809.8331 | 1 | 18.1012 | 22809.8331
920 | 0.413 | 0.87907 | 5.1123 | 1 | 21.1123 | 46459.966 | 0 | 16 | 6000
921 | 0.071615 | 0.067299 | 1.7343 | 1 | 17.7343 | 13874.1689 | 1 | 17.7343 | 19874.1689
922 | 0.75169 | 0.78476 | 4.546 | 0 | 16 | 0 | 0 | 16 | 6000
923 | 0.51155 | 0.48387 | 3.3259 | 0 | 16 | 0 | 0 | 16 | 6000
924 | 0.17007 | 0.18467 | 2.2674 | 1 | 18.2674 | 18139.4633 | 1 | 18.2674 | 24139.4633
925 | 0.14765 | 0.25661 | 2.5363 | 1 | 18.5363 | 20290.5949 | 1 | 18.5363 | 26290.5949
926 | 0.8612 | 0.58613 | 3.6948 | 0 | 16 | 0 | 0 | 16 | 6000
927 | 0.61302 | 0.98703 | 6.4773 | 0 | 16 | 0 | 0 | 16 | 6000
928 | 0.32488 | 0.49343 | 3.3594 | 1 | 19.3594 | 26875.5442 | 0 | 16 | 6000
929 | 0.81693 | 0.63036 | 3.864 | 0 | 16 | 0 | 0 | 16 | 6000
930 | 0.28385 | 0.19007 | 2.2885 | 1 | 18.2885 | 18307.747 | 0 | 16 | 6000
931 | 0.36154 | 0.32033 | 2.7613 | 1 | 18.7613 | 22090.1399 | 0 | 16 | 6000
932 | 0.12114 | 0.32001 | 2.7602 | 1 | 18.7602 | 22081.2643 | 1 | 18.7602 | 28081.2643
933 | 0.24594 | 0.83082 | 4.7988 | 1 | 20.7988 | 42384.2442 | 0 | 16 | 6000
934 | 0.16364 | 0.51066 | 3.4203 | 1 | 19.4203 | 27362.4293 | 1 | 19.4203 | 33362.4293
935 | 0.7648 | 0.30036 | 2.6916 | 0 | 16 | 0 | 0 | 16 | 6000
936 | 0.187 | 0.61817 | 3.8166 | 1 | 19.8166 | 30532.9549 | 1 | 19.8166 | 36532.9549
937 | 0.40636 | 0.49039 | 3.3488 | 1 | 19.3488 | 26790.0539 | 0 | 16 | 6000
938 | 0.091682 | 0.9939 | 6.762 | 1 | 22.762 | 67906.2584 | 1 | 22.762 | 73906.2584
939 | 0.217 | 0.76816 | 4.4625 | 1 | 20.4625 | 38013.0814 | 0 | 16 | 6000
940 | 0.98634 | 0.3121 | 2.7326 | 0 | 16 | 0 | 0 | 16 | 6000
941 | 0.99699 | 0.34378 | 2.8425 | 0 | 16 | 0 | 0 | 16 | 6000
942 | 0.47803 | 0.47805 | 3.3055 | 1 | 19.3055 | 26444.2087 | 0 | 16 | 6000
943 | 0.34177 | 0.2727 | 2.5939 | 1 | 18.5939 | 20751.5005 | 0 | 16 | 6000
944 | 0.17166 | 0.81164 | 4.6892 | 1 | 20.6892 | 40960.114 | 1 | 20.6892 | 46960.114
945 | 0.271 | 0.39763 | 3.0276 | 1 | 19.0276 | 24220.7023 | 0 | 16 | 6000
946 | 0.38981 | 0.6531 | 3.9543 | 1 | 19.9543 | 31634.6292 | 0 | 16 | 6000
947 | 0.15687 | 0.8362 | 4.8308 | 1 | 20.8308 | 42800.7369 | 1 | 20.8308 | 48800.7369
948 | 0.14306 | 0.64877 | 3.9369 | 1 | 19.9369 | 31495.3238 | 1 | 19.9369 | 37495.3238
949 | 0.8757 | 0.28497 | 2.6374 | 0 | 16 | 0 | 0 | 16 | 6000
950 | 0.2809 | 0.80451 | 4.6502 | 1 | 20.6502 | 40452.559 | 0 | 16 | 6000
951 | 0.67286 | 0.1591 | 2.1651 | 0 | 16 | 0 | 0 | 16 | 6000
952 | 0.1835 | 0.9278 | 5.5232 | 1 | 21.5232 | 51801.6566 | 1 | 21.5232 | 57801.6566
953 | 0.86044 | 0.53566 | 3.5096 | 0 | 16 | 0 | 0 | 16 | 6000
954 | 0.78713 | 0.39818 | 3.0295 | 0 | 16 | 0 | 0 | 16 | 6000
955 | 0.010589 | 0.28535 | 2.6388 | 1 | 18.6388 | 21110.3107 | 1 | 18.6388 | 27110.3107
956 | 0.22668 | 0.79737 | 4.6119 | 1 | 20.6119 | 39954.2129 | 0 | 16 | 6000
957 | 0.15534 | 0.40213 | 3.043 | 1 | 19.043 | 24344.3175 | 1 | 19.043 | 30344.3175
958 | 0.97829 | 0.27782 | 2.6121 | 0 | 16 | 0 | 0 | 16 | 6000
959 | 0.63912 | 0.68488 | 4.0851 | 0 | 16 | 0 | 0 | 16 | 6000
960 | 0.91659 | 0.96246 | 5.9494 | 0 | 16 | 0 | 0 | 16 | 6000
961 | 0.93414 | 0.58064 | 3.6743 | 0 | 16 | 0 | 0 | 16 | 6000
962 | 0.9682 | 0.067368 | 1.7347 | 0 | 16 | 0 | 0 | 16 | 6000
963 | 0.029438 | 0.72839 | 4.2748 | 1 | 20.2748 | 35572.8233 | 1 | 20.2748 | 41572.8233
964 | 0.61239 | 0.39314 | 3.0122 | 0 | 16 | 0 | 0 | 16 | 6000
965 | 0.67832 | 0.83358 | 4.8151 | 0 | 16 | 0 | 0 | 16 | 6000
966 | 0.99276 | 0.67684 | 4.0514 | 0 | 16 | 0 | 0 | 16 | 6000
967 | 0.71356 | 0.65302 | 3.954 | 0 | 16 | 0 | 0 | 16 | 6000
968 | 0.45363 | 0.45957 | 3.2412 | 1 | 19.2412 | 25929.2146 | 0 | 16 | 6000
969 | 0.21895 | 0.63369 | 3.8771 | 1 | 19.8771 | 31016.7105 | 0 | 16 | 6000
970 | 0.35387 | 0.017512 | 1.373 | 1 | 17.373 | 10984.2703 | 0 | 16 | 6000
971 | 0.93088 | 0.58296 | 3.683 | 0 | 16 | 0 | 0 | 16 | 6000
972 | 0.62884 | 0.74844 | 4.3675 | 0 | 16 | 0 | 0 | 16 | 6000
973 | 0.27118 | 0.38669 | 2.99 | 1 | 18.99 | 23920.3623 | 0 | 16 | 6000
974 | 0.99228 | 0.25005 | 2.5126 | 0 | 16 | 0 | 0 | 16 | 6000
975 | 0.37824 | 0.91387 | 5.3911 | 1 | 21.3911 | 50084.668 | 0 | 16 | 6000
976 | 0.25893 | 0.14236 | 2.0954 | 1 | 18.0954 | 16762.9883 | 0 | 16 | 6000
977 | 0.1733 | 0.18266 | 2.2595 | 1 | 18.2595 | 18076.3281 | 1 | 18.2595 | 24076.3281
978 | 0.22331 | 0.012924 | 1.3215 | 1 | 17.3215 | 10572.017 | 0 | 16 | 6000
979 | 0.038642 | 0.67574 | 4.0468 | 1 | 20.0468 | 32608.8963 | 1 | 20.0468 | 38608.8963
980 | 0.72757 | 0.72568 | 4.2626 | 0 | 16 | 0 | 0 | 16 | 6000
981 | 0.49681 | 0.48075 | 3.315 | 1 | 19.315 | 26519.7416 | 0 | 16 | 6000
982 | 0.82164 | 0.64951 | 3.9399 | 0 | 16 | 0 | 0 | 16 | 6000
983 | 0.76483 | 0.89669 | 5.246 | 0 | 16 | 0 | 0 | 16 | 6000
984 | 0.5655 | 0.96107 | 5.9279 | 0 | 16 | 0 | 0 | 16 | 6000
985 | 0.55767 | 0.84684 | 4.8961 | 0 | 16 | 0 | 0 | 16 | 6000
986 | 0.63472 | 0.95672 | 5.8643 | 0 | 16 | 0 | 0 | 16 | 6000
987 | 0.61988 | 0.19866 | 2.3216 | 0 | 16 | 0 | 0 | 16 | 6000
988 | 0.61839 | 0.24105 | 2.4799 | 0 | 16 | 0 | 0 | 16 | 6000
989 | 0.84094 | 0.99766 | 7.0445 | 0 | 16 | 0 | 0 | 16 | 6000
990 | 0.82203 | 0.49032 | 3.3485 | 0 | 16 | 0 | 0 | 16 | 6000
991 | 0.43773 | 0.86195 | 4.9935 | 1 | 20.9935 | 44915.916 | 0 | 16 | 6000
992 | 0.12295 | 0.69421 | 4.1246 | 1 | 20.1246 | 33619.8882 | 1 | 20.1246 | 39619.8882
993 | 0.21657 | 0.11917 | 1.9938 | 1 | 17.9938 | 15950.4699 | 0 | 16 | 6000
994 | 0.88894 | 0.12668 | 2.0274 | 0 | 16 | 0 | 0 | 16 | 6000
995 | 0.31429 | 0.46327 | 3.254 | 1 | 19.254 | 26032.0618 | 0 | 16 | 6000
996 | 0.24635 | 0.8314 | 4.8022 | 1 | 20.8022 | 42428.7702 | 0 | 16 | 6000
997 | 0.98957 | 0.037385 | 1.5438 | 0 | 16 | 0 | 0 | 16 | 6000
998 | 0.89679 | 0.42535 | 3.1229 | 0 | 16 | 0 | 0 | 16 | 6000
999 | 0.63903 | 0.46784 | 3.2699 | 0 | 16 | 0 | 0 | 16 | 6000
1000 | 0.42812 | 0.4395 | 3.1717 | 1 | 19.1717 | 25373.5072 | 0 | 16 | 6000
1001 | 0.76218 | 0.21905 | 2.3987 | 0 | 16 | 0 | 0 | 16 | 6000
1002 | 0.96226 | 0.80098 | 4.6312 | 0 | 16 | 0 | 0 | 16 | 6000
1003 | 0.15461 | 0.016596 | 1.3633 | 1 | 17.3633 | 10906.6282 | 1 | 17.3633 | 16906.6282
1004 | 0.33165 | 0.22221 | 2.4105 | 1 | 18.4105 | 19283.9195 | 0 | 16 | 6000
1005 | 0.11762 | 0.74519 | 4.3522 | 1 | 20.3522 | 36579.0193 | 1 | 20.3522 | 42579.0193
1006 | 0.087907 | 0.32707 | 2.7847 | 1 | 18.7847 | 22277.2235 | 1 | 18.7847 | 28277.2235
1007 | 0.28742 | 0.77785 | 4.5109 | 1 | 20.5109 | 38641.1975 | 0 | 16 | 6000
1008 | 0.93015 | 0.50051 | 3.3844 | 0 | 16 | 0 | 0 | 16 | 6000
1009 | 0.3906 | 0.32477 | 2.7767 | 1 | 18.7767 | 22213.39 | 0 | 16 | 6000
1010 | 0.51892 | 0.30849 | 2.72 | 0 | 16 | 0 | 0 | 16 | 6000
1011 | 0.71163 | 0.047314 | 1.6127 | 0 | 16 | 0 | 0 | 16 | 6000
1012 | 0.88029 | 0.8192 | 4.7316 | 0 | 16 | 0 | 0 | 16 | 6000
1013 | 0.25501 | 0.011305 | 1.3012 | 1 | 17.3012 | 10409.8521 | 0 | 16 | 6000
1014 | 0.73263 | 0.20158 | 2.3327 | 0 | 16 | 0 | 0 | 16 | 6000
1015 | 0.43865 | 0.33657 | 2.8175 | 1 | 18.8175 | 22540.3624 | 0 | 16 | 6000
1016 | 0.54238 | 0.90052 | 5.277 | 0 | 16 | 0 | 0 | 16 | 6000
1017 | 0.36745 | 0.74944 | 4.3722 | 1 | 20.3722 | 36839.08 | 0 | 16 | 6000
1018 | 0.5773 | 0.11047 | 1.9539 | 0 | 16 | 0 | 0 | 16 | 6000
1019 | 0.70508 | 0.80864 | 4.6727 | 0 | 16 | 0 | 0 | 16 | 6000
1020 | 0.45566 | 0.40499 | 3.0529 | 1 | 19.0529 | 24422.8939 | 0 | 16 | 6000
1021 | 0.763 | 0.69422 | 4.1247 | 0 | 16 | 0 | 0 | 16 | 6000
1022 | 0.24998 | 0.88144 | 5.1296 | 1 | 21.1296 | 46684.3527 | 0 | 16 | 6000
1023 | 0.90021 | 0.7818 | 4.5309 | 0 | 16 | 0 | 0 | 16 | 6000
1024 | 0.26054 | 0.94901 | 5.7614 | 1 | 21.7614 | 54897.6391 | 0 | 16 | 6000
1025 | 0.73979 | 0.029794 | 1.4853 | 0 | 16 | 0 | 0 | 16 | 6000
1026 | 0.8475 | 0.50662 | 3.406 | 0 | 16 | 0 | 0 | 16 | 6000
1027 | 0.009137 | 0.16285 | 2.1805 | 1 | 18.1805 | 17443.6042 | 1 | 18.1805 | 23443.6042
1028 | 0.23468 | 0.66281 | 3.9937 | 1 | 19.9937 | 31949.4028 | 0 | 16 | 6000
1029 | 0.11992 | 0.22702 | 2.4283 | 1 | 18.4283 | 19426.7065 | 1 | 18.4283 | 25426.7065
1030 | 0.10082 | 0.51682 | 3.4422 | 1 | 19.4422 | 27537.7329 | 1 | 19.4422 | 33537.7329
1031 | 0.18451 | 0.23543 | 2.4593 | 1 | 18.4593 | 19674.6883 | 1 | 18.4593 | 25674.6883
1032 | 0.88997 | 0.81175 | 4.6899 | 0 | 16 | 0 | 0 | 16 | 6000
1033 | 0.24889 | 0.93338 | 5.5808 | 1 | 21.5808 | 52550.0145 | 0 | 16 | 6000
1034 | 0.35015 | 0.15093 | 2.1314 | 1 | 18.1314 | 17051.3476 | 0 | 16 | 6000
1035 | 0.67589 | 0.60907 | 3.7816 | 0 | 16 | 0 | 0 | 16 | 6000
1036 | 0.5239 | 0.9695 | 6.0667 | 0 | 16 | 0 | 0 | 16 | 6000
1037 | 0.32855 | 0.60429 | 3.7634 | 1 | 19.7634 | 30107.0366 | 0 | 16 | 6000
1038 | 0.21509 | 0.70773 | 4.183 | 1 | 20.183 | 34378.8947 | 0 | 16 | 6000
1039 | 0.67686 | 0.35496 | 2.881 | 0 | 16 | 0 | 0 | 16 | 6000
1040 | 0.0015428 | 0.34152 | 2.8346 | 1 | 18.8346 | 22677.1225 | 1 | 18.8346 | 28677.1225
1041 | 0.1783 | 0.62314 | 3.8359 | 1 | 19.8359 | 30686.9519 | 1 | 19.8359 | 36686.9519
1042 | 0.25024 | 0.16802 | 2.2014 | 1 | 18.2014 | 17610.9764 | 0 | 16 | 6000
1043 | 0.43314 | 0.55416 | 3.5767 | 1 | 19.5767 | 28613.6473 | 0 | 16 | 6000
1044 | 0.064092 | 0.94057 | 5.6599 | 1 | 21.6599 | 53579.0018 | 1 | 21.6599 | 59579.0018
1045 | 0.20462 | 0.3834 | 2.9788 | 1 | 18.9788 | 23830.0059 | 0 | 16 | 6000
1046 | 0.29992 | 0.95912 | 5.8988 | 1 | 21.8988 | 56684.77 | 0 | 16 | 6000
1047 | 0.86404 | 0.16694 | 2.197 | 0 | 16 | 0 | 0 | 16 | 6000
1048 | 0.88463 | 0.58993 | 3.709 | 0 | 16 | 0 | 0 | 16 | 6000
1049 | 0.3265 | 0.95929 | 5.9014 | 1 | 21.9014 | 56717.9148 | 0 | 16 | 6000
1050 | 0.7452 | 0.20401 | 2.342 | 0 | 16 | 0 | 0 | 16 | 6000
1051 | 0.98554 | 0.64454 | 3.92 | 0 | 16 | 0 | 0 | 16 | 6000
1052 | 0.661 | 0.47067 | 3.2798 | 0 | 16 | 0 | 0 | 16 | 6000
1053 | 0.3947 | 0.007174 | 1.2417 | 1 | 17.2417 | 9933.6787 | 0 | 16 | 6000
1054 | 0.76048 | 0.60427 | 3.7633 | 0 | 16 | 0 | 0 | 16 | 6000
1055 | 0.72161 | 0.38904 | 2.9981 | 0 | 16 | 0 | 0 | 16 | 6000
1056 | 0.76671 | 0.14743 | 2.1168 | 0 | 16 | 0 | 0 | 16 | 6000
1057 | 0.99929 | 0.77779 | 4.5106 | 0 | 16 | 0 | 0 | 16 | 6000
1058 | 0.37153 | 0.64498 | 3.9218 | 1 | 19.9218 | 31374.2094 | 0 | 16 | 6000
1059 | 0.14813 | 0.60264 | 3.7571 | 1 | 19.7571 | 30056.8116 | 1 | 19.7571 | 36056.8116
1060 | 0.9193 | 0.75582 | 4.4026 | 0 | 16 | 0 | 0 | 16 | 6000
1061 | 0.75745 | 0.76633 | 4.4536 | 0 | 16 | 0 | 0 | 16 | 6000
1062 | 0.15592 | 0.28193 | 2.6267 | 1 | 18.6267 | 21013.4957 | 1 | 18.6267 | 27013.4957
1063 | 0.71977 | 0.11826 | 1.9897 | 0 | 16 | 0 | 0 | 16 | 6000
1064 | 0.31312 | 0.039303 | 1.5577 | 1 | 17.5577 | 12461.4425 | 0 | 16 | 6000
1065 | 0.19303 | 0.68237 | 4.0745 | 1 | 20.0745 | 32968.8149 | 1 | 20.0745 | 38968.8149
1066 | 0.82892 | 0.98669 | 6.4665 | 0 | 16 | 0 | 0 | 16 | 6000
1067 | 0.8833 | 0.75698 | 4.4082 | 0 | 16 | 0 | 0 | 16 | 6000
1068 | 0.85593 | 0.87034 | 5.0506 | 0 | 16 | 0 | 0 | 16 | 6000
1069 | 0.64003 | 0.51001 | 3.418 | 0 | 16 | 0 | 0 | 16 | 6000
1070 | 0.68869 | 0.72848 | 4.2753 | 0 | 16 | 0 | 0 | 16 | 6000
1071 | 0.070397 | 0.84194 | 4.8657 | 1 | 20.8657 | 43254.0715 | 1 | 20.8657 | 49254.0715
1072 | 0.48402 | 0.55116 | 3.5657 | 1 | 19.5657 | 28525.9781 | 0 | 16 | 6000
1073 | 0.42674 | 0.13706 | 2.0727 | 1 | 18.0727 | 16581.5609 | 0 | 16 | 6000
1074 | 0.86727 | 0.64247 | 3.9118 | 0 | 16 | 0 | 0 | 16 | 6000
1075 | 0.24661 | 0.35693 | 2.8878 | 1 | 18.8878 | 23102.1401 | 0 | 16 | 6000
1076 | 0.48213 | 0.19686 | 2.3147 | 1 | 18.3147 | 18517.2281 | 0 | 16 | 6000
1077 | 0.59473 | 0.46031 | 3.2437 | 0 | 16 | 0 | 0 | 16 | 6000
1078 | 0.77553 | 0.79448 | 4.5966 | 0 | 16 | 0 | 0 | 16 | 6000
1079 | 0.72807 | 0.48526 | 3.3308 | 0 | 16 | 0 | 0 | 16 | 6000
1080 | 0.55326 | 0.29662 | 2.6785 | 0 | 16 | 0 | 0 | 16 | 6000
1081 | 0.32287 | 0.097277 | 1.8911 | 1 | 17.8911 | 15129.0969 | 0 | 16 | 6000
1082 | 0.89863 | 0.35501 | 2.8812 | 0 | 16 | 0 | 0 | 16 | 6000
1083 | 0.40109 | 0.46932 | 3.2751 | 1 | 19.2751 | 26200.5921 | 0 | 16 | 6000
1084 | 0.93504 | 0.6806 | 4.0671 | 0 | 16 | 0 | 0 | 16 | 6000
1085 | 0.82194 | 0.18014 | 2.2496 | 0 | 16 | 0 | 0 | 16 | 6000
1086 | 0.18834 | 0.1221 | 2.007 | 1 | 18.007 | 16056.2109 | 1 | 18.007 | 22056.2109
1087 | 0.98917 | 0.64407 | 3.9182 | 0 | 16 | 0 | 0 | 16 | 6000
1088 | 0.45604 | 0.52015 | 3.4541 | 1 | 19.4541 | 27632.6014 | 0 | 16 | 6000
1089 | 0.68175 | 0.82119 | 4.7429 | 0 | 16 | 0 | 0 | 16 | 6000
1090 | 0.63688 | 0.76645 | 4.4541 | 0 | 16 | 0 | 0 | 16 | 6000
1091 | 0.02373 | 0.16738 | 2.1988 | 1 | 18.1988 | 17590.1014 | 1 | 18.1988 | 23590.1014
1092 | 0.97243 | 0.86528 | 5.0159 | 0 | 16 | 0 | 0 | 16 | 6000
1093 | 0.43052 | 0.39759 | 3.0275 | 1 | 19.0275 | 24219.6257 | 0 | 16 | 6000
1094 | 0.15016 | 0.11402 | 1.9704 | 1 | 17.9704 | 15762.8737 | 1 | 17.9704 | 21762.8737
1095 | 0.44012 | 0.11337 | 1.9674 | 1 | 17.9674 | 15739.0905 | 0 | 16 | 6000
1096 | 0.80101 | 0.59977 | 3.7462 | 0 | 16 | 0 | 0 | 16 | 6000
1097 | 0.36722 | 0.88203 | 5.1339 | 1 | 21.1339 | 46740.2958 | 0 | 16 | 6000
1098 | 0.20622 | 0.12492 | 2.0196 | 1 | 18.0196 | 16156.9508 | 0 | 16 | 6000
1099 | 0.19498 | 0.89301 | 5.2169 | 1 | 21.2169 | 47820.3019 | 1 | 21.2169 | 53820.3019
1100 | 0.1454 | 0.076949 | 1.7874 | 1 | 17.7874 | 14299.1332 | 1 | 17.7874 | 20299.1332
1101 | 0.65077 | 0.67396 | 4.0395 | 0 | 16 | 0 | 0 | 16 | 6000
1102 | 0.26316 | 0.43502 | 3.1562 | 1 | 19.1562 | 25249.7455 | 0 | 16 | 6000
1103 | 0.41771 | 0.8148 | 4.7068 | 1 | 20.7068 | 41188.3911 | 0 | 16 | 6000
1104 | 0.65459 | 0.92466 | 5.4921 | 0 | 16 | 0 | 0 | 16 | 6000
1105 | 0.98014 | 0.16571 | 2.192 | 0 | 16 | 0 | 0 | 16 | 6000
1106 | 0.37003 | 0.6139 | 3.8002 | 1 | 19.8002 | 30401.4104 | 0 | 16 | 6000
1107 | 0.92802 | 0.17755 | 2.2394 | 0 | 16 | 0 | 0 | 16 | 6000
1108 | 0.19152 | 0.0018121 | 1.1252 | 1 | 17.1252 | 9001.9729 | 1 | 17.1252 | 15001.9729
1109 | 0.69807 | 0.77767 | 4.5099 | 0 | 16 | 0 | 0 | 16 | 6000
1110 | 0.015367 | 0.016274 | 1.3599 | 1 | 17.3599 | 10878.8086 | 1 | 17.3599 | 16878.8086
1111 | 0.7506 | 0.53475 | 3.5064 | 0 | 16 | 0 | 0 | 16 | 6000
1112 | 0.26391 | 0.57642 | 3.6586 | 1 | 19.6586 | 29268.817 | 0 | 16 | 6000
1113 | 0.34742 | 0.75086 | 4.3789 | 1 | 20.3789 | 36926.2885 | 0 | 16 | 6000
1114 | 0.89245 | 0.0013599 | 1.1093 | 0 | 16 | 0 | 0 | 16 | 6000
1115 | 0.73823 | 0.76494 | 4.4467 | 0 | 16 | 0 | 0 | 16 | 6000
1116 | 0.27125 | 0.69576 | 4.1313 | 1 | 20.1313 | 33706.3062 | 0 | 16 | 6000
1117 | 0.38161 | 0.29575 | 2.6754 | 1 | 18.6754 | 21403.2519 | 0 | 16 | 6000
1118 | 0.57772 | 0.75905 | 4.4181 | 0 | 16 | 0 | 0 | 16 | 6000
1119 | 0.90897 | 0.89487 | 5.2315 | 0 | 16 | 0 | 0 | 16 | 6000
1120 | 0.13213 | 0.70323 | 4.1634 | 1 | 20.1634 | 34124.4136 | 1 | 20.1634 | 40124.4136
1121 | 0.56574 | 0.76349 | 4.4396 | 0 | 16 | 0 | 0 | 16 | 6000
1122 | 0.82557 | 0.10883 | 1.9463 | 0 | 16 | 0 | 0 | 16 | 6000
1123 | 0.69822 | 0.21641 | 2.3888 | 0 | 16 | 0 | 0 | 16 | 6000
1124 | 0.39591 | 0.06711 | 1.7332 | 1 | 17.7332 | 13865.619 | 0 | 16 | 6000
1125 | 0.94636 | 0.5887 | 3.7044 | 0 | 16 | 0 | 0 | 16 | 6000
1126 | 0.65694 | 0.42665 | 3.1274 | 0 | 16 | 0 | 0 | 16 | 6000
1127 | 0.33483 | 0.23033 | 2.4406 | 1 | 18.4406 | 19524.6528 | 0 | 16 | 6000
1128 | 0.24444 | 0.39996 | 3.0356 | 1 | 19.0356 | 24284.8781 | 0 | 16 | 6000
1129 | 0.83028 | 0.13465 | 2.0623 | 0 | 16 | 0 | 0 | 16 | 6000
1130 | 0.92629 | 0.023457 | 1.4309 | 0 | 16 | 0 | 0 | 16 | 6000
1131 | 0.98841 | 0.81363 | 4.7003 | 0 | 16 | 0 | 0 | 16 | 6000
1132 | 0.80835 | 0.78425 | 4.5434 | 0 | 16 | 0 | 0 | 16 | 6000
1133 | 0.73517 | 0.91971 | 5.4447 | 0 | 16 | 0 | 0 | 16 | 6000
1134 | 0.14506 | 0.72945 | 4.2797 | 1 | 20.2797 | 35635.7924 | 1 | 20.2797 | 41635.7924
1135 | 0.052464 | 0.358 | 2.8914 | 1 | 18.8914 | 23131.5606 | 1 | 18.8914 | 29131.5606
1136 | 0.72802 | 0.57335 | 3.6472 | 0 | 16 | 0 | 0 | 16 | 6000
1137 | 0.50477 | 0.05467 | 1.6596 | 0 | 16 | 0 | 0 | 16 | 6000
1138 | 0.72578 | 0.20538 | 2.3472 | 0 | 16 | 0 | 0 | 16 | 6000
1139 | 0.50999 | 0.9761 | 6.1951 | 0 | 16 | 0 | 0 | 16 | 6000
1140 | 0.48246 | 0.6777 | 4.055 | 1 | 20.055 | 32714.9995 | 0 | 16 | 6000
1141 | 0.37657 | 0.63905 | 3.8982 | 1 | 19.8982 | 31185.8544 | 0 | 16 | 6000
1142 | 0.10944 | 0.1034 | 1.9206 | 1 | 17.9206 | 15365.1989 | 1 | 17.9206 | 21365.1989
1143 | 0.14441 | 0.70595 | 4.1752 | 1 | 20.1752 | 34277.8703 | 1 | 20.1752 | 40277.8703
1144 | 0.19845 | 0.19522 | 2.3084 | 1 | 18.3084 | 18466.9735 | 1 | 18.3084 | 24466.9735
1145 | 0.63763 | 0.33048 | 2.7965 | 0 | 16 | 0 | 0 | 16 | 6000
1146 | 0.61883 | 0.16087 | 2.1724 | 0 | 16 | 0 | 0 | 16 | 6000
1147 | 0.12009 | 0.51082 | 3.4209 | 1 | 19.4209 | 27366.9247 | 1 | 19.4209 | 33366.9247
1148 | 0.24508 | 0.16877 | 2.2044 | 1 | 18.2044 | 17634.8647 | 0 | 16 | 6000
1149 | 0.042399 | 0.94643 | 5.7292 | 1 | 21.7292 | 54479.4874 | 1 | 21.7292 | 60479.4874
1150 | 0.57267 | 0.67613 | 4.0485 | 0 | 16 | 0 | 0 | 16 | 6000
1151 | 0.90855 | 0.95922 | 5.9004 | 0 | 16 | 0 | 0 | 16 | 6000
1152 | 0.67365 | 0.98592 | 6.4424 | 0 | 16 | 0 | 0 | 16 | 6000
1153 | 0.50368 | 0.40582 | 3.0557 | 0 | 16 | 0 | 0 | 16 | 6000
1154 | 0.1683 | 0.41 | 3.0701 | 1 | 19.0701 | 24560.6846 | 1 | 19.0701 | 30560.6846
1155 | 0.59739 | 0.33978 | 2.8286 | 0 | 16 | 0 | 0 | 16 | 6000
1156 | 0.94452 | 0.10793 | 1.9421 | 0 | 16 | 0 | 0 | 16 | 6000
1157 | 0.91719 | 0.56818 | 3.6281 | 0 | 16 | 0 | 0 | 16 | 6000
1158 | 0.35516 | 0.22868 | 2.4345 | 1 | 18.4345 | 19475.7185 | 0 | 16 | 6000
1159 | 0.11813 | 0.11275 | 1.9645 | 1 | 17.9645 | 15716.1381 | 1 | 17.9645 | 21716.1381
1160 | 0.039456 | 0.25618 | 2.5348 | 1 | 18.5348 | 20278.1668 | 1 | 18.5348 | 26278.1668
1161 | 0.87059 | 0.11726 | 1.9852 | 0 | 16 | 0 | 0 | 16 | 6000
1162 | 0.027051 | 0.50041 | 3.384 | 1 | 19.384 | 27072.2692 | 1 | 19.384 | 33072.2692
1163 | 0.33427 | 0.36662 | 2.9211 | 1 | 18.9211 | 23368.6688 | 0 | 16 | 6000
1164 | 0.039491 | 0.44017 | 3.174 | 1 | 19.174 | 25391.9361 | 1 | 19.174 | 31391.9361
1165 | 0.3863 | 0.98856 | 6.5293 | 1 | 22.5293 | 64881.3704 | 0 | 16 | 6000
1166 | 0.95998 | 0.40398 | 3.0494 | 0 | 16 | 0 | 0 | 16 | 6000
1167 | 0.92353 | 0.58241 | 3.6809 | 0 | 16 | 0 | 0 | 16 | 6000
1168 | 0.1684 | 0.9756 | 6.1844 | 1 | 22.1844 | 60396.9328 | 1 | 22.1844 | 66396.9328
1169 | 0.39559 | 0.49289 | 3.3575 | 1 | 19.3575 | 26860.3111 | 0 | 16 | 6000
1170 | 0.70463 | 0.23066 | 2.4418 | 0 | 16 | 0 | 0 | 16 | 6000
1171 | 0.48315 | 0.24076 | 2.4789 | 1 | 18.4789 | 19830.803 | 0 | 16 | 6000
1172 | 0.24812 | 0.35357 | 2.8762 | 1 | 18.8762 | 23009.4297 | 0 | 16 | 6000
1173 | 0.91389 | 0.65307 | 3.9542 | 0 | 16 | 0 | 0 | 16 | 6000
1174 | 0.39151 | 0.33999 | 2.8294 | 1 | 18.8294 | 22634.9942 | 0 | 16 | 6000
1175 | 0.41234 | 0.14652 | 2.1129 | 1 | 18.1129 | 16903.3899 | 0 | 16 | 6000
1176 | 0.87746 | 0.37103 | 2.9363 | 0 | 16 | 0 | 0 | 16 | 6000
1177 | 0.48721 | 0.1009 | 1.9087 | 1 | 17.9087 | 15269.6374 | 0 | 16 | 6000
1178 | 0.90868 | 0.51393 | 3.4319 | 0 | 16 | 0 | 0 | 16 | 6000
1179 | 0.99546 | 0.1089 | 1.9466 | 0 | 16 | 0 | 0 | 16 | 6000
1180 | 0.26297 | 0.61503 | 3.8045 | 1 | 19.8045 | 30435.9209 | 0 | 16 | 6000
1181 | 0.40539 | 0.80393 | 4.647 | 1 | 20.647 | 40411.039 | 0 | 16 | 6000
1182 | 0.59387 | 0.86681 | 5.0263 | 0 | 16 | 0 | 0 | 16 | 6000
1183 | 0.79651 | 0.023581 | 1.432 | 0 | 16 | 0 | 0 | 16 | 6000
1184 | 0.93972 | 0.14709 | 2.1154 | 0 | 16 | 0 | 0 | 16 | 6000
1185 | 0.34759 | 0.53936 | 3.523 | 1 | 19.523 | 28184.0532 | 0 | 16 | 6000
1186 | 0.88405 | 0.30154 | 2.6957 | 0 | 16 | 0 | 0 | 16 | 6000
1187 | 0.029755 | 0.11061 | 1.9546 | 1 | 17.9546 | 15636.59 | 1 | 17.9546 | 21636.59
1188 | 0.79612 | 0.20154 | 2.3326 | 0 | 16 | 0 | 0 | 16 | 6000
1189 | 0.66972 | 0.68382 | 4.0806 | 0 | 16 | 0 | 0 | 16 | 6000
1190 | 0.95689 | 0.99973 | 7.4619 | 0 | 16 | 0 | 0 | 16 | 6000
1191 | 0.23681 | 0.84445 | 4.8811 | 1 | 20.8811 | 43454.8851 | 0 | 16 | 6000
1192 | 0.39428 | 0.22029 | 2.4033 | 1 | 18.4033 | 19226.4523 | 0 | 16 | 6000
1193 | 0.33956 | 0.20471 | 2.3447 | 1 | 18.3447 | 18757.387 | 0 | 16 | 6000
1194 | 0.99883 | 0.012839 | 1.3205 | 0 | 16 | 0 | 0 | 16 | 6000
1195 | 0.85289 | 0.70524 | 4.1721 | 0 | 16 | 0 | 0 | 16 | 6000
1196 | 0.56371 | 0.22323 | 2.4143 | 0 | 16 | 0 | 0 | 16 | 6000
1197 | 0.32042 | 0.94907 | 5.7621 | 1 | 21.7621 | 54906.7005 | 0 | 16 | 6000
1198 | 0.81977 | 0.12268 | 2.0096 | 0 | 16 | 0 | 0 | 16 | 6000
1199 | 0.43998 | 0.94799 | 5.7485 | 1 | 21.7485 | 54730.0003 | 0 | 16 | 6000
1200 | 0.032771 | 0.53105 | 3.4931 | 1 | 19.4931 | 27944.6749 | 1 | 19.4931 | 33944.6749
1201 | 0.72852 | 0.26476 | 2.5656 | 0 | 16 | 0 | 0 | 16 | 6000
1202 | 0.41004 | 0.93055 | 5.5512 | 1 | 21.5512 | 52165.7982 | 0 | 16 | 6000
1203 | 0.61412 | 0.85009 | 4.9165 | 0 | 16 | 0 | 0 | 16 | 6000
1204 | 0.69736 | 0.22736 | 2.4296 | 0 | 16 | 0 | 0 | 16 | 6000
1205 | 0.15357 | 0.61243 | 3.7945 | 1 | 19.7945 | 30355.958 | 1 | 19.7945 | 36355.958
1206 | 0.32157 | 0.069622 | 1.7473 | 1 | 17.7473 | 13978.6546 | 0 | 16 | 6000
1207 | 0.056918 | 0.80899 | 4.6746 | 1 | 20.6746 | 40770.1267 | 1 | 20.6746 | 46770.1267
1208 | 0.72364 | 0.85031 | 4.9179 | 0 | 16 | 0 | 0 | 16 | 6000
1209 | 0.01336 | 0.59971 | 3.746 | 1 | 19.746 | 29967.7616 | 1 | 19.746 | 35967.7616
1210 | 0.14964 | 0.88523 | 5.1576 | 1 | 21.1576 | 47048.6351 | 1 | 21.1576 | 53048.6351
1211 | 0.62245 | 0.038666 | 1.5531 | 0 | 16 | 0 | 0 | 16 | 6000
1212 | 0.86871 | 0.24881 | 2.5081 | 0 | 16 | 0 | 0 | 16 | 6000
1213 | 0.95015 | 0.33182 | 2.8011 | 0 | 16 | 0 | 0 | 16 | 6000
1214 | 0.77961 | 0.50654 | 3.4057 | 0 | 16 | 0 | 0 | 16 | 6000
1215 | 0.4748 | 0.30182 | 2.6967 | 1 | 18.6967 | 21573.7401 | 0 | 16 | 6000
1216 | 0.99417 | 0.87888 | 5.1109 | 0 | 16 | 0 | 0 | 16 | 6000
1217 | 0.99693 | 0.089537 | 1.8528 | 0 | 16 | 0 | 0 | 16 | 6000
1218 | 0.60783 | 0.49774 | 3.3746 | 0 | 16 | 0 | 0 | 16 | 6000
1219 | 0.29314 | 0.61818 | 3.8167 | 1 | 19.8167 | 30533.2178 | 0 | 16 | 6000
1220 | 0.95939 | 0.74436 | 4.3483 | 0 | 16 | 0 | 0 | 16 | 6000
1221 | 0.64656 | 0.36101 | 2.9018 | 0 | 16 | 0 | 0 | 16 | 6000
1222 | 0.58009 | 0.0049685 | 1.2026 | 0 | 16 | 0 | 0 | 16 | 6000
1223 | 0.25692 | 0.64075 | 3.905 | 1 | 19.905 | 31239.7396 | 0 | 16 | 6000
1224 | 0.64899 | 0.1263 | 2.0257 | 0 | 16 | 0 | 0 | 16 | 6000
1225 | 0.34842 | 0.96923 | 6.0619 | 1 | 22.0619 | 58805.1116 | 0 | 16 | 6000
1226 | 0.21744 | 0.16008 | 2.1692 | 1 | 18.1692 | 17353.3294 | 0 | 16 | 6000
1227 | 0.50485 | 0.36585 | 2.9184 | 0 | 16 | 0 | 0 | 16 | 6000
1228 | 0.52135 | 0.066749 | 1.7312 | 0 | 16 | 0 | 0 | 16 | 6000
1229 | 0.67919 | 0.40464 | 3.0517 | 0 | 16 | 0 | 0 | 16 | 6000
1230 | 0.092687 | 0.52281 | 3.4635 | 1 | 19.4635 | 27708.3946 | 1 | 19.4635 | 33708.3946
1231 | 0.5902 | 0.3143 | 2.7403 | 0 | 16 | 0 | 0 | 16 | 6000
1232 | 0.23593 | 0.88598 | 5.1632 | 1 | 21.1632 | 47121.3094 | 0 | 16 | 6000
1233 | 0.63719 | 0.30905 | 2.722 | 0 | 16 | 0 | 0 | 16 | 6000
1234 | 0.78249 | 0.40586 | 3.0559 | 0 | 16 | 0 | 0 | 16 | 6000
1235 | 0.47681 | 0.14552 | 2.1087 | 1 | 18.1087 | 16869.9555 | 0 | 16 | 6000
1236 | 0.30344 | 0.36487 | 2.9151 | 1 | 18.9151 | 23320.5512 | 0 | 16 | 6000
1237 | 0.82267 | 0.22293 | 2.4132 | 0 | 16 | 0 | 0 | 16 | 6000
1238 | 0.52041 | 0.24441 | 2.4921 | 0 | 16 | 0 | 0 | 16 | 6000
1239 | 0.74389 | 0.14895 | 2.1231 | 0 | 16 | 0 | 0 | 16 | 6000
1240 | 0.49041 | 0.25899 | 2.5449 | 1 | 18.5449 | 20359.1036 | 0 | 16 | 6000
1241 | 0.71085 | 0.88118 | 5.1277 | 0 | 16 | 0 | 0 | 16 | 6000
1242 | 0.98059 | 0.68902 | 4.1026 | 0 | 16 | 0 | 0 | 16 | 6000
1243 | 0.0052157 | 0.73908 | 4.3238 | 1 | 20.3238 | 36209.2105 | 1 | 20.3238 | 42209.2105
1244 | 0.73061 | 0.81656 | 4.7167 | 0 | 16 | 0 | 0 | 16 | 6000
1245 | 0.73792 | 0.15069 | 2.1304 | 0 | 16 | 0 | 0 | 16 | 6000
1246 | 0.93246 | 0.25974 | 2.5476 | 0 | 16 | 0 | 0 | 16 | 6000
1247 | 0.80896 | 0.12925 | 2.0387 | 0 | 16 | 0 | 0 | 16 | 6000
1248 | 0.082167 | 0.28332 | 2.6316 | 1 | 18.6316 | 21052.8817 | 1 | 18.6316 | 27052.8817
1249 | 0.099796 | 0.31797 | 2.7531 | 1 | 18.7531 | 22024.4785 | 1 | 18.7531 | 28024.4785
1250 | 0.15776 | 0.87164 | 5.0596 | 1 | 21.0596 | 45774.1816 | 1 | 21.0596 | 51774.1816
1251 | 0.77814 | 0.87207 | 5.0625 | 0 | 16 | 0 | 0 | 16 | 6000
1252 | 0.58478 | 0.23562 | 2.46 | 0 | 16 | 0 | 0 | 16 | 6000
1253 | 0.040955 | 0.093762 | 1.8739 | 1 | 17.8739 | 14990.8888 | 1 | 17.8739 | 20990.8888
1254 | 0.27105 | 0.27663 | 2.6079 | 1 | 18.6079 | 20863.3937 | 0 | 16 | 6000
1255 | 0.28892 | 0.83399 | 4.8176 | 1 | 20.8176 | 42628.7489 | 0 | 16 | 6000
1256 | 0.72348 | 0.5723 | 3.6433 | 0 | 16 | 0 | 0 | 16 | 6000
1257 | 0.42719 | 0.24044 | 2.4777 | 1 | 18.4777 | 19821.3491 | 0 | 16 | 6000
1258 | 0.59515 | 0.264 | 2.5629 | 0 | 16 | 0 | 0 | 16 | 6000
1259 | 0.80914 | 0.91765 | 5.4255 | 0 | 16 | 0 | 0 | 16 | 6000
1260 | 0.5418 | 0.040633 | 1.5671 | 0 | 16 | 0 | 0 | 16 | 6000
1261 | 0.68507 | 0.31581 | 2.7455 | 0 | 16 | 0 | 0 | 16 | 6000
1262 | 0.92721 | 0.077676 | 1.7913 | 0 | 16 | 0 | 0 | 16 | 6000
1263 | 0.70835 | 0.75334 | 4.3908 | 0 | 16 | 0 | 0 | 16 | 6000
1264 | 0.043436 | 0.83423 | 4.819 | 1 | 20.819 | 42647.0742 | 1 | 20.819 | 48647.0742
1265 | 0.2308 | 0.78348 | 4.5394 | 1 | 20.5394 | 39012.7585 | 0 | 16 | 6000
1266 | 0.82757 | 0.55447 | 3.5778 | 0 | 16 | 0 | 0 | 16 | 6000
1267 | 0.60116 | 0.93287 | 5.5754 | 0 | 16 | 0 | 0 | 16 | 6000
1268 | 0.15731 | 0.51737 | 3.4442 | 1 | 19.4442 | 27553.2711 | 1 | 19.4442 | 33553.2711
1269 | 0.37139 | 0.020179 | 1.4 | 1 | 17.4 | 11199.8343 | 0 | 16 | 6000
1270 | 0.10207 | 0.34375 | 2.8424 | 1 | 18.8424 | 22738.8145 | 1 | 18.8424 | 28738.8145
1271 | 0.85592 | 0.85087 | 4.9215 | 0 | 16 | 0 | 0 | 16 | 6000
1272 | 0.3159 | 0.72196 | 4.2459 | 1 | 20.2459 | 35196.5225 | 0 | 16 | 6000
1273 | 0.58628 | 0.83076 | 4.7984 | 0 | 16 | 0 | 0 | 16 | 6000
1274 | 0.77015 | 0.31784 | 2.7526 | 0 | 16 | 0 | 0 | 16 | 6000
1275 | 0.87125 | 0.68418 | 4.0821 | 0 | 16 | 0 | 0 | 16 | 6000
1276 | 0.12304 | 0.086517 | 1.8374 | 1 | 17.8374 | 14699.4562 | 1 | 17.8374 | 20699.4562
1277 | 0.061798 | 0.79935 | 4.6224 | 1 | 20.6224 | 40091.0818 | 1 | 20.6224 | 46091.0818
1278 | 0.49998 | 0.096117 | 1.8855 | 1 | 17.8855 | 15083.7125 | 0 | 16 | 6000
1279 | 0.64538 | 0.65793 | 3.9738 | 0 | 16 | 0 | 0 | 16 | 6000
1280 | 0.87918 | 0.62387 | 3.8387 | 0 | 16 | 0 | 0 | 16 | 6000
1281 | 0.99948 | 0.55216 | 3.5694 | 0 | 16 | 0 | 0 | 16 | 6000
1282 | 0.45797 | 0.81358 | 4.7 | 1 | 20.7 | 41100.3589 | 0 | 16 | 6000
1283 | 0.26412 | 0.24721 | 2.5023 | 1 | 18.5023 | 20018.5715 | 0 | 16 | 6000
1284 | 0.7235 | 0.83878 | 4.8464 | 0 | 16 | 0 | 0 | 16 | 6000
1285 | 0.68103 | 0.2172 | 2.3918 | 0 | 16 | 0 | 0 | 16 | 6000
1286 | 0.5582 | 0.087016 | 1.84 | 0 | 16 | 0 | 0 | 16 | 6000
1287 | 0.85911 | 0.96883 | 6.0548 | 0 | 16 | 0 | 0 | 16 | 6000
1288 | 0.018542 | 0.39019 | 3.0021 | 1 | 19.0021 | 24016.4792 | 1 | 19.0021 | 30016.4792
1289 | 0.86357 | 0.84881 | 4.9084 | 0 | 16 | 0 | 0 | 16 | 6000
1290 | 0.36629 | 0.24104 | 2.4799 | 1 | 18.4799 | 19838.8122 | 0 | 16 | 6000
1291 | 0.57602 | 0.38615 | 2.9882 | 0 | 16 | 0 | 0 | 16 | 6000
1292 | 0.015015 | 0.51535 | 3.437 | 1 | 19.437 | 27495.747 | 1 | 19.437 | 33495.747
1293 | 0.37121 | 0.37345 | 2.9446 | 1 | 18.9446 | 23556.6414 | 0 | 16 | 6000
1294 | 0.17337 | 0.59831 | 3.7406 | 1 | 19.7406 | 29925.1632 | 1 | 19.7406 | 35925.1632
1295 | 0.2603 | 0.99464 | 6.8047 | 1 | 22.8047 | 68461.2034 | 0 | 16 | 6000
1296 | 0.63577 | 0.78811 | 4.5633 | 0 | 16 | 0 | 0 | 16 | 6000
1297 | 0.8057 | 0.19865 | 2.3216 | 0 | 16 | 0 | 0 | 16 | 6000
1298 | 0.87177 | 0.80986 | 4.6794 | 0 | 16 | 0 | 0 | 16 | 6000
1299 | 0.59548 | 0.85529 | 4.9498 | 0 | 16 | 0 | 0 | 16 | 6000
1300 | 0.40894 | 0.24667 | 2.5004 | 1 | 18.5004 | 20003.0052 | 0 | 16 | 6000
1301 | 0.31329 | 0.78777 | 4.5616 | 1 | 20.5616 | 39300.1521 | 0 | 16 | 6000
1302 | 0.60704 | 0.51649 | 3.441 | 0 | 16 | 0 | 0 | 16 | 6000
1303 | 0.84562 | 0.10084 | 1.9084 | 0 | 16 | 0 | 0 | 16 | 6000
1304 | 0.026267 | 0.58496 | 3.6904 | 1 | 19.6904 | 29523.2764 | 1 | 19.6904 | 35523.2764
1305 | 0.69327 | 0.85009 | 4.9165 | 0 | 16 | 0 | 0 | 16 | 6000
1306 | 0.46836 | 0.6564 | 3.9676 | 1 | 19.9676 | 31741.0796 | 0 | 16 | 6000
1307 | 0.3628 | 0.1406 | 2.0879 | 1 | 18.0879 | 16702.8169 | 0 | 16 | 6000
1308 | 0.83056 | 0.93842 | 5.6356 | 0 | 16 | 0 | 0 | 16 | 6000
1309 | 0.13514 | 0.61819 | 3.8167 | 1 | 19.8167 | 30533.4973 | 1 | 19.8167 | 36533.4973
1310 | 0.64628 | 0.69187 | 4.1146 | 0 | 16 | 0 | 0 | 16 | 6000
1311 | 0.44186 | 0.32845 | 2.7894 | 1 | 18.7894 | 22315.4715 | 0 | 16 | 6000
1312 | 0.385 | 0.28024 | 2.6207 | 1 | 18.6207 | 20965.7374 | 0 | 16 | 6000
1313 | 0.57747 | 0.12836 | 2.0348 | 0 | 16 | 0 | 0 | 16 | 6000
1314 | 0.48384 | 0.55907 | 3.5946 | 1 | 19.5946 | 28757.1103 | 0 | 16 | 6000
1315 | 0.88492 | 0.53572 | 3.5099 | 0 | 16 | 0 | 0 | 16 | 6000
1316 | 0.32899 | 0.6098 | 3.7844 | 1 | 19.7844 | 30275.4651 | 0 | 16 | 6000
1317 | 0.055576 | 0.30675 | 2.7139 | 1 | 18.7139 | 21711.4562 | 1 | 18.7139 | 27711.4562
1318 | 0.52317 | 0.61856 | 3.8181 | 0 | 16 | 0 | 0 | 16 | 6000
1319 | 0.2089 | 0.79886 | 4.6198 | 1 | 20.6198 | 40057.3838 | 0 | 16 | 6000
1320 | 0.29538 | 0.98533 | 6.4245 | 1 | 22.4245 | 63518.8043 | 0 | 16 | 6000
1321 | 0.95052 | 0.36737 | 2.9237 | 0 | 16 | 0 | 0 | 16 | 6000
1322 | 0.030979 | 0.60402 | 3.7623 | 1 | 19.7623 | 30098.6742 | 1 | 19.7623 | 36098.6742
1323 | 0.8656 | 0.51897 | 3.4499 | 0 | 16 | 0 | 0 | 16 | 6000
1324 | 0.87803 | 0.43968 | 3.1723 | 0 | 16 | 0 | 0 | 16 | 6000
1325 | 0.53831 | 0.40257 | 3.0446 | 0 | 16 | 0 | 0 | 16 | 6000
1326 | 0.082497 | 0.20562 | 2.3481 | 1 | 18.3481 | 18785.0077 | 1 | 18.3481 | 24785.0077
1327 | 0.86954 | 0.49121 | 3.3516 | 0 | 16 | 0 | 0 | 16 | 6000
1328 | 0.70586 | 0.68205 | 4.0732 | 0 | 16 | 0 | 0 | 16 | 6000
1329 | 0.17646 | 0.041028 | 1.5699 | 1 | 17.5699 | 12559.3092 | 1 | 17.5699 | 18559.3092
1330 | 0.14902 | 0.023372 | 1.4301 | 1 | 17.4301 | 11440.7908 | 1 | 17.4301 | 17440.7908
1331 | 0.23157 | 0.56406 | 3.6129 | 1 | 19.6129 | 28903.5387 | 0 | 16 | 6000
1332 | 0.38728 | 0.21822 | 2.3956 | 1 | 18.3956 | 19164.8077 | 0 | 16 | 6000
1333 | 0.78938 | 0.27642 | 2.6072 | 0 | 16 | 0 | 0 | 16 | 6000
1334 | 0.90662 | 0.15072 | 2.1305 | 0 | 16 | 0 | 0 | 16 | 6000
1335 | 0.20837 | 0.20387 | 2.3415 | 1 | 18.3415 | 18731.9357 | 0 | 16 | 6000
1336 | 0.18548 | 0.13715 | 2.0731 | 1 | 18.0731 | 16584.5421 | 1 | 18.0731 | 22584.5421
1337 | 0.97799 | 0.12407 | 2.0158 | 0 | 16 | 0 | 0 | 16 | 6000
1338 | 0.92586 | 0.3042 | 2.705 | 0 | 16 | 0 | 0 | 16 | 6000
1339 | 0.1094 | 0.35781 | 2.8908 | 1 | 18.8908 | 23126.4226 | 1 | 18.8908 | 29126.4226
1340 | 0.48535 | 0.65103 | 3.946 | 1 | 19.946 | 31567.9848 | 0 | 16 | 6000
1341 | 0.97527 | 0.53222 | 3.4973 | 0 | 16 | 0 | 0 | 16 | 6000
1342 | 0.60862 | 0.68687 | 4.0935 | 0 | 16 | 0 | 0 | 16 | 6000
1343 | 0.18834 | 0.43573 | 3.1587 | 1 | 19.1587 | 25269.4744 | 1 | 19.1587 | 31269.4744
1344 | 0.76591 | 0.1823 | 2.2581 | 0 | 16 | 0 | 0 | 16 | 6000
1345 | 0.16827 | 0.66451 | 4.0006 | 1 | 20.0006 | 32007.6527 | 1 | 20.0006 | 38007.6527
1346 | 0.56147 | 0.21923 | 2.3994 | 0 | 16 | 0 | 0 | 16 | 6000
1347 | 0.33705 | 0.19027 | 2.2892 | 1 | 18.2892 | 18313.8641 | 0 | 16 | 6000
1348 | 0.16977 | 0.6138 | 3.7998 | 1 | 19.7998 | 30398.333 | 1 | 19.7998 | 36398.333
1349 | 0.063286 | 0.31956 | 2.7586 | 1 | 18.7586 | 22068.8115 | 1 | 18.7586 | 28068.8115
1350 | 0.83794 | 0.81179 | 4.6901 | 0 | 16 | 0 | 0 | 16 | 6000
1351 | 0.21404 | 0.26573 | 2.5691 | 1 | 18.5691 | 20552.5005 | 0 | 16 | 6000
1352 | 0.2738 | 0.40679 | 3.0591 | 1 | 19.0591 | 24472.4412 | 0 | 16 | 6000
1353 | 0.2061 | 0.38065 | 2.9693 | 1 | 18.9693 | 23754.3303 | 0 | 16 | 6000
1354 | 0.21322 | 0.57019 | 3.6355 | 1 | 19.6355 | 29084.1577 | 0 | 16 | 6000
1355 | 0.401 | 0.31161 | 2.7309 | 1 | 18.7309 | 21847.1533 | 0 | 16 | 6000
1356 | 0.10286 | 0.076587 | 1.7855 | 1 | 17.7855 | 14283.6279 | 1 | 17.7855 | 20283.6279
1357 | 0.75616 | 0.25066 | 2.5148 | 0 | 16 | 0 | 0 | 16 | 6000
1358 | 0.1247 | 0.35486 | 2.8806 | 1 | 18.8806 | 23045.0171 | 1 | 18.8806 | 29045.0171
1359 | 0.57638 | 0.97543 | 6.1809 | 0 | 16 | 0 | 0 | 16 | 6000
1360 | 0.2379 | 0.9815 | 6.3198 | 1 | 22.3198 | 62157.0529 | 0 | 16 | 6000
1361 | 0.39786 | 0.099712 | 1.903 | 1 | 17.903 | 15223.6787 | 0 | 16 | 6000
1362 | 0.94333 | 0.076828 | 1.7867 | 0 | 16 | 0 | 0 | 16 | 6000
1363 | 0.071457 | 0.16239 | 2.1786 | 1 | 18.1786 | 17428.6838 | 1 | 18.1786 | 23428.6838
1364 | 0.95871 | 0.083186 | 1.8203 | 0 | 16 | 0 | 0 | 16 | 6000
1365 | 0.18442 | 0.37089 | 2.9358 | 1 | 18.9358 | 23486.2127 | 1 | 18.9358 | 29486.2127
1366 | 0.91421 | 0.9362 | 5.6112 | 0 | 16 | 0 | 0 | 16 | 6000
1367 | 0.76964 | 0.39154 | 3.0067 | 0 | 16 | 0 | 0 | 16 | 6000
1368 | 0.74427 | 0.91011 | 5.3579 | 0 | 16 | 0 | 0 | 16 | 6000
1369 | 0.65832 | 0.81001 | 4.6802 | 0 | 16 | 0 | 0 | 16 | 6000
1370 | 0.33358 | 0.045589 | 1.6012 | 1 | 17.6012 | 12809.6284 | 0 | 16 | 6000
1371 | 0.44915 | 0.86066 | 4.985 | 1 | 20.985 | 44804.6617 | 0 | 16 | 6000
1372 | 0.17949 | 0.12926 | 2.0388 | 1 | 18.0388 | 16310.2578 | 1 | 18.0388 | 22310.2578
1373 | 0.44854 | 0.30326 | 2.7017 | 1 | 18.7017 | 21613.9375 | 0 | 16 | 6000
1374 | 0.0051705 | 0.79742 | 4.6121 | 1 | 20.6121 | 39957.9436 | 1 | 20.6121 | 45957.9436
1375 | 0.72204 | 0.96716 | 6.0258 | 0 | 16 | 0 | 0 | 16 | 6000
1376 | 0.022064 | 0.12107 | 2.0024 | 1 | 18.0024 | 16019.2658 | 1 | 18.0024 | 22019.2658
1377 | 0.42501 | 0.7332 | 4.2967 | 1 | 20.2967 | 35857.3445 | 0 | 16 | 6000
1378 | 0.26739 | 0.11515 | 1.9755 | 1 | 17.9755 | 15804.3524 | 0 | 16 | 6000
1379 | 0.12215 | 0.38092 | 2.9702 | 1 | 18.9702 | 23761.8519 | 1 | 18.9702 | 29761.8519
1380 | 0.35197 | 0.9151 | 5.4022 | 1 | 21.4022 | 50228.4016 | 0 | 16 | 6000
1381 | 0.45016 | 0.45714 | 3.2327 | 1 | 19.2327 | 25861.8056 | 0 | 16 | 6000
1382 | 0.9453 | 0.53784 | 3.5175 | 0 | 16 | 0 | 0 | 16 | 6000
1383 | 0.062541 | 0.030105 | 1.4878 | 1 | 17.4878 | 11902.4685 | 1 | 17.4878 | 17902.4685
1384 | 0.43465 | 0.23498 | 2.4577 | 1 | 18.4577 | 19661.2909 | 0 | 16 | 6000
1385 | 0.6445 | 0.54982 | 3.5609 | 0 | 16 | 0 | 0 | 16 | 6000
1386 | 0.28084 | 0.032669 | 1.5082 | 1 | 17.5082 | 12065.3261 | 0 | 16 | 6000
1387 | 0.3006 | 0.69778 | 4.1399 | 1 | 20.1399 | 33819.0108 | 0 | 16 | 6000
1388 | 0.56149 | 0.12989 | 2.0415 | 0 | 16 | 0 | 0 | 16 | 6000
1389 | 0.066936 | 0.63406 | 3.8786 | 1 | 19.8786 | 31028.5245 | 1 | 19.8786 | 37028.5245
1390 | 0.98735 | 0.90231 | 5.2917 | 0 | 16 | 0 | 0 | 16 | 6000
1391 | 0.77434 | 0.033611 | 1.5155 | 0 | 16 | 0 | 0 | 16 | 6000
1392 | 0.73089 | 0.27113 | 2.5884 | 0 | 16 | 0 | 0 | 16 | 6000
1393 | 0.90567 | 0.33252 | 2.8035 | 0 | 16 | 0 | 0 | 16 | 6000
1394 | 0.37452 | 0.69918 | 4.1459 | 1 | 20.1459 | 33897.0122 | 0 | 16 | 6000
1395 | 0.065373 | 0.41438 | 3.0851 | 1 | 19.0851 | 24681.184 | 1 | 19.0851 | 30681.184
1396 | 0.16191 | 0.6401 | 3.9024 | 1 | 19.9024 | 31219.291 | 1 | 19.9024 | 37219.291
1397 | 0.26171 | 0.39167 | 3.0071 | 1 | 19.0071 | 24057.1 | 0 | 16 | 6000
1398 | 0.86145 | 0.53489 | 3.5069 | 0 | 16 | 0 | 0 | 16 | 6000
1399 | 0.81838 | 0.76562 | 4.45 | 0 | 16 | 0 | 0 | 16 | 6000
1400 | 0.24726 | 0.74542 | 4.3533 | 1 | 20.3533 | 36593.086 | 0 | 16 | 6000
1401 | 0.93054 | 0.76668 | 4.4553 | 0 | 16 | 0 | 0 | 16 | 6000
1402 | 0.72544 | 0.16822 | 2.2022 | 0 | 16 | 0 | 0 | 16 | 6000
1403 | 0.51377 | 0.077442 | 1.79 | 0 | 16 | 0 | 0 | 16 | 6000
1404 | 0.50599 | 0.090065 | 1.8554 | 0 | 16 | 0 | 0 | 16 | 6000
1405 | 0.84753 | 0.46461 | 3.2587 | 0 | 16 | 0 | 0 | 16 | 6000
1406 | 0.4074 | 0.73933 | 4.3249 | 1 | 20.3249 | 36223.9934 | 0 | 16 | 6000
1407 | 0.56917 | 0.27254 | 2.5934 | 0 | 16 | 0 | 0 | 16 | 6000
1408 | 0.6458 | 0.50107 | 3.3864 | 0 | 16 | 0 | 0 | 16 | 6000
1409 | 0.38164 | 0.81526 | 4.7094 | 1 | 20.7094 | 41222.0566 | 0 | 16 | 6000
1410 | 0.64287 | 0.47746 | 3.3035 | 0 | 16 | 0 | 0 | 16 | 6000
1411 | 0.98851 | 0.61466 | 3.8031 | 0 | 16 | 0 | 0 | 16 | 6000
1412 | 0.622 | 0.4537 | 3.2208 | 0 | 16 | 0 | 0 | 16 | 6000
1413 | 0.37992 | 0.43584 | 3.1591 | 1 | 19.1591 | 25272.4924 | 0 | 16 | 6000
1414 | 0.27467 | 0.89228 | 5.2113 | 1 | 21.2113 | 47747.1081 | 0 | 16 | 6000
1415 | 0.096583 | 0.95021 | 5.7766 | 1 | 21.7766 | 55095.9368 | 1 | 21.7766 | 61095.9368
1416 | 0.69755 | 0.19252 | 2.298 | 0 | 16 | 0 | 0 | 16 | 6000
1417 | 0.12203 | 0.32505 | 2.7776 | 1 | 18.7776 | 22221.1433 | 1 | 18.7776 | 28221.1433
1418 | 0.4041 | 0.94 | 5.6534 | 1 | 21.6534 | 53494.1296 | 0 | 16 | 6000
1419 | 0.53934 | 0.52379 | 3.4671 | 0 | 16 | 0 | 0 | 16 | 6000
1420 | 0.95618 | 0.68414 | 4.0819 | 0 | 16 | 0 | 0 | 16 | 6000
1421 | 0.76422 | 0.24907 | 2.5091 | 0 | 16 | 0 | 0 | 16 | 6000
1422 | 0.55337 | 0.1409 | 2.0891 | 0 | 16 | 0 | 0 | 16 | 6000
1423 | 0.20329 | 0.63741 | 3.8918 | 1 | 19.8918 | 31134.124 | 0 | 16 | 6000
1424 | 0.18714 | 0.53703 | 3.5146 | 1 | 19.5146 | 28116.756 | 1 | 19.5146 | 34116.756
1425 | 0.37437 | 0.19942 | 2.3245 | 1 | 18.3245 | 18595.7957 | 0 | 16 | 6000
1426 | 0.0075773 | 0.31337 | 2.737 | 1 | 18.737 | 21896.3109 | 1 | 18.737 | 27896.3109
1427 | 0.4372 | 0.38314 | 2.9778 | 1 | 18.9778 | 23822.7019 | 0 | 16 | 6000
1428 | 0.60156 | 0.98415 | 6.3906 | 0 | 16 | 0 | 0 | 16 | 6000
1429 | 0.85108 | 0.40062 | 3.0379 | 0 | 16 | 0 | 0 | 16 | 6000
1430 | 0.72346 | 0.21016 | 2.3653 | 0 | 16 | 0 | 0 | 16 | 6000
1431 | 0.87946 | 0.17075 | 2.2123 | 0 | 16 | 0 | 0 | 16 | 6000
1432 | 0.31524 | 0.80883 | 4.6738 | 1 | 20.6738 | 40758.927 | 0 | 16 | 6000
1433 | 0.97495 | 0.0015453 | 1.1161 | 0 | 16 | 0 | 0 | 16 | 6000
1434 | 0.9487 | 0.07212 | 1.7612 | 0 | 16 | 0 | 0 | 16 | 6000
1435 | 0.75251 | 0.36734 | 2.9236 | 0 | 16 | 0 | 0 | 16 | 6000
1436 | 0.23166 | 0.5677 | 3.6263 | 1 | 19.6263 | 29010.7732 | 0 | 16 | 6000
1437 | 0.72632 | 0.35714 | 2.8885 | 0 | 16 | 0 | 0 | 16 | 6000
1438 | 0.24281 | 0.13504 | 2.064 | 1 | 18.064 | 16511.9957 | 0 | 16 | 6000
1439 | 0.76947 | 0.81073 | 4.6842 | 0 | 16 | 0 | 0 | 16 | 6000
1440 | 0.44598 | 0.50321 | 3.3939 | 1 | 19.3939 | 27151.3395 | 0 | 16 | 6000
1441 | 0.59351 | 0.082783 | 1.8182 | 0 | 16 | 0 | 0 | 16 | 6000
1442 | 0.29091 | 0.60242 | 3.7563 | 1 | 19.7563 | 30050.0578 | 0 | 16 | 6000
1443 | 0.35076 | 0.11627 | 1.9807 | 1 | 17.9807 | 15845.3744 | 0 | 16 | 6000
1444 | 0.014427 | 0.49035 | 3.3486 | 1 | 19.3486 | 26789.034 | 1 | 19.3486 | 32789.034
1445 | 0.45353 | 0.24716 | 2.5022 | 1 | 18.5022 | 20017.2412 | 0 | 16 | 6000
1446 | 0.040296 | 0.7022 | 4.1589 | 1 | 20.1589 | 34066.2898 | 1 | 20.1589 | 40066.2898
1447 | 0.724 | 0.03709 | 1.5416 | 0 | 16 | 0 | 0 | 16 | 6000
1448 | 0.233 | 0.14711 | 2.1154 | 1 | 18.1154 | 16923.4501 | 0 | 16 | 6000
1449 | 0.41346 | 0.59685 | 3.7351 | 1 | 19.7351 | 29880.9604 | 0 | 16 | 6000
1450 | 0.63625 | 0.76168 | 4.4308 | 0 | 16 | 0 | 0 | 16 | 6000
1451 | 0.5445 | 0.66352 | 3.9965 | 0 | 16 | 0 | 0 | 16 | 6000
1452 | 0.50356 | 0.81897 | 4.7303 | 0 | 16 | 0 | 0 | 16 | 6000
1453 | 0.53213 | 0.58866 | 3.7043 | 0 | 16 | 0 | 0 | 16 | 6000
1454 | 0.33498 | 0.91415 | 5.3936 | 1 | 21.3936 | 50117.1399 | 0 | 16 | 6000
1455 | 0.94146 | 0.66448 | 4.0005 | 0 | 16 | 0 | 0 | 16 | 6000
1456 | 0.66221 | 0.40992 | 3.0698 | 0 | 16 | 0 | 0 | 16 | 6000
1457 | 0.23056 | 0.32686 | 2.7839 | 1 | 18.7839 | 22271.2773 | 0 | 16 | 6000
1458 | 0.48128 | 0.93757 | 5.6262 | 1 | 21.6262 | 53140.6891 | 0 | 16 | 6000
1459 | 0.20312 | 0.28825 | 2.649 | 1 | 18.649 | 21192.2171 | 0 | 16 | 6000
1460 | 0.93714 | 0.45836 | 3.237 | 0 | 16 | 0 | 0 | 16 | 6000
1461 | 0.77706 | 0.71732 | 4.2252 | 0 | 16 | 0 | 0 | 16 | 6000
1462 | 0.36075 | 0.1107 | 1.955 | 1 | 17.955 | 15640.0445 | 0 | 16 | 6000
1463 | 0.072791 | 0.80822 | 4.6704 | 1 | 20.6704 | 40714.8561 | 1 | 20.6704 | 46714.8561
1464 | 0.92094 | 0.27953 | 2.6182 | 0 | 16 | 0 | 0 | 16 | 6000
1465 | 0.70971 | 0.50772 | 3.4099 | 0 | 16 | 0 | 0 | 16 | 6000
1466 | 0.67894 | 0.40618 | 3.057 | 0 | 16 | 0 | 0 | 16 | 6000
1467 | 0.75522 | 0.99312 | 6.7209 | 0 | 16 | 0 | 0 | 16 | 6000
1468 | 0.50125 | 0.80457 | 4.6505 | 0 | 16 | 0 | 0 | 16 | 6000
1469 | 0.24602 | 0.54116 | 3.5295 | 1 | 19.5295 | 28236.0529 | 0 | 16 | 6000
1470 | 0.92482 | 0.27083 | 2.5873 | 0 | 16 | 0 | 0 | 16 | 6000
1471 | 0.10254 | 0.29818 | 2.6839 | 1 | 18.6839 | 21471.5552 | 1 | 18.6839 | 27471.5552
1472 | 0.33854 | 0.76727 | 4.4582 | 1 | 20.4582 | 37956.0414 | 0 | 16 | 6000
1473 | 0.18491 | 0.26701 | 2.5736 | 1 | 18.5736 | 20589.1492 | 1 | 18.5736 | 26589.1492
1474 | 0.78367 | 0.40261 | 3.0447 | 0 | 16 | 0 | 0 | 16 | 6000
1475 | 0.99665 | 0.03066 | 1.4923 | 0 | 16 | 0 | 0 | 16 | 6000
1476 | 0.13172 | 0.21297 | 2.3759 | 1 | 18.3759 | 19007.1668 | 1 | 18.3759 | 25007.1668
1477 | 0.81872 | 0.55391 | 3.5758 | 0 | 16 | 0 | 0 | 16 | 6000
1478 | 0.86035 | 0.33007 | 2.795 | 0 | 16 | 0 | 0 | 16 | 6000
1479 | 0.82514 | 0.044473 | 1.5937 | 0 | 16 | 0 | 0 | 16 | 6000
1480 | 0.52353 | 0.91554 | 5.4062 | 0 | 16 | 0 | 0 | 16 | 6000
1481 | 0.26731 | 0.14253 | 2.0961 | 1 | 18.0961 | 16768.4879 | 0 | 16 | 6000
1482 | 0.31846 | 0.97356 | 6.1429 | 1 | 22.1429 | 59858.215 | 0 | 16 | 6000
1483 | 0.96375 | 0.66524 | 4.0036 | 0 | 16 | 0 | 0 | 16 | 6000
1484 | 0.97538 | 0.28492 | 2.6373 | 0 | 16 | 0 | 0 | 16 | 6000
1485 | 0.70501 | 0.54942 | 3.5594 | 0 | 16 | 0 | 0 | 16 | 6000
1486 | 0.22323 | 0.14602 | 2.1109 | 1 | 18.1109 | 16886.8329 | 0 | 16 | 6000
1487 | 0.6387 | 0.46123 | 3.2469 | 0 | 16 | 0 | 0 | 16 | 6000
1488 | 0.43743 | 0.3571 | 2.8884 | 1 | 18.8884 | 23106.8328 | 0 | 16 | 6000
1489 | 0.21072 | 0.9401 | 5.6545 | 1 | 21.6545 | 53509.091 | 0 | 16 | 6000
1490 | 0.59692 | 0.12611 | 2.0249 | 0 | 16 | 0 | 0 | 16 | 6000
1491 | 0.4844 | 0.30718 | 2.7154 | 1 | 18.7154 | 21723.5888 | 0 | 16 | 6000
1492 | 0.38872 | 0.80325 | 4.6433 | 1 | 20.6433 | 40363.2686 | 0 | 16 | 6000
1493 | 0.97213 | 0.5157 | 3.4382 | 0 | 16 | 0 | 0 | 16 | 6000
1494 | 0.17225 | 0.75744 | 4.4104 | 1 | 20.4104 | 37334.7984 | 1 | 20.4104 | 43334.7984
1495 | 0.022603 | 0.63438 | 3.8798 | 1 | 19.8798 | 31038.4441 | 1 | 19.8798 | 37038.4441
1496 | 0.44278 | 0.33319 | 2.8058 | 1 | 18.8058 | 22446.7382 | 0 | 16 | 6000
1497 | 0.048933 | 0.27868 | 2.6152 | 1 | 18.6152 | 20921.419 | 1 | 18.6152 | 26921.419
1498 | 0.078473 | 0.78029 | 4.5232 | 1 | 20.5232 | 38801.3009 | 1 | 20.5232 | 44801.3009
1499 | 0.31703 | 0.89276 | 5.215 | 1 | 21.215 | 47795.4216 | 0 | 16 | 6000
1500 | 0.74445 | 0.77519 | 4.4975 | 0 | 16 | 0 | 0 | 16 | 6000
1501 | 0.99352 | 0.98645 | 6.459 | 0 | 16 | 0 | 0 | 16 | 6000
1502 | 0.642 | 0.50313 | 3.3936 | 0 | 16 | 0 | 0 | 16 | 6000
1503 | 0.47635 | 0.60739 | 3.7752 | 1 | 19.7752 | 30201.7076 | 0 | 16 | 6000
1504 | 0.45021 | 0.2536 | 2.5255 | 1 | 18.5255 | 20203.8441 | 0 | 16 | 6000
1505 | 0.42636 | 0.85955 | 4.9777 | 1 | 20.9777 | 44709.6686 | 0 | 16 | 6000
1506 | 0.17297 | 0.051588 | 1.6403 | 1 | 17.6403 | 13122.458 | 1 | 17.6403 | 19122.458
1507 | 0.98419 | 0.73059 | 4.2848 | 0 | 16 | 0 | 0 | 16 | 6000
1508 | 0.62337 | 0.33218 | 2.8023 | 0 | 16 | 0 | 0 | 16 | 6000
1509 | 0.34317 | 0.3589 | 2.8945 | 1 | 18.8945 | 23156.2566 | 0 | 16 | 6000
1510 | 0.017454 | 0.67674 | 4.051 | 1 | 20.051 | 32663.4098 | 1 | 20.051 | 38663.4098
1511 | 0.24714 | 0.86646 | 5.0239 | 1 | 21.0239 | 45311.1402 | 0 | 16 | 6000
1512 | 0.96664 | 0.56236 | 3.6067 | 0 | 16 | 0 | 0 | 16 | 6000
1513 | 0.2951 | 0.68466 | 4.0842 | 1 | 20.0842 | 33093.9743 | 0 | 16 | 6000
1514 | 0.16783 | 0.77459 | 4.4945 | 1 | 20.4945 | 38428.3118 | 1 | 20.4945 | 44428.3118
1515 | 0.7549 | 0.86222 | 4.9954 | 0 | 16 | 0 | 0 | 16 | 6000
1516 | 0.060113 | 0.4881 | 3.3407 | 1 | 19.3407 | 26725.6406 | 1 | 19.3407 | 32725.6406
1517 | 0.88175 | 0.47444 | 3.2929 | 0 | 16 | 0 | 0 | 16 | 6000
1518 | 0.4889 | 0.37191 | 2.9393 | 1 | 18.9393 | 23514.3 | 0 | 16 | 6000
1519 | 0.87932 | 0.74898 | 4.37 | 0 | 16 | 0 | 0 | 16 | 6000
1520 | 0.5377 | 0.23116 | 2.4436 | 0 | 16 | 0 | 0 | 16 | 6000
1521 | 0.60204 | 0.30193 | 2.6971 | 0 | 16 | 0 | 0 | 16 | 6000
1522 | 0.15217 | 0.10744 | 1.9398 | 1 | 17.9398 | 15518.1233 | 1 | 17.9398 | 21518.1233
1523 | 0.88884 | 0.53634 | 3.5121 | 0 | 16 | 0 | 0 | 16 | 6000
1524 | 0.4547 | 0.86782 | 5.0332 | 1 | 21.0332 | 45431.3598 | 0 | 16 | 6000
1525 | 0.8746 | 0.68603 | 4.0899 | 0 | 16 | 0 | 0 | 16 | 6000
1526 | 0.038143 | 0.71069 | 4.1959 | 1 | 20.1959 | 34546.9972 | 1 | 20.1959 | 40546.9972
1527 | 0.98112 | 0.33837 | 2.8237 | 0 | 16 | 0 | 0 | 16 | 6000
1528 | 0.12667 | 0.90542 | 5.3176 | 1 | 21.3176 | 49129.0644 | 1 | 21.3176 | 55129.0644
1529 | 0.34556 | 0.52319 | 3.4649 | 1 | 19.4649 | 27719.3215 | 0 | 16 | 6000
1530 | 0.089018 | 0.77919 | 4.5176 | 1 | 20.5176 | 38729.4055 | 1 | 20.5176 | 44729.4055
1531 | 0.396 | 0.41208 | 3.0772 | 1 | 19.0772 | 24617.8764 | 0 | 16 | 6000
1532 | 0.31549 | 0.91544 | 5.4053 | 1 | 21.4053 | 50269.4106 | 0 | 16 | 6000
1533 | 0.82418 | 0.31575 | 2.7453 | 0 | 16 | 0 | 0 | 16 | 6000
1534 | 0.34794 | 0.72987 | 4.2816 | 1 | 20.2816 | 35660.3315 | 0 | 16 | 6000
1535 | 0.8427 | 0.13887 | 2.0805 | 0 | 16 | 0 | 0 | 16 | 6000
1536 | 0.00049131 | 0.575 | 3.6533 | 1 | 19.6533 | 29226.6919 | 1 | 19.6533 | 35226.6919
1537 | 0.84846 | 0.993 | 6.7146 | 0 | 16 | 0 | 0 | 16 | 6000
1538 | 0.32559 | 0.41655 | 3.0926 | 1 | 19.0926 | 24740.9926 | 0 | 16 | 6000
1539 | 0.50822 | 0.90709 | 5.3318 | 0 | 16 | 0 | 0 | 16 | 6000
1540 | 0.58244 | 0.23861 | 2.471 | 0 | 16 | 0 | 0 | 16 | 6000
1541 | 0.2127 | 0.22956 | 2.4377 | 1 | 18.4377 | 19501.8032 | 0 | 16 | 6000
1542 | 0.62966 | 0.70904 | 4.1887 | 0 | 16 | 0 | 0 | 16 | 6000
1543 | 0.73067 | 0.56759 | 3.6259 | 0 | 16 | 0 | 0 | 16 | 6000
1544 | 0.24361 | 0.96117 | 5.9295 | 1 | 21.9295 | 57082.979 | 0 | 16 | 6000
1545 | 0.26479 | 0.30834 | 2.7195 | 1 | 18.7195 | 21755.9347 | 0 | 16 | 6000
1546 | 0.76842 | 0.078931 | 1.798 | 0 | 16 | 0 | 0 | 16 | 6000
1547 | 0.4952 | 0.51456 | 3.4341 | 1 | 19.4341 | 27473.1667 | 0 | 16 | 6000
1548 | 0.96035 | 0.092696 | 1.8686 | 0 | 16 | 0 | 0 | 16 | 6000
1549 | 0.57484 | 0.97629 | 6.199 | 0 | 16 | 0 | 0 | 16 | 6000
1550 | 0.34617 | 0.70982 | 4.1921 | 1 | 20.1921 | 34497.5917 | 0 | 16 | 6000
1551 | 0.98014 | 0.74235 | 4.339 | 0 | 16 | 0 | 0 | 16 | 6000
1552 | 0.18204 | 0.24554 | 2.4962 | 1 | 18.4962 | 19969.9942 | 1 | 18.4962 | 25969.9942
1553 | 0.57368 | 0.015528 | 1.3517 | 0 | 16 | 0 | 0 | 16 | 6000
1554 | 0.89222 | 0.42821 | 3.1328 | 0 | 16 | 0 | 0 | 16 | 6000
1555 | 0.84711 | 0.091003 | 1.8601 | 0 | 16 | 0 | 0 | 16 | 6000
1556 | 0.80398 | 0.48086 | 3.3154 | 0 | 16 | 0 | 0 | 16 | 6000
1557 | 0.18854 | 0.68884 | 4.1018 | 1 | 20.1018 | 33323.1228 | 1 | 20.1018 | 39323.1228
1558 | 0.5081 | 0.66765 | 4.0134 | 0 | 16 | 0 | 0 | 16 | 6000
1559 | 0.35818 | 0.42076 | 3.1071 | 1 | 19.1071 | 24856.8371 | 0 | 16 | 6000
1560 | 0.72483 | 0.58458 | 3.689 | 0 | 16 | 0 | 0 | 16 | 6000
1561 | 0.29812 | 0.66373 | 3.9974 | 1 | 19.9974 | 31979.3264 | 0 | 16 | 6000
1562 | 0.63357 | 0.15213 | 2.1364 | 0 | 16 | 0 | 0 | 16 | 6000
1563 | 0.58142 | 0.002065 | 1.1333 | 0 | 16 | 0 | 0 | 16 | 6000
1564 | 0.92929 | 0.78345 | 4.5393 | 0 | 16 | 0 | 0 | 16 | 6000
1565 | 0.6033 | 0.92909 | 5.5363 | 0 | 16 | 0 | 0 | 16 | 6000
1566 | 0.16639 | 0.75401 | 4.3939 | 1 | 20.3939 | 37120.9088 | 1 | 20.3939 | 43120.9088
1567 | 0.32923 | 0.5122 | 3.4258 | 1 | 19.4258 | 27406.1555 | 0 | 16 | 6000
1568 | 0.89133 | 0.20615 | 2.3501 | 0 | 16 | 0 | 0 | 16 | 6000
1569 | 0.28779 | 0.3582 | 2.8922 | 1 | 18.8922 | 23137.2238 | 0 | 16 | 6000
1570 | 0.66134 | 0.48502 | 3.3299 | 0 | 16 | 0 | 0 | 16 | 6000
1571 | 0.67253 | 0.38756 | 2.993 | 0 | 16 | 0 | 0 | 16 | 6000
1572 | 0.98973 | 0.10324 | 1.9199 | 0 | 16 | 0 | 0 | 16 | 6000
1573 | 0.49933 | 0.064278 | 1.717 | 1 | 17.717 | 13735.98 | 0 | 16 | 6000
1574 | 0.48701 | 0.62643 | 3.8487 | 1 | 19.8487 | 30789.4215 | 0 | 16 | 6000
1575 | 0.2833 | 0.26223 | 2.5565 | 1 | 18.5565 | 20452.2296 | 0 | 16 | 6000
1576 | 0.071068 | 0.74907 | 4.3705 | 1 | 20.3705 | 36816.4256 | 1 | 20.3705 | 42816.4256
1577 | 0.62846 | 0.34773 | 2.8561 | 0 | 16 | 0 | 0 | 16 | 6000
1578 | 0.078511 | 0.91188 | 5.3734 | 1 | 21.3734 | 49854.7833 | 1 | 21.3734 | 55854.7833
1579 | 0.4811 | 0.83907 | 4.8482 | 1 | 20.8482 | 43026.2173 | 0 | 16 | 6000
1580 | 0.7584 | 0.80538 | 4.6549 | 0 | 16 | 0 | 0 | 16 | 6000
1581 | 0.26738 | 0.6866 | 4.0923 | 1 | 20.0923 | 33200.0522 | 0 | 16 | 6000
1582 | 0.78505 | 0.48406 | 3.3265 | 0 | 16 | 0 | 0 | 16 | 6000
1583 | 0.62285 | 0.57272 | 3.6449 | 0 | 16 | 0 | 0 | 16 | 6000
1584 | 0.33249 | 0.69739 | 4.1382 | 1 | 20.1382 | 33797.2099 | 0 | 16 | 6000
1585 | 0.086863 | 0.64963 | 3.9404 | 1 | 19.9404 | 31523.0835 | 1 | 19.9404 | 37523.0835
1586 | 0.36802 | 0.40874 | 3.0658 | 1 | 19.0658 | 24526.0248 | 0 | 16 | 6000
1587 | 0.53779 | 0.16682 | 2.1965 | 0 | 16 | 0 | 0 | 16 | 6000
1588 | 0.06489 | 0.3992 | 3.033 | 1 | 19.033 | 24263.9767 | 1 | 19.033 | 30263.9767
1589 | 0.55204 | 0.61404 | 3.8007 | 0 | 16 | 0 | 0 | 16 | 6000
1590 | 0.85824 | 0.08466 | 1.8279 | 0 | 16 | 0 | 0 | 16 | 6000
1591 | 0.20807 | 0.24113 | 2.4802 | 1 | 18.4802 | 19841.5156 | 0 | 16 | 6000
1592 | 0.91395 | 0.27099 | 2.5878 | 0 | 16 | 0 | 0 | 16 | 6000
1593 | 0.54715 | 0.48625 | 3.3342 | 0 | 16 | 0 | 0 | 16 | 6000
1594 | 0.38408 | 0.56363 | 3.6114 | 1 | 19.6114 | 28891.0366 | 0 | 16 | 6000
1595 | 0.83758 | 0.28374 | 2.6331 | 0 | 16 | 0 | 0 | 16 | 6000
1596 | 0.25193 | 0.78491 | 4.5468 | 1 | 20.5468 | 39108.395 | 0 | 16 | 6000
1597 | 0.30002 | 0.45866 | 3.238 | 1 | 19.238 | 25903.9417 | 0 | 16 | 6000
1598 | 0.3149 | 0.39767 | 3.0277 | 1 | 19.0277 | 24221.9283 | 0 | 16 | 6000
1599 | 0.8478 | 0.72943 | 4.2796 | 0 | 16 | 0 | 0 | 16 | 6000
1600 | 0.35233 | 0.15988 | 2.1683 | 1 | 18.1683 | 17346.716 | 0 | 16 | 6000
1601 | 0.94564 | 0.13866 | 2.0796 | 0 | 16 | 0 | 0 | 16 | 6000
1602 | 0.66542 | 0.8234 | 4.7556 | 0 | 16 | 0 | 0 | 16 | 6000
1603 | 0.33963 | 0.59743 | 3.7373 | 1 | 19.7373 | 29898.7277 | 0 | 16 | 6000
1604 | 0.94851 | 0.77537 | 4.4984 | 0 | 16 | 0 | 0 | 16 | 6000
1605 | 0.34347 | 0.96662 | 6.0167 | 1 | 22.0167 | 58216.9917 | 0 | 16 | 6000
1606 | 0.32894 | 0.073814 | 1.7705 | 1 | 17.7705 | 14163.6274 | 0 | 16 | 6000
1607 | 0.52683 | 0.7388 | 4.3225 | 0 | 16 | 0 | 0 | 16 | 6000
1608 | 0.19717 | 0.01187 | 1.3085 | 1 | 17.3085 | 10467.6868 | 1 | 17.3085 | 16467.6868
1609 | 0.90301 | 0.80502 | 4.6529 | 0 | 16 | 0 | 0 | 16 | 6000
1610 | 0.75119 | 0.8003 | 4.6275 | 0 | 16 | 0 | 0 | 16 | 6000
1611 | 0.2667 | 0.75764 | 4.4113 | 1 | 20.4113 | 37347.4962 | 0 | 16 | 6000
1612 | 0.20624 | 0.10352 | 1.9212 | 1 | 17.9212 | 15369.7048 | 0 | 16 | 6000
1613 | 0.15024 | 0.65433 | 3.9593 | 1 | 19.9593 | 31674.2523 | 1 | 19.9593 | 37674.2523
1614 | 0.90333 | 0.89822 | 5.2583 | 0 | 16 | 0 | 0 | 16 | 6000
1615 | 0.43049 | 0.11129 | 1.9578 | 1 | 17.9578 | 15662.0289 | 0 | 16 | 6000
1616 | 0.44656 | 0.30176 | 2.6965 | 1 | 18.6965 | 21572.0837 | 0 | 16 | 6000
1617 | 0.17778 | 0.87875 | 5.11 | 1 | 21.11 | 46429.7834 | 1 | 21.11 | 52429.7834
1618 | 0.065639 | 0.27515 | 2.6026 | 1 | 18.6026 | 20821.1216 | 1 | 18.6026 | 26821.1216
1619 | 0.10043 | 0.033823 | 1.5171 | 1 | 17.5171 | 12136.7245 | 1 | 17.5171 | 18136.7245
1620 | 0.036396 | 0.93623 | 5.6115 | 1 | 21.6115 | 52949.547 | 1 | 21.6115 | 58949.547
1621 | 0.46092 | 0.28158 | 2.6254 | 1 | 18.6254 | 21003.557 | 0 | 16 | 6000
1622 | 0.82813 | 0.85463 | 4.9456 | 0 | 16 | 0 | 0 | 16 | 6000
1623 | 0.073841 | 0.13079 | 2.0455 | 1 | 18.0455 | 16363.8185 | 1 | 18.0455 | 22363.8185
1624 | 0.7921 | 0.72133 | 4.2431 | 0 | 16 | 0 | 0 | 16 | 6000
1625 | 0.90559 | 0.79638 | 4.6066 | 0 | 16 | 0 | 0 | 16 | 6000
1626 | 0.69155 | 0.21097 | 2.3684 | 0 | 16 | 0 | 0 | 16 | 6000
1627 | 0.13174 | 0.28473 | 2.6366 | 1 | 18.6366 | 21092.9472 | 1 | 18.6366 | 27092.9472
1628 | 0.06226 | 0.30628 | 2.7123 | 1 | 18.7123 | 21698.5219 | 1 | 18.7123 | 27698.5219
1629 | 0.20909 | 0.92964 | 5.5419 | 1 | 21.5419 | 52044.811 | 0 | 16 | 6000
1630 | 0.18294 | 0.86767 | 5.0321 | 1 | 21.0321 | 45417.846 | 1 | 21.0321 | 51417.846
1631 | 0.87512 | 0.78795 | 4.5625 | 0 | 16 | 0 | 0 | 16 | 6000
1632 | 0.79855 | 0.53627 | 3.5119 | 0 | 16 | 0 | 0 | 16 | 6000
1633 | 0.72809 | 0.16203 | 2.1771 | 0 | 16 | 0 | 0 | 16 | 6000
1634 | 0.065305 | 0.42486 | 3.1212 | 1 | 19.1212 | 24969.6237 | 1 | 19.1212 | 30969.6237
1635 | 0.91102 | 0.49562 | 3.3671 | 0 | 16 | 0 | 0 | 16 | 6000
1636 | 0.42733 | 0.67211 | 4.0318 | 1 | 20.0318 | 32413.5548 | 0 | 16 | 6000
1637 | 0.77357 | 0.30701 | 2.7148 | 0 | 16 | 0 | 0 | 16 | 6000
1638 | 0.35904 | 0.2813 | 2.6245 | 1 | 18.6245 | 20995.7772 | 0 | 16 | 6000
1639 | 0.85611 | 0.48588 | 3.3329 | 0 | 16 | 0 | 0 | 16 | 6000
1640 | 0.021714 | 0.68549 | 4.0876 | 1 | 20.0876 | 33139.4394 | 1 | 20.0876 | 39139.4394
1641 | 0.38481 | 0.22615 | 2.4251 | 1 | 18.4251 | 19400.9752 | 0 | 16 | 6000
1642 | 0.88578 | 0.24694 | 2.5014 | 0 | 16 | 0 | 0 | 16 | 6000
1643 | 0.98321 | 0.67105 | 4.0275 | 0 | 16 | 0 | 0 | 16 | 6000
1644 | 0.87926 | 0.7826 | 4.535 | 0 | 16 | 0 | 0 | 16 | 6000
1645 | 0.035976 | 0.97448 | 6.1614 | 1 | 22.1614 | 60097.9524 | 1 | 22.1614 | 66097.9524
1646 | 0.47577 | 0.090473 | 1.8575 | 1 | 17.8575 | 14859.7306 | 0 | 16 | 6000
1647 | 0.23412 | 0.24062 | 2.4783 | 1 | 18.4783 | 19826.6905 | 0 | 16 | 6000
1648 | 0.37572 | 0.77468 | 4.4949 | 1 | 20.4949 | 38433.9012 | 0 | 16 | 6000
1649 | 0.9225 | 0.40744 | 3.0613 | 0 | 16 | 0 | 0 | 16 | 6000
1650 | 0.32983 | 0.23696 | 2.465 | 1 | 18.465 | 19719.604 | 0 | 16 | 6000
1651 | 0.72484 | 0.27905 | 2.6165 | 0 | 16 | 0 | 0 | 16 | 6000
1652 | 0.72649 | 0.6787 | 4.0592 | 0 | 16 | 0 | 0 | 16 | 6000
1653 | 0.55661 | 0.3765 | 2.955 | 0 | 16 | 0 | 0 | 16 | 6000
1654 | 0.26839 | 0.47002 | 3.2775 | 1 | 19.2775 | 26220.0159 | 0 | 16 | 6000
1655 | 0.40116 | 0.52716 | 3.4791 | 1 | 19.4791 | 27832.871 | 0 | 16 | 6000
1656 | 0.87124 | 0.49604 | 3.3686 | 0 | 16 | 0 | 0 | 16 | 6000
1657 | 0.051257 | 0.42153 | 3.1097 | 1 | 19.1097 | 24877.9373 | 1 | 19.1097 | 30877.9373
1658 | 0.52295 | 0.91258 | 5.3796 | 0 | 16 | 0 | 0 | 16 | 6000
1659 | 0.65121 | 0.50325 | 3.3941 | 0 | 16 | 0 | 0 | 16 | 6000
1660 | 0.49318 | 0.1074 | 1.9396 | 1 | 17.9396 | 15516.948 | 0 | 16 | 6000
1661 | 0.10106 | 0.85678 | 4.9595 | 1 | 20.9595 | 44473.469 | 1 | 20.9595 | 50473.469
1662 | 0.44321 | 0.25759 | 2.5399 | 1 | 18.5399 | 20318.8624 | 0 | 16 | 6000
1663 | 0.74071 | 0.40485 | 3.0524 | 0 | 16 | 0 | 0 | 16 | 6000
1664 | 0.26414 | 0.67154 | 4.0295 | 1 | 20.0295 | 32382.9461 | 0 | 16 | 6000
1665 | 0.22047 | 0.6928 | 4.1186 | 1 | 20.1186 | 33541.6151 | 0 | 16 | 6000
1666 | 0.20831 | 0.59497 | 3.728 | 1 | 19.728 | 29824.2506 | 0 | 16 | 6000
1667 | 0.71222 | 0.42657 | 3.1271 | 0 | 16 | 0 | 0 | 16 | 6000
1668 | 0.51976 | 0.94596 | 5.7235 | 0 | 16 | 0 | 0 | 16 | 6000
1669 | 0.41825 | 0.56771 | 3.6264 | 1 | 19.6264 | 29011.0498 | 0 | 16 | 6000
1670 | 0.9292 | 0.089066 | 1.8504 | 0 | 16 | 0 | 0 | 16 | 6000
1671 | 0.31839 | 0.15418 | 2.1449 | 1 | 18.1449 | 17159.1437 | 0 | 16 | 6000
1672 | 0.67444 | 0.20652 | 2.3515 | 0 | 16 | 0 | 0 | 16 | 6000
1673 | 0.55651 | 0.71158 | 4.1998 | 0 | 16 | 0 | 0 | 16 | 6000
1674 | 0.83979 | 0.55997 | 3.5979 | 0 | 16 | 0 | 0 | 16 | 6000
1675 | 0.59158 | 0.26425 | 2.5638 | 0 | 16 | 0 | 0 | 16 | 6000
1676 | 0.35825 | 0.23493 | 2.4575 | 1 | 18.4575 | 19660.0056 | 0 | 16 | 6000
1677 | 0.41976 | 0.5071 | 3.4077 | 1 | 19.4077 | 27261.4536 | 0 | 16 | 6000
1678 | 0.30246 | 0.44773 | 3.2001 | 1 | 19.2001 | 25601.065 | 0 | 16 | 6000
1679 | 0.021242 | 0.12363 | 2.0139 | 1 | 18.0139 | 16110.956 | 1 | 18.0139 | 22110.956
1680 | 0.56935 | 0.38774 | 2.9936 | 0 | 16 | 0 | 0 | 16 | 6000
1681 | 0.48827 | 0.64135 | 3.9074 | 1 | 19.9074 | 31258.8128 | 0 | 16 | 6000
1682 | 0.51661 | 0.43735 | 3.1642 | 0 | 16 | 0 | 0 | 16 | 6000
1683 | 0.019348 | 0.81361 | 4.7002 | 1 | 20.7002 | 41102.5736 | 1 | 20.7002 | 47102.5736
1684 | 0.54731 | 0.15415 | 2.1448 | 0 | 16 | 0 | 0 | 16 | 6000
1685 | 0.24622 | 0.94021 | 5.6558 | 1 | 21.6558 | 53525.9722 | 0 | 16 | 6000
1686 | 0.71692 | 0.75883 | 4.4171 | 0 | 16 | 0 | 0 | 16 | 6000
1687 | 0.47607 | 0.32149 | 2.7653 | 1 | 18.7653 | 22122.2895 | 0 | 16 | 6000
1688 | 0.60817 | 0.12371 | 2.0142 | 0 | 16 | 0 | 0 | 16 | 6000
1689 | 0.9091 | 0.77653 | 4.5042 | 0 | 16 | 0 | 0 | 16 | 6000
1690 | 0.42625 | 0.57257 | 3.6443 | 1 | 19.6443 | 29154.6904 | 0 | 16 | 6000
1691 | 0.30501 | 0.9964 | 6.9269 | 1 | 22.9269 | 70049.866 | 0 | 16 | 6000
1692 | 0.42047 | 0.59007 | 3.7096 | 1 | 19.7096 | 29676.5781 | 0 | 16 | 6000
1693 | 0.49492 | 0.33145 | 2.7998 | 1 | 18.7998 | 22398.6331 | 0 | 16 | 6000
1694 | 0.59223 | 0.070989 | 1.7549 | 0 | 16 | 0 | 0 | 16 | 6000
1695 | 0.76839 | 0.094571 | 1.8779 | 0 | 16 | 0 | 0 | 16 | 6000
1696 | 0.43686 | 0.97351 | 6.142 | 1 | 22.142 | 59845.6113 | 0 | 16 | 6000
1697 | 0.58103 | 0.87695 | 5.0971 | 0 | 16 | 0 | 0 | 16 | 6000
1698 | 0.15931 | 0.04328 | 1.5855 | 1 | 17.5855 | 12684.3758 | 1 | 17.5855 | 18684.3758
1699 | 0.82138 | 0.95411 | 5.8282 | 0 | 16 | 0 | 0 | 16 | 6000
1700 | 0.65113 | 0.73195 | 4.291 | 0 | 16 | 0 | 0 | 16 | 6000
1701 | 0.73222 | 0.71926 | 4.2339 | 0 | 16 | 0 | 0 | 16 | 6000
1702 | 0.52515 | 0.34556 | 2.8486 | 0 | 16 | 0 | 0 | 16 | 6000
1703 | 0.41733 | 0.8005 | 4.6285 | 1 | 20.6285 | 40170.9411 | 0 | 16 | 6000
1704 | 0.73103 | 0.0021243 | 1.1351 | 0 | 16 | 0 | 0 | 16 | 6000
1705 | 0.35961 | 0.39567 | 3.0209 | 1 | 19.0209 | 24166.8405 | 0 | 16 | 6000
1706 | 0.36016 | 0.13529 | 2.0651 | 1 | 18.0651 | 16520.4084 | 0 | 16 | 6000
1707 | 0.27246 | 0.58417 | 3.6874 | 1 | 19.6874 | 29499.5967 | 0 | 16 | 6000
1708 | 0.21826 | 0.14879 | 2.1225 | 1 | 18.1225 | 16979.832 | 0 | 16 | 6000
1709 | 0.11161 | 0.86318 | 5.0018 | 1 | 21.0018 | 45023.0467 | 1 | 21.0018 | 51023.0467
1710 | 0.61038 | 0.42984 | 3.1383 | 0 | 16 | 0 | 0 | 16 | 6000
1711 | 0.38854 | 0.71908 | 4.233 | 1 | 20.233 | 35029.2586 | 0 | 16 | 6000
1712 | 0.20242 | 0.4606 | 3.2447 | 1 | 19.2447 | 25957.989 | 0 | 16 | 6000
1713 | 0.45752 | 0.2708 | 2.5872 | 1 | 18.5872 | 20697.2326 | 0 | 16 | 6000
1714 | 0.23378 | 0.73766 | 4.3172 | 1 | 20.3172 | 36124.2214 | 0 | 16 | 6000
1715 | 0.81024 | 0.83009 | 4.7945 | 0 | 16 | 0 | 0 | 16 | 6000
1716 | 0.13922 | 0.43883 | 3.1694 | 1 | 19.1694 | 25354.9891 | 1 | 19.1694 | 31354.9891
1717 | 0.063467 | 0.092413 | 1.8672 | 1 | 17.8672 | 14937.3063 | 1 | 17.8672 | 20937.3063
1718 | 0.21861 | 0.59313 | 3.7211 | 1 | 19.7211 | 29768.7476 | 0 | 16 | 6000
1719 | 0.017997 | 0.9299 | 5.5446 | 1 | 21.5446 | 52079.2983 | 1 | 21.5446 | 58079.2983
1720 | 0.081975 | 0.94349 | 5.6939 | 1 | 21.6939 | 54020.351 | 1 | 21.6939 | 60020.351
1721 | 0.61501 | 0.077889 | 1.7924 | 0 | 16 | 0 | 0 | 16 | 6000
1722 | 0.75424 | 0.36692 | 2.9221 | 0 | 16 | 0 | 0 | 16 | 6000
1723 | 0.79652 | 0.63867 | 3.8967 | 0 | 16 | 0 | 0 | 16 | 6000
1724 | 0.54218 | 0.57435 | 3.6509 | 0 | 16 | 0 | 0 | 16 | 6000
1725 | 0.93462 | 0.64206 | 3.9102 | 0 | 16 | 0 | 0 | 16 | 6000
1726 | 0.54161 | 0.97721 | 6.219 | 0 | 16 | 0 | 0 | 16 | 6000
1727 | 0.99062 | 0.19925 | 2.3238 | 0 | 16 | 0 | 0 | 16 | 6000
1728 | 0.57218 | 0.99674 | 6.9554 | 0 | 16 | 0 | 0 | 16 | 6000
1729 | 0.73728 | 0.14893 | 2.123 | 0 | 16 | 0 | 0 | 16 | 6000
1730 | 0.59941 | 0.75658 | 4.4062 | 0 | 16 | 0 | 0 | 16 | 6000
1731 | 0.8113 | 0.036882 | 1.5401 | 0 | 16 | 0 | 0 | 16 | 6000
1732 | 0.027945 | 0.22651 | 2.4264 | 1 | 18.4264 | 19411.4601 | 1 | 18.4264 | 25411.4601
1733 | 0.37376 | 0.34913 | 2.8609 | 1 | 18.8609 | 22887.1888 | 0 | 16 | 6000
1734 | 0.74891 | 0.39899 | 3.0323 | 0 | 16 | 0 | 0 | 16 | 6000
1735 | 0.56837 | 0.77766 | 4.5099 | 0 | 16 | 0 | 0 | 16 | 6000
1736 | 0.62862 | 0.87496 | 5.0829 | 0 | 16 | 0 | 0 | 16 | 6000
1737 | 0.49954 | 0.51897 | 3.4499 | 1 | 19.4499 | 27598.8536 | 0 | 16 | 6000
1738 | 0.91893 | 0.23456 | 2.4562 | 0 | 16 | 0 | 0 | 16 | 6000
1739 | 0.2495 | 0.245 | 2.4943 | 1 | 18.4943 | 19954.4489 | 0 | 16 | 6000
1740 | 0.35301 | 0.33638 | 2.8169 | 1 | 18.8169 | 22534.9462 | 0 | 16 | 6000
1741 | 0.97989 | 0.025223 | 1.4467 | 0 | 16 | 0 | 0 | 16 | 6000
1742 | 0.37427 | 0.27782 | 2.6121 | 1 | 18.6121 | 20897.0778 | 0 | 16 | 6000
1743 | 0.67241 | 0.62507 | 3.8434 | 0 | 16 | 0 | 0 | 16 | 6000
1744 | 0.038906 | 0.96991 | 6.074 | 1 | 22.074 | 58962.5642 | 1 | 22.074 | 64962.5642
1745 | 0.21511 | 0.38685 | 2.9906 | 1 | 18.9906 | 23924.6461 | 0 | 16 | 6000
1746 | 0.59837 | 0.35978 | 2.8976 | 0 | 16 | 0 | 0 | 16 | 6000
1747 | 0.39562 | 0.92684 | 5.5136 | 1 | 21.5136 | 51677.041 | 0 | 16 | 6000
1748 | 0.56423 | 0.80135 | 4.6331 | 0 | 16 | 0 | 0 | 16 | 6000
1749 | 0.43638 | 0.7499 | 4.3744 | 1 | 20.3744 | 36867.1195 | 0 | 16 | 6000
1750 | 0.43957 | 0.7064 | 4.1772 | 1 | 20.1772 | 34303.3306 | 0 | 16 | 6000
1751 | 0.76021 | 0.76037 | 4.4245 | 0 | 16 | 0 | 0 | 16 | 6000
1752 | 0.38718 | 0.57285 | 3.6454 | 1 | 19.6454 | 29163.0111 | 0 | 16 | 6000
1753 | 0.35572 | 0.89264 | 5.214 | 1 | 21.214 | 47782.6382 | 0 | 16 | 6000
1754 | 0.9943 | 0.28807 | 2.6484 | 0 | 16 | 0 | 0 | 16 | 6000
1755 | 0.15788 | 0.18985 | 2.2876 | 1 | 18.2876 | 18300.686 | 1 | 18.2876 | 24300.686
1756 | 0.53128 | 0.43108 | 3.1426 | 0 | 16 | 0 | 0 | 16 | 6000
1757 | 0.1834 | 0.5002 | 3.3833 | 1 | 19.3833 | 27066.4538 | 1 | 19.3833 | 33066.4538
1758 | 0.034778 | 0.45025 | 3.2088 | 1 | 19.2088 | 25670.7377 | 1 | 19.2088 | 31670.7377
1759 | 0.80132 | 0.92312 | 5.4771 | 0 | 16 | 0 | 0 | 16 | 6000
1760 | 0.66307 | 0.9001 | 5.2735 | 0 | 16 | 0 | 0 | 16 | 6000
1761 | 0.076496 | 0.03105 | 1.4954 | 1 | 17.4954 | 11963.203 | 1 | 17.4954 | 17963.203
1762 | 0.37323 | 0.65146 | 3.9477 | 1 | 19.9477 | 31581.6329 | 0 | 16 | 6000
1763 | 0.37701 | 0.8689 | 5.0406 | 1 | 21.0406 | 45527.571 | 0 | 16 | 6000
1764 | 0.31156 | 0.56497 | 3.6163 | 1 | 19.6163 | 28930.2791 | 0 | 16 | 6000
1765 | 0.77987 | 0.16595 | 2.193 | 0 | 16 | 0 | 0 | 16 | 6000
1766 | 0.45589 | 0.74981 | 4.374 | 1 | 20.374 | 36861.9384 | 0 | 16 | 6000
1767 | 0.96654 | 0.78218 | 4.5328 | 0 | 16 | 0 | 0 | 16 | 6000
1768 | 0.8285 | 0.55001 | 3.5616 | 0 | 16 | 0 | 0 | 16 | 6000
1769 | 0.95153 | 0.76065 | 4.4258 | 0 | 16 | 0 | 0 | 16 | 6000
1770 | 0.061104 | 0.57313 | 3.6464 | 1 | 19.6464 | 29171.2009 | 1 | 19.6464 | 35171.2009
1771 | 0.41258 | 0.28109 | 2.6237 | 1 | 18.6237 | 20989.727 | 0 | 16 | 6000
1772 | 0.34698 | 0.61653 | 3.8103 | 1 | 19.8103 | 30482.3455 | 0 | 16 | 6000
1773 | 0.76703 | 0.02506 | 1.4452 | 0 | 16 | 0 | 0 | 16 | 6000
1774 | 0.25593 | 0.24114 | 2.4802 | 1 | 18.4802 | 19841.7617 | 0 | 16 | 6000
1775 | 0.31877 | 0.77266 | 4.4848 | 1 | 20.4848 | 38302.7032 | 0 | 16 | 6000
1776 | 0.015654 | 0.15605 | 2.1526 | 1 | 18.1526 | 17221.0341 | 1 | 18.1526 | 23221.0341
1777 | 0.63135 | 0.20089 | 2.3301 | 0 | 16 | 0 | 0 | 16 | 6000
1778 | 0.97593 | 0.21701 | 2.3911 | 0 | 16 | 0 | 0 | 16 | 6000
1779 | 0.89843 | 0.20157 | 2.3327 | 0 | 16 | 0 | 0 | 16 | 6000
1780 | 0.19505 | 0.4571 | 3.2326 | 1 | 19.2326 | 25860.7737 | 1 | 19.2326 | 31860.7737
1781 | 0.28496 | 0.86193 | 4.9934 | 1 | 20.9934 | 44914.8065 | 0 | 16 | 6000
1782 | 0.67697 | 0.16142 | 2.1746 | 0 | 16 | 0 | 0 | 16 | 6000
1783 | 0.55631 | 0.6101 | 3.7856 | 0 | 16 | 0 | 0 | 16 | 6000
1784 | 0.66097 | 0.20088 | 2.3301 | 0 | 16 | 0 | 0 | 16 | 6000
1785 | 0.52634 | 0.16956 | 2.2075 | 0 | 16 | 0 | 0 | 16 | 6000
1786 | 0.74426 | 0.48193 | 3.3191 | 0 | 16 | 0 | 0 | 16 | 6000
1787 | 0.16358 | 0.083656 | 1.8227 | 1 | 17.8227 | 14581.6946 | 1 | 17.8227 | 20581.6946
1788 | 0.71795 | 0.93541 | 5.6025 | 0 | 16 | 0 | 0 | 16 | 6000
1789 | 0.13566 | 0.63963 | 3.9005 | 1 | 19.9005 | 31204.2208 | 1 | 19.9005 | 37204.2208
1790 | 0.93549 | 0.71276 | 4.205 | 0 | 16 | 0 | 0 | 16 | 6000
1791 | 0.16689 | 0.8344 | 4.82 | 1 | 20.82 | 42660.5622 | 1 | 20.82 | 48660.5622
1792 | 0.59724 | 0.43653 | 3.1614 | 0 | 16 | 0 | 0 | 16 | 6000
1793 | 0.9063 | 0.27425 | 2.5995 | 0 | 16 | 0 | 0 | 16 | 6000
1794 | 0.93822 | 0.54662 | 3.5492 | 0 | 16 | 0 | 0 | 16 | 6000
1795 | 0.94873 | 0.57328 | 3.6469 | 0 | 16 | 0 | 0 | 16 | 6000
1796 | 0.69401 | 0.11235 | 1.9626 | 0 | 16 | 0 | 0 | 16 | 6000
1797 | 0.53987 | 0.45308 | 3.2187 | 0 | 16 | 0 | 0 | 16 | 6000
1798 | 0.62719 | 0.193 | 2.2998 | 0 | 16 | 0 | 0 | 16 | 6000
1799 | 0.90124 | 0.62366 | 3.8379 | 0 | 16 | 0 | 0 | 16 | 6000
1800 | 0.41433 | 0.32334 | 2.7717 | 1 | 18.7717 | 22173.7505 | 0 | 16 | 6000
1801 | 0.25218 | 0.98939 | 6.5596 | 1 | 22.5596 | 65274.9698 | 0 | 16 | 6000
1802 | 0.90549 | 0.86232 | 4.996 | 0 | 16 | 0 | 0 | 16 | 6000
1803 | 0.39872 | 0.85596 | 4.9542 | 1 | 20.9542 | 44404.1203 | 0 | 16 | 6000
1804 | 0.47094 | 0.83229 | 4.8075 | 1 | 20.8075 | 42496.8917 | 0 | 16 | 6000
1805 | 0.8483 | 0.92464 | 5.4919 | 0 | 16 | 0 | 0 | 16 | 6000
1806 | 0.23807 | 0.082288 | 1.8156 | 1 | 17.8156 | 14524.8389 | 0 | 16 | 6000
1807 | 0.71039 | 0.22653 | 2.4265 | 0 | 16 | 0 | 0 | 16 | 6000
1808 | 0.92042 | 0.73133 | 4.2882 | 0 | 16 | 0 | 0 | 16 | 6000
1809 | 0.23762 | 0.79051 | 4.5758 | 1 | 20.5758 | 39485.2149 | 0 | 16 | 6000
1810 | 0.49819 | 0.55988 | 3.5976 | 1 | 19.5976 | 28780.8712 | 0 | 16 | 6000
1811 | 0.59392 | 0.96799 | 6.04 | 0 | 16 | 0 | 0 | 16 | 6000
1812 | 0.59609 | 0.77146 | 4.4789 | 0 | 16 | 0 | 0 | 16 | 6000
1813 | 0.5071 | 0.48685 | 3.3363 | 0 | 16 | 0 | 0 | 16 | 6000
1814 | 0.16588 | 0.68237 | 4.0745 | 1 | 20.0745 | 32968.7366 | 1 | 20.0745 | 38968.7366
1815 | 0.54893 | 0.83091 | 4.7993 | 0 | 16 | 0 | 0 | 16 | 6000
1816 | 0.68834 | 0.56301 | 3.6091 | 0 | 16 | 0 | 0 | 16 | 6000
1817 | 0.94288 | 0.73127 | 4.2879 | 0 | 16 | 0 | 0 | 16 | 6000
1818 | 0.90709 | 0.62391 | 3.8389 | 0 | 16 | 0 | 0 | 16 | 6000
1819 | 0.20257 | 0.2961 | 2.6766 | 1 | 18.6766 | 21413.1852 | 0 | 16 | 6000
1820 | 0.66685 | 0.9257 | 5.5023 | 0 | 16 | 0 | 0 | 16 | 6000
1821 | 0.70925 | 0.58439 | 3.6883 | 0 | 16 | 0 | 0 | 16 | 6000
1822 | 0.62629 | 0.30293 | 2.7006 | 0 | 16 | 0 | 0 | 16 | 6000
1823 | 0.13143 | 0.06425 | 1.7168 | 1 | 17.7168 | 13734.7109 | 1 | 17.7168 | 19734.7109
1824 | 0.73414 | 0.53453 | 3.5056 | 0 | 16 | 0 | 0 | 16 | 6000
1825 | 0.71691 | 0.86581 | 5.0195 | 0 | 16 | 0 | 0 | 16 | 6000
1826 | 0.12358 | 0.31207 | 2.7325 | 1 | 18.7325 | 21860.2491 | 1 | 18.7325 | 27860.2491
1827 | 0.16409 | 0.83806 | 4.842 | 1 | 20.842 | 42946.0692 | 1 | 20.842 | 48946.0692
1828 | 0.57028 | 0.24921 | 2.5096 | 0 | 16 | 0 | 0 | 16 | 6000
1829 | 0.45576 | 0.7067 | 4.1785 | 1 | 20.1785 | 34320.3753 | 0 | 16 | 6000
1830 | 0.057603 | 0.50355 | 3.3951 | 1 | 19.3951 | 27160.8973 | 1 | 19.3951 | 33160.8973
1831 | 0.80638 | 0.88541 | 5.1589 | 0 | 16 | 0 | 0 | 16 | 6000
1832 | 0.59009 | 0.52334 | 3.4654 | 0 | 16 | 0 | 0 | 16 | 6000
1833 | 0.22446 | 0.018363 | 1.3818 | 1 | 17.3818 | 11054.6865 | 0 | 16 | 6000
1834 | 0.29287 | 0.10331 | 1.9202 | 1 | 17.9202 | 15361.8373 | 0 | 16 | 6000
1835 | 0.85869 | 0.024578 | 1.441 | 0 | 16 | 0 | 0 | 16 | 6000
1836 | 0.82399 | 0.37656 | 2.9552 | 0 | 16 | 0 | 0 | 16 | 6000
1837 | 0.45739 | 0.18607 | 2.2729 | 1 | 18.2729 | 18183.027 | 0 | 16 | 6000
1838 | 0.59709 | 0.12906 | 2.0379 | 0 | 16 | 0 | 0 | 16 | 6000
1839 | 0.41781 | 0.72916 | 4.2784 | 1 | 20.2784 | 35618.6832 | 0 | 16 | 6000
1840 | 0.040555 | 0.50117 | 3.3867 | 1 | 19.3867 | 27093.7122 | 1 | 19.3867 | 33093.7122
1841 | 0.0049913 | 0.24209 | 2.4837 | 1 | 18.4837 | 19869.4881 | 1 | 18.4837 | 25869.4881
1842 | 0.44697 | 0.082642 | 1.8175 | 1 | 17.8175 | 14539.6146 | 0 | 16 | 6000
1843 | 0.80749 | 0.61813 | 3.8165 | 0 | 16 | 0 | 0 | 16 | 6000
1844 | 0.84579 | 0.70284 | 4.1617 | 0 | 16 | 0 | 0 | 16 | 6000
1845 | 0.28326 | 0.9862 | 6.451 | 1 | 22.451 | 63863.2032 | 0 | 16 | 6000
1846 | 0.24182 | 0.15465 | 2.1468 | 1 | 18.1468 | 17174.7511 | 0 | 16 | 6000
1847 | 0.22677 | 0.30128 | 2.6948 | 1 | 18.6948 | 21558.5815 | 0 | 16 | 6000
1848 | 0.86098 | 0.783 | 4.537 | 0 | 16 | 0 | 0 | 16 | 6000
1849 | 0.42669 | 0.58599 | 3.6943 | 1 | 19.6943 | 29554.1186 | 0 | 16 | 6000
1850 | 0.44547 | 0.58126 | 3.6766 | 1 | 19.6766 | 29412.9657 | 0 | 16 | 6000
1851 | 0.50102 | 0.60581 | 3.7692 | 0 | 16 | 0 | 0 | 16 | 6000
1852 | 0.60877 | 0.28889 | 2.6513 | 0 | 16 | 0 | 0 | 16 | 6000
1853 | 0.35662 | 0.22571 | 2.4235 | 1 | 18.4235 | 19387.7478 | 0 | 16 | 6000
1854 | 0.38207 | 0.7029 | 4.162 | 1 | 20.162 | 34105.7215 | 0 | 16 | 6000
1855 | 0.80339 | 0.62031 | 3.8249 | 0 | 16 | 0 | 0 | 16 | 6000
1856 | 0.24146 | 0.10964 | 1.9501 | 1 | 17.9501 | 15600.4994 | 0 | 16 | 6000
1857 | 0.83551 | 0.49698 | 3.3719 | 0 | 16 | 0 | 0 | 16 | 6000
1858 | 0.74737 | 0.67446 | 4.0415 | 0 | 16 | 0 | 0 | 16 | 6000
1859 | 0.30731 | 0.62742 | 3.8526 | 1 | 19.8526 | 30820.432 | 0 | 16 | 6000
1860 | 0.049843 | 0.14154 | 2.0919 | 1 | 18.0919 | 16734.8421 | 1 | 18.0919 | 22734.8421
1861 | 0.044295 | 0.38937 | 2.9992 | 1 | 18.9992 | 23993.9816 | 1 | 18.9992 | 29993.9816
1862 | 0.20262 | 0.88243 | 5.1368 | 1 | 21.1368 | 46778.4451 | 0 | 16 | 6000
1863 | 0.15438 | 0.20363 | 2.3406 | 1 | 18.3406 | 18724.5566 | 1 | 18.3406 | 24724.5566
1864 | 0.1582 | 0.48983 | 3.3468 | 1 | 19.3468 | 26774.2112 | 1 | 19.3468 | 32774.2112
1865 | 0.69321 | 0.61397 | 3.8004 | 0 | 16 | 0 | 0 | 16 | 6000
1866 | 0.46243 | 0.83017 | 4.795 | 1 | 20.795 | 42334.6769 | 0 | 16 | 6000
1867 | 0.13651 | 0.69594 | 4.132 | 1 | 20.132 | 33716.1223 | 1 | 20.132 | 39716.1223
1868 | 0.66184 | 0.11781 | 1.9877 | 0 | 16 | 0 | 0 | 16 | 6000
1869 | 0.13887 | 0.044458 | 1.5936 | 1 | 17.5936 | 12748.5994 | 1 | 17.5936 | 18748.5994
1870 | 0.079019 | 0.9558 | 5.8514 | 1 | 21.8514 | 56067.7077 | 1 | 21.8514 | 62067.7077
1871 | 0.45057 | 0.22707 | 2.4285 | 1 | 18.4285 | 19428.0335 | 0 | 16 | 6000
1872 | 0.10389 | 0.31659 | 2.7483 | 1 | 18.7483 | 21986.1712 | 1 | 18.7483 | 27986.1712
1873 | 0.2268 | 0.38984 | 3.0008 | 1 | 19.0008 | 24006.7174 | 0 | 16 | 6000
1874 | 0.1853 | 0.22966 | 2.4381 | 1 | 18.4381 | 19504.5795 | 1 | 18.4381 | 25504.5795
1875 | 0.046237 | 0.50655 | 3.4057 | 1 | 19.4057 | 27245.9909 | 1 | 19.4057 | 33245.9909
1876 | 0.4615 | 0.52575 | 3.4741 | 1 | 19.4741 | 27792.6877 | 0 | 16 | 6000
1877 | 0.86959 | 0.68544 | 4.0874 | 0 | 16 | 0 | 0 | 16 | 6000
1878 | 0.067688 | 0.031614 | 1.4999 | 1 | 17.4999 | 11999.0572 | 1 | 17.4999 | 17999.0572
1879 | 0.39955 | 0.41668 | 3.0931 | 1 | 19.0931 | 24744.5084 | 0 | 16 | 6000
1880 | 0.94744 | 0.42122 | 3.1087 | 0 | 16 | 0 | 0 | 16 | 6000
1881 | 0.86625 | 0.88876 | 5.1842 | 0 | 16 | 0 | 0 | 16 | 6000
1882 | 0.83119 | 0.51159 | 3.4236 | 0 | 16 | 0 | 0 | 16 | 6000
1883 | 0.50156 | 0.80672 | 4.6622 | 0 | 16 | 0 | 0 | 16 | 6000
1884 | 0.97023 | 0.32326 | 2.7714 | 0 | 16 | 0 | 0 | 16 | 6000
1885 | 0.47062 | 0.62032 | 3.8249 | 1 | 19.8249 | 30599.3733 | 0 | 16 | 6000
1886 | 0.4186 | 0.18576 | 2.2717 | 1 | 18.2717 | 18173.3858 | 0 | 16 | 6000
1887 | 0.13141 | 0.42459 | 3.1203 | 1 | 19.1203 | 24962.302 | 1 | 19.1203 | 30962.302
1888 | 0.52088 | 0.89077 | 5.1996 | 0 | 16 | 0 | 0 | 16 | 6000
1889 | 0.22836 | 0.62245 | 3.8332 | 1 | 19.8332 | 30665.533 | 0 | 16 | 6000
1890 | 0.1624 | 0.664 | 3.9985 | 1 | 19.9985 | 31988.1208 | 1 | 19.9985 | 37988.1208
1891 | 0.84479 | 0.75805 | 4.4133 | 0 | 16 | 0 | 0 | 16 | 6000
1892 | 0.53483 | 0.82237 | 4.7497 | 0 | 16 | 0 | 0 | 16 | 6000
1893 | 0.80601 | 0.57262 | 3.6445 | 0 | 16 | 0 | 0 | 16 | 6000
1894 | 0.74376 | 0.42829 | 3.133 | 0 | 16 | 0 | 0 | 16 | 6000
1895 | 0.88874 | 0.63795 | 3.8939 | 0 | 16 | 0 | 0 | 16 | 6000
1896 | 0.59311 | 0.68992 | 4.1064 | 0 | 16 | 0 | 0 | 16 | 6000
1897 | 0.30728 | 0.63191 | 3.8701 | 1 | 19.8701 | 30960.8041 | 0 | 16 | 6000
1898 | 0.31262 | 0.8764 | 5.0932 | 1 | 21.0932 | 46210.9601 | 0 | 16 | 6000
1899 | 0.11547 | 0.43685 | 3.1625 | 1 | 19.1625 | 25300.1629 | 1 | 19.1625 | 31300.1629
1900 | 0.56049 | 0.69493 | 4.1277 | 0 | 16 | 0 | 0 | 16 | 6000
1901 | 0.24615 | 0.0056421 | 1.2153 | 1 | 17.2153 | 9722.6005 | 0 | 16 | 6000
1902 | 0.84629 | 0.001175 | 1.102 | 0 | 16 | 0 | 0 | 16 | 6000
1903 | 0.26417 | 0.67612 | 4.0484 | 1 | 20.0484 | 32629.819 | 0 | 16 | 6000
1904 | 0.068192 | 0.075726 | 1.7808 | 1 | 17.7808 | 14246.5729 | 1 | 17.7808 | 20246.5729
1905 | 0.62041 | 0.52851 | 3.4839 | 0 | 16 | 0 | 0 | 16 | 6000
1906 | 0.075861 | 0.09156 | 1.8629 | 1 | 17.8629 | 14903.2807 | 1 | 17.8629 | 20903.2807
1907 | 0.23945 | 0.043602 | 1.5878 | 1 | 17.5878 | 12702.0046 | 0 | 16 | 6000
1908 | 0.39483 | 0.64224 | 3.9109 | 1 | 19.9109 | 31287.2733 | 0 | 16 | 6000
1909 | 0.90264 | 0.36058 | 2.9003 | 0 | 16 | 0 | 0 | 16 | 6000
1910 | 0.84972 | 0.06118 | 1.6989 | 0 | 16 | 0 | 0 | 16 | 6000
1911 | 0.84553 | 0.031372 | 1.498 | 0 | 16 | 0 | 0 | 16 | 6000
1912 | 0.76812 | 0.65218 | 3.9506 | 0 | 16 | 0 | 0 | 16 | 6000
1913 | 0.20127 | 0.20483 | 2.3451 | 1 | 18.3451 | 18761.077 | 0 | 16 | 6000
1914 | 0.97913 | 0.50338 | 3.3945 | 0 | 16 | 0 | 0 | 16 | 6000
1915 | 0.75039 | 0.1391 | 2.0815 | 0 | 16 | 0 | 0 | 16 | 6000
1916 | 0.55361 | 0.53703 | 3.5146 | 0 | 16 | 0 | 0 | 16 | 6000
1917 | 0.13145 | 0.47127 | 3.2819 | 1 | 19.2819 | 26255.0044 | 1 | 19.2819 | 32255.0044
1918 | 0.67173 | 0.30371 | 2.7033 | 0 | 16 | 0 | 0 | 16 | 6000
1919 | 0.92334 | 0.78747 | 4.56 | 0 | 16 | 0 | 0 | 16 | 6000
1920 | 0.8006 | 0.14368 | 2.1009 | 0 | 16 | 0 | 0 | 16 | 6000
1921 | 0.59458 | 0.56398 | 3.6126 | 0 | 16 | 0 | 0 | 16 | 6000
1922 | 0.66545 | 0.99096 | 6.6216 | 0 | 16 | 0 | 0 | 16 | 6000
1923 | 0.38738 | 0.27837 | 2.6141 | 1 | 18.6141 | 20912.7772 | 0 | 16 | 6000
1924 | 0.29284 | 0.0038369 | 1.179 | 1 | 17.179 | 9432.0517 | 0 | 16 | 6000
1925 | 0.56369 | 0.010478 | 1.2903 | 0 | 16 | 0 | 0 | 16 | 6000
1926 | 0.55597 | 0.21915 | 2.3991 | 0 | 16 | 0 | 0 | 16 | 6000
1927 | 0.94287 | 0.84596 | 4.8905 | 0 | 16 | 0 | 0 | 16 | 6000
1928 | 0.86939 | 0.034075 | 1.519 | 0 | 16 | 0 | 0 | 16 | 6000
1929 | 0.59065 | 0.54267 | 3.535 | 0 | 16 | 0 | 0 | 16 | 6000
1930 | 0.48955 | 0.74027 | 4.3293 | 1 | 20.3293 | 36280.6399 | 0 | 16 | 6000
1931 | 0.41551 | 0.90018 | 5.2742 | 1 | 21.2742 | 48564.7072 | 0 | 16 | 6000
1932 | 0.38449 | 0.26499 | 2.5664 | 1 | 18.5664 | 20531.2932 | 0 | 16 | 6000
1933 | 0.13412 | 0.53262 | 3.4987 | 1 | 19.4987 | 27989.7658 | 1 | 19.4987 | 33989.7658
1934 | 0.16051 | 0.93317 | 5.5786 | 1 | 21.5786 | 52522.2571 | 1 | 21.5786 | 58522.2571
1935 | 0.56856 | 0.55725 | 3.588 | 0 | 16 | 0 | 0 | 16 | 6000
1936 | 0.77093 | 0.62336 | 3.8367 | 0 | 16 | 0 | 0 | 16 | 6000
1937 | 0.067602 | 0.55897 | 3.5943 | 1 | 19.5943 | 28754.2035 | 1 | 19.5943 | 34754.2035
1938 | 0.73756 | 0.10665 | 1.936 | 0 | 16 | 0 | 0 | 16 | 6000
1939 | 0.77094 | 0.27647 | 2.6074 | 0 | 16 | 0 | 0 | 16 | 6000
1940 | 0.95769 | 0.1346 | 2.0621 | 0 | 16 | 0 | 0 | 16 | 6000
1941 | 0.0366 | 0.249 | 2.5088 | 1 | 18.5088 | 20070.6346 | 1 | 18.5088 | 26070.6346
1942 | 0.5872 | 0.13058 | 2.0446 | 0 | 16 | 0 | 0 | 16 | 6000
1943 | 0.28612 | 0.47564 | 3.2971 | 1 | 19.2971 | 26376.7095 | 0 | 16 | 6000
1944 | 0.81738 | 0.82483 | 4.7638 | 0 | 16 | 0 | 0 | 16 | 6000
1945 | 0.9651 | 0.69701 | 4.1366 | 0 | 16 | 0 | 0 | 16 | 6000
1946 | 0.5174 | 0.39181 | 3.0076 | 0 | 16 | 0 | 0 | 16 | 6000
1947 | 0.37374 | 0.10595 | 1.9328 | 1 | 17.9328 | 15462.1802 | 0 | 16 | 6000
1948 | 0.84658 | 0.21835 | 2.3961 | 0 | 16 | 0 | 0 | 16 | 6000
1949 | 0.60618 | 0.35285 | 2.8737 | 0 | 16 | 0 | 0 | 16 | 6000
1950 | 0.75537 | 0.48982 | 3.3468 | 0 | 16 | 0 | 0 | 16 | 6000
1951 | 0.86248 | 0.77811 | 4.5122 | 0 | 16 | 0 | 0 | 16 | 6000
1952 | 0.56997 | 0.75689 | 4.4077 | 0 | 16 | 0 | 0 | 16 | 6000
1953 | 0.36349 | 0.31923 | 2.7574 | 1 | 18.7574 | 22059.4204 | 0 | 16 | 6000
1954 | 0.22237 | 0.31978 | 2.7593 | 1 | 18.7593 | 22074.7712 | 0 | 16 | 6000
1955 | 0.94579 | 0.44851 | 3.2028 | 0 | 16 | 0 | 0 | 16 | 6000
1956 | 0.056443 | 0.34263 | 2.8385 | 1 | 18.8385 | 22707.8509 | 1 | 18.8385 | 28707.8509
1957 | 0.98655 | 0.46657 | 3.2655 | 0 | 16 | 0 | 0 | 16 | 6000
1958 | 0.60001 | 0.22033 | 2.4035 | 0 | 16 | 0 | 0 | 16 | 6000
1959 | 0.22522 | 0.79105 | 4.5786 | 1 | 20.5786 | 39521.8508 | 0 | 16 | 6000
1960 | 0.022292 | 0.63784 | 3.8935 | 1 | 19.8935 | 31147.6814 | 1 | 19.8935 | 37147.6814
1961 | 0.96904 | 0.54203 | 3.5326 | 0 | 16 | 0 | 0 | 16 | 6000
1962 | 0.25709 | 0.66479 | 4.0018 | 1 | 20.0018 | 32022.7547 | 0 | 16 | 6000
1963 | 0.062831 | 0.069617 | 1.7473 | 1 | 17.7473 | 13978.4327 | 1 | 17.7473 | 19978.4327
1964 | 0.51829 | 0.22692 | 2.428 | 0 | 16 | 0 | 0 | 16 | 6000
1965 | 0.59703 | 0.020845 | 1.4064 | 0 | 16 | 0 | 0 | 16 | 6000
1966 | 0.17959 | 0.063621 | 1.7132 | 1 | 17.7132 | 13705.5653 | 1 | 17.7132 | 19705.5653
1967 | 0.74756 | 0.7946 | 4.5972 | 0 | 16 | 0 | 0 | 16 | 6000
1968 | 0.6926 | 0.75425 | 4.3951 | 0 | 16 | 0 | 0 | 16 | 6000
1969 | 0.85683 | 0.076629 | 1.7857 | 0 | 16 | 0 | 0 | 16 | 6000
1970 | 0.94531 | 0.067116 | 1.7332 | 0 | 16 | 0 | 0 | 16 | 6000
1971 | 0.56689 | 0.72371 | 4.2537 | 0 | 16 | 0 | 0 | 16 | 6000
1972 | 0.5638 | 0.5008 | 3.3854 | 0 | 16 | 0 | 0 | 16 | 6000
1973 | 0.060044 | 0.10912 | 1.9476 | 1 | 17.9476 | 15581.1792 | 1 | 17.9476 | 21581.1792
1974 | 0.56369 | 0.77892 | 4.5162 | 0 | 16 | 0 | 0 | 16 | 6000
1975 | 0.88911 | 0.8351 | 4.8242 | 0 | 16 | 0 | 0 | 16 | 6000
1976 | 0.8573 | 0.26009 | 2.5489 | 0 | 16 | 0 | 0 | 16 | 6000
1977 | 0.082627 | 0.36516 | 2.9161 | 1 | 18.9161 | 23328.5464 | 1 | 18.9161 | 29328.5464
1978 | 0.4903 | 0.21516 | 2.3841 | 1 | 18.3841 | 19073.0302 | 0 | 16 | 6000
1979 | 0.24065 | 0.36725 | 2.9233 | 1 | 18.9233 | 23386.0578 | 0 | 16 | 6000
1980 | 0.90802 | 0.57708 | 3.661 | 0 | 16 | 0 | 0 | 16 | 6000
1981 | 0.23528 | 0.89225 | 5.2111 | 1 | 21.2111 | 47743.9837 | 0 | 16 | 6000
1982 | 0.33982 | 0.42362 | 3.1169 | 1 | 19.1169 | 24935.3977 | 0 | 16 | 6000
1983 | 0.74192 | 0.86487 | 5.0132 | 0 | 16 | 0 | 0 | 16 | 6000
1984 | 0.19543 | 0.12596 | 2.0242 | 1 | 18.0242 | 16193.7342 | 1 | 18.0242 | 22193.7342
1985 | 0.73388 | 0.08408 | 1.8249 | 0 | 16 | 0 | 0 | 16 | 6000
1986 | 0.43186 | 0.44158 | 3.1789 | 1 | 19.1789 | 25430.8864 | 0 | 16 | 6000
1987 | 0.48019 | 0.83122 | 4.8011 | 1 | 20.8011 | 42414.8295 | 0 | 16 | 6000
1988 | 0.65361 | 0.15723 | 2.1575 | 0 | 16 | 0 | 0 | 16 | 6000
1989 | 0.90503 | 0.68045 | 4.0665 | 0 | 16 | 0 | 0 | 16 | 6000
1990 | 0.61938 | 0.94293 | 5.6872 | 0 | 16 | 0 | 0 | 16 | 6000
1991 | 0.42469 | 0.23441 | 2.4556 | 1 | 18.4556 | 19644.6348 | 0 | 16 | 6000
1992 | 0.68207 | 0.28492 | 2.6373 | 0 | 16 | 0 | 0 | 16 | 6000
1993 | 0.42527 | 0.95875 | 5.8934 | 1 | 21.8934 | 56614.745 | 0 | 16 | 6000
1994 | 0.1347 | 0.9448 | 5.7094 | 1 | 21.7094 | 54222.2811 | 1 | 21.7094 | 60222.2811
1995 | 0.24823 | 0.48789 | 3.34 | 1 | 19.34 | 26719.8429 | 0 | 16 | 6000
1996 | 0.089022 | 0.69428 | 4.1249 | 1 | 20.1249 | 33623.8941 | 1 | 20.1249 | 39623.8941
1997 | 0.44078 | 0.54394 | 3.5396 | 1 | 19.5396 | 28316.5148 | 0 | 16 | 6000
1998 | 0.36058 | 0.19008 | 2.2885 | 1 | 18.2885 | 18307.9175 | 0 | 16 | 6000
1999 | 0.44365 | 0.81375 | 4.7009 | 1 | 20.7009 | 41112.2239 | 0 | 16 | 6000
2000 | 0.74657 | 0.7982 | 4.6163 | 0 | 16 | 0 | 0 | 16 | 6000

## Result
Test 1 result: hand vs Excel simulation vs the tool
The hand column is exact (formulas on Test1_Hand). Tool columns are the numbers the tool printed for the same case (seed 12345). Tolerance: 3 standard errors of each quantity for the 2,000-draw Excel run (the least precise run), computed from the exact distribution below; the two tool runs are held to the same limit.
Quantity | Hand (exact) | Excel simulation (2,000 draws) | Tool n=10,000 | Tool n=200,000 | ¦Excel - hand¦ | ¦Tool 10k - hand¦ | ¦Tool 200k - hand¦ | Tolerance | Excel | Tool 10k | Tool 200k
ACCEPT (no response)
P(delay occurs) | 0.5 | 0.512 | 0.4998 | 0.50014 | 0.012 | 0.0002 | 0.00014 | 0.033541 | PASS | PASS | PASS
Expected delay (d) | 1.75 | 1.7861 | 1.7458 | 1.7539 | 0.036084 | 0.0042077 | 0.003916 | 0.1319 | PASS | PASS | PASS
P(finish after the deadline) | 0.16782 | 0.1655 | 0.1683 | 0.16879 | 0.0023181 | 0.00048187 | 0.00097187 | 0.025069 | PASS | PASS | PASS
P90 duration (d) | 20.6259 | 20.6201 | 20.6231 | 20.6359 | 0.0058217 | 0.0027682 | 0.010013 | 0.21539 | PASS | PASS | PASS
Total expected cost (INR) | 14803.9801 | 15078.4258 | 14755.4163 | 14839.5764 | 274.4457 | 48.5637 | 35.5964 | 1155.1456 | PASS | PASS | PASS
WITH M-BUF
P(delay occurs) | 0.2 | 0.189 | n/a | n/a | 0.011 |  |  | 0.026833 | PASS
Expected delay (d) | 0.7 | 0.65757 | 0.6872 | 0.70583 | 0.042426 | 0.012798 | 0.0058252 | 0.10132 | PASS | PASS | PASS
P(finish after the deadline) | 0.067127 | 0.0625 | 0.0637 | 0.0676 | 0.0046273 | 0.0034273 | 0.00047275 | 0.016787 | PASS | PASS | PASS
P90 duration (d) | 19.3826 | 19.2112 | 19.3445 | 19.4022 | 0.17137 | 0.038083 | 0.019573 | 0.35512 | PASS | PASS | PASS
Total expected cost incl. M-BUF (INR) | 11921.592 | 11559.3577 | 11803.1557 | 11972.7094 | 362.2343 | 118.4363 | 51.1174 | 855.8165 | PASS | PASS | PASS
Decision
Source | Decision | TEC accept (INR) | TEC with M-BUF (INR) | Saving from M-BUF (INR) | Agrees with hand?
Hand (exact) | AUTHORIZE MITIGATION | 14803.9801 | 11921.592 | 2882.388 | -
Excel simulation | AUTHORIZE MITIGATION | 15078.4258 | 11559.3577 | 3519.0681 | PASS
Tool, n=10,000 | AUTHORIZE MITIGATION | 14755.4163 | 11803.1557 | 2952.2606 | PASS
Tool, n=200,000 | AUTHORIZE MITIGATION | 14839.5764 | 11972.7094 | 2866.867 | PASS
Overall | ALL CHECKS PASS
Checks counted | 31
Reading: the exact hand result, a 2,000-draw spreadsheet simulation and the tool's own simulation agree within sampling error, and all three reach the same decision. These inputs are placeholders; the result shows the arithmetic is right, not that the numbers fit a real site.
Standard error of the P90 duration at the Excel run's N (helper for the tolerance)
Quantity | Accept | With M-BUF
SE of P90 (d) = sqrt(0.9 x 0.1 / N) / density at P90 | 0.071795 | 0.11837
Density of duration at the exact P90 (per day) | 0.093435 | 0.056671