## README
Manual-calculation check of the brick-masonry delay-risk tool
What this is | Hand calculations, written as live Excel formulas, for the ILLUSTRATIVE example case (examples/example_analysis_case.json). Each tool value is the number printed by the tool in the validation run of 9 Oct 2026; the workbook recomputes the same quantity by hand and shows the difference.
Not evidence | Every probability, delay range, duration and cost in this example is an Assumption placeholder, not site data. This workbook shows the arithmetic is right, not that the numbers describe a real site.
Colour legend | Blue text on yellow = input you may change. Black = formula. Green = link to another sheet. Tool values (pasted from the validation run) are blue text on white.
Sheets | Inputs: case numbers. Risk_Calc: PERT mean, variance, EMV, totals. Matrix: 5x5 class and level by hand. Mitigation_Calc: net benefit and break-even. Options: 23 options, exact total expected cost vs tool. Copula: occurrence-correlation check. All_Checks: all 242 checks of the run. Test_Summary: counts and findings.
Exact values | Option costs on the Options sheet and the copula joint probabilities come from numerical convolution and a bivariate-normal integral (scripts in report/scripts/validation_2026-10-09/). They cannot be written as a cell formula, so they are pasted as values; every sum, rank and difference around them is a formula.
Changing inputs | If you change a blue input on Inputs, the hand columns recompute but the pasted tool columns do not, so differences will appear. Re-run the tool and paste new tool values to compare again.
Source | Case: examples/example_analysis_case.json. Tool and exact values: report/scripts/validation_2026-10-09/v1_results.json (run of 9 Oct 2026, seed 12345, n = 10,000 and 200,000). Formulas: Beta-PERT mean (a + lambda*m + b)/(lambda + 2) and variance (mean - a)(b - mean)/(lambda + 3); event EMV = p x mean delay x delay cost per day.

## Inputs
Inputs (ILLUSTRATIVE example case; all values are Assumptions)
Quantity | Value | Unit | Note
Planned duration T0 | 16 | days | activity.planned_duration_days
Deadline | 20 | days | activity.deadline_days
Delay cost Cd | 8000 | INR/day | cost.cost_per_delay_day
Liquidated damages LD | 5000 | INR/day | after the deadline
PERT lambda | 4 | - | standard Beta-PERT weight; the tool's default
Risk id | Name | p (probability) | a (min, days) | m (mode, days) | b (max, days)
R-MAT | Brick / material shortage | 0.5 | 1 | 3 | 8
R-LAB | Labour absenteeism / shortage | 0.35 | 1 | 2 | 6
R-RWK | Rework due to workmanship | 0.25 | 1 | 2 | 5
R-WX | Rain / monsoon stoppage | 0.2 | 1 | 2 | 7
R-PLAN | Poor planning or unrealistic scheduling | 0.1 | 1 | 1 | 3
R-SAFE | Unsafe conditions / work at height | 0.3 | 1 | 2 | 6
R-SKILL | Unskilled or unqualified labour | 0.22 | 1 | 2 | 5
Response id | Targets risk | Cost (INR) | p after | Delay after a | Delay after m | Delay after b | Secondary p | Secondary a | Secondary m | Secondary b | Feasible?
M-BUF | R-MAT | 6000 | 0.2 | [7 empty] | Yes
M-SUP | R-MAT | 3000 | 0.35 | [7 empty] | Yes
M-GANG | R-LAB | 9000 |  | 0 | 1 | 3 | 0.3 | 0 | 1 | 2 | Yes
M-COV | R-WX | 2500 | 0.12 | [7 empty] | Yes
M-QC | R-RWK | 1500 | 0.15 | [7 empty] | Yes
M-MECH | R-SKILL | 4000 | 0.1 | [7 empty] | No
Matrix settings
Probability class edges (lower-edge inclusive) | 0.2 | 0.4 | 0.6 | 0.8
Impact edges (fraction of T0) | 0.02 | 0.05 | 0.1 | 0.2
Level cut-offs on score (Low <=, Moderate <=, High <=) | 5 | 10 | 15

## Risk_Calc
Per-risk hand calculation vs tool
Risk id | p | Mean delay (d) =(a+lam*m+b)/(lam+2) | Variance (d^2) =(mean-a)(b-mean)/(lam+3) | EMV (INR) =p*mean*Cd | p x mean (d) | Var contribution =p(var+mean^2)-(p mean)^2 | 1 - p | Tool mean | Tool EMV (INR) | Mean diff | EMV diff (INR) | Result
R-MAT | 0.5 | 3.5 | 1.6071 | 14000 | 1.75 | 3.8661 | 0.5 | 3.5 | 14000 | 0 | 0 | PASS
R-LAB | 0.35 | 2.5 | 0.75 | 7000 | 0.875 | 1.6844 | 0.65 | 2.5 | 7000 | 0 | 0 | PASS
R-RWK | 0.25 | 2.3333 | 0.50794 | 4666.6667 | 0.58333 | 1.1478 | 0.75 | 2.3333 | 4666.6667 | 0 | 0 | PASS
R-WX | 0.2 | 2.6667 | 1.0317 | 4266.6667 | 0.53333 | 1.3441 | 0.8 | 2.6667 | 4266.6667 | 0 | 0 | PASS
R-PLAN | 0.1 | 1.3333 | 0.079365 | 1066.6667 | 0.13333 | 0.16794 | 0.9 | 1.3333 | 1066.6667 | 0 | 0 | PASS
R-SAFE | 0.3 | 2.5 | 0.75 | 6000 | 0.75 | 1.5375 | 0.7 | 2.5 | 6000 | 0 | 0 | PASS
R-SKILL | 0.22 | 2.3333 | 0.50794 | 4106.6667 | 0.51333 | 1.046 | 0.78 | 2.3333 | 4106.6667 | 0 | 0 | PASS
Totals | Hand (formula) | Tool / exact | Difference | Result
Expected total delay E[D] (d) | 5.1383 | 5.1383 | 0 | PASS
Variance of total delay (d^2) | 10.7938 | 10.7938 | 0 | PASS
Standard deviation (d) | 3.2854 | 3.2854 | 0 | PASS
Sum of event EMV (INR) | 41106.6667 | 41106.6667 | 0 | PASS
P(at least one delay) =1-PRODUCT(1-p) | 0.90418 | 0.90418 | 0 | PASS
Planned duration + E[D] (d) | 21.1383
Note: Var contribution uses E[(I*D)^2] = p(var+mean^2) and the independent-occurrence assumption (no correlation), the case the tool runs by default. Tool values are from the validation run; the tool variance is the closed form used in the tool's own tests.

## Matrix
5 x 5 matrix class and level by hand vs tool
Risk id | p | Mean delay (d) | Ratio = mean / T0 | Probability class =1+count(p>=edge) | Impact class =1+count(ratio>=edge) | Score = pc x ic | Level (hand) | Tool pc | Tool ic | Tool score | Tool level | Result
R-MAT | 0.5 | 3.5 | 0.21875 | 3 | 5 | 15 | High | 3 | 5 | 15 | High | PASS
R-LAB | 0.35 | 2.5 | 0.15625 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-RWK | 0.25 | 2.3333 | 0.14583 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-WX | 0.2 | 2.6667 | 0.16667 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-PLAN | 0.1 | 1.3333 | 0.083333 | 1 | 3 | 3 | Low | 1 | 3 | 3 | Low | PASS
R-SAFE | 0.3 | 2.5 | 0.15625 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-SKILL | 0.22 | 2.3333 | 0.14583 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
Exhaustive check in the validation run: 0 of 20,010 probability-class, 0 of 20,004 impact-class and 0 of 25 level mismatches (All_Checks, V5). Edges are lower-edge inclusive; the edge tolerance is 1e-12.

## Mitigation_Calc
Net benefit of each response, by hand vs tool
Response | Targets | EMV before (INR) | Mean delay after (d) | p after | EMV after (INR) | Secondary EMV (INR) | Cost (INR) | Net benefit (INR) =before-after-secondary-cost | Break-even reduction =cost/EMV before | Pays? | Feasible? | Tool net (INR) | Tool break-even | Net diff | Result
M-BUF | R-MAT | 14000 | 3.5 | 0.2 | 5600 | 0 | 6000 | 2400 | 0.42857 | Yes | Yes | 2400 | 0.42857 | 0 | PASS
M-SUP | R-MAT | 14000 | 3.5 | 0.35 | 9800 | 0 | 3000 | 1200 | 0.21429 | Yes | Yes | 1200 | 0.21429 | 0 | PASS
M-GANG | R-LAB | 7000 | 1.1667 | 0.35 | 3266.6667 | 2400 | 9000 | -7666.6667 | 1.2857 | No | Yes | -7666.6667 | 1.2857 | 0 | PASS
M-COV | R-WX | 4266.6667 | 2.6667 | 0.12 | 2560 | 0 | 2500 | -793.3333 | 0.58594 | No | Yes | -793.3333 | 0.58594 | 0 | PASS
M-QC | R-RWK | 4666.6667 | 2.3333 | 0.15 | 2800 | 0 | 1500 | 366.6667 | 0.32143 | Yes | Yes | 366.6667 | 0.32143 | 0 | PASS
M-MECH | R-SKILL | 4106.6667 | 2.3333 | 0.1 | 1866.6667 | 0 | 4000 | -1760 | 0.97403 | No | No | -1760 | 0.97403 | 0 | PASS
Reading: a response pays when the EMV it removes exceeds its cost plus any secondary risk it creates. M-MECH is marked not feasible in the case, so the tool keeps it out of the options even though its arithmetic net benefit is shown here.

## Options
All 23 options: exact total expected cost (TEC) vs tool
Residual expected cost and exact P90 come from numerical convolution of the mixture distributions (pasted values, blue). TEC, ranks, z-scores and the decision are formulas.
Option | Mitigation cost (INR) | Exact residual E[cost] (INR) | Exact TEC (INR) =mit cost + residual | Rank among feasible (1 = lowest TEC) | Tool TEC n=10,000 (INR) | Tool TEC n=200,000 (INR) | Standard error n=200k (INR) | z-score n=200k =(tool-exact)/SE | Exact P90 (d) | Tool P90 n=200k (d) | Exact P(finish > deadline) | Tool P(exceed) n=200k | Feasible? | ¦z¦ <= 4?
ACCEPT | 0 | 50792.7375 | 50792.7375 | 11 | 50821.0481 | 50960.9272 | 85.3564 | 1.9704 | 25.5677 | 25.5852 | 0.60185 | 0.60408 | Yes | PASS
O-M-BUF | 6000 | 39008.1783 | 45008.1783 | 3 | 44929.4269 | 45197.6844 | 75.8694 | 2.4978 | 24.2336 | 24.2765 | 0.463 | 0.4649 | Yes | PASS
O-M-SUP | 3000 | 44900.4579 | 47900.4579 | 7 | 48045.5098 | 48083.1842 | 81.8111 | 2.2335 | 24.9806 | 25.0059 | 0.53243 | 0.53509 | Yes | PASS
O-M-GANG | 9000 | 48661.1539 | 57661.1539 | 21 | 57736.6198 | 57817.0422 | 80.8284 | 1.9286 | 25.1951 | 25.2121 | 0.58727 | 0.58889 | Yes | PASS
O-M-COV | 2500 | 48318.429 | 50818.429 | 12 | 50770.295 | 51012.5888 | 82.7763 | 2.3456 | 25.2603 | 25.2866 | 0.57848 | 0.58088 | Yes | PASS
O-M-QC | 1500 | 48123.9442 | 49623.9442 | 9 | 49518.3664 | 49753.372 | 83.0343 | 1.5587 | 25.2619 | 25.2821 | 0.57499 | 0.57646 | Yes | PASS
O-M-BUF+M-GANG | 15000 | 36944.3145 | 51944.3145 | 14 | 51932.5087 | 52123.2195 | 71.0763 | 2.5171 | 23.8482 | 23.8876 | 0.43849 | 0.44001 | Yes | PASS
O-M-BUF+M-COV | 8500 | 36663.1092 | 45163.1092 | 4 | 45023.4289 | 45375.1415 | 73.121 | 2.8997 | 23.9193 | 23.9679 | 0.43439 | 0.43683 | Yes | PASS
O-M-BUF+M-QC | 7500 | 36492.0951 | 43992.0951 | 1 | 43774.4452 | 44143.4356 | 73.4511 | 2.0604 | 23.9243 | 23.9753 | 0.43129 | 0.43241 | Yes | PASS
O-M-SUP+M-GANG | 12000 | 42802.7342 | 54802.7342 | 17 | 55002.7074 | 54973.2552 | 77.2233 | 2.2082 | 24.6093 | 24.631 | 0.51288 | 0.51489 | Yes | PASS
O-M-SUP+M-COV | 5500 | 42490.7691 | 47990.7691 | 8 | 48072.5595 | 48197.9074 | 79.1608 | 2.6167 | 24.6741 | 24.6957 | 0.50643 | 0.50935 | Yes | PASS
O-M-SUP+M-QC | 4500 | 42308.0196 | 46808.0196 | 5 | 46805.2802 | 46951.9814 | 79.4503 | 1.812 | 24.6759 | 24.7009 | 0.50314 | 0.50504 | Yes | PASS
O-M-GANG+M-COV | 11500 | 46196.2173 | 57696.2173 | 22 | 57700.1291 | 57880.4858 | 78.1568 | 2.3577 | 24.8825 | 24.9123 | 0.56274 | 0.56446 | Yes | PASS
O-M-GANG+M-QC | 10500 | 46006 | 56506 | 19 | 56444.8358 | 56622.4458 | 78.4129 | 1.485 | 24.8854 | 24.9135 | 0.55948 | 0.56031 | Yes | PASS
O-M-COV+M-QC | 4000 | 45674.0112 | 49674.0112 | 10 | 49490.8114 | 49828.7253 | 80.4052 | 1.9242 | 24.9527 | 24.9861 | 0.55064 | 0.55244 | Yes | PASS
O-M-BUF+M-GANG+M-COV | 17500 | 34618.2341 | 52118.2341 | 15 | 52044.404 | 52320.5678 | 68.2372 | 2.9652 | 23.5289 | 23.5619 | 0.40812 | 0.41014 | Yes | PASS
O-M-BUF+M-GANG+M-QC | 16500 | 34455.1566 | 50955.1566 | 13 | 50810.9739 | 51095.3876 | 68.5713 | 2.045 | 23.5373 | 23.5831 | 0.40555 | 0.40608 | Yes | PASS
O-M-BUF+M-COV+M-QC | 10000 | 34179.8173 | 44179.8173 | 2 | 43904.591 | 44353.3251 | 70.6662 | 2.4553 | 23.6077 | 23.647 | 0.40206 | 0.40393 | Yes | PASS
O-M-SUP+M-GANG+M-COV | 14500 | 40407.2257 | 54907.2257 | 18 | 55042.0925 | 55104.1927 | 74.4837 | 2.6444 | 24.2982 | 24.3237 | 0.48543 | 0.48776 | Yes | PASS
O-M-SUP+M-GANG+M-QC | 13500 | 40230.5783 | 53730.5783 | 16 | 53786.0955 | 53862.5876 | 74.7736 | 1.7655 | 24.3017 | 24.3295 | 0.48252 | 0.48351 | Yes | PASS
O-M-SUP+M-COV+M-QC | 7000 | 39926.9143 | 46926.9143 | 6 | 46862.8858 | 47094.8691 | 76.7563 | 2.1882 | 24.3678 | 24.3963 | 0.47635 | 0.4787 | Yes | PASS
O-M-GANG+M-COV+M-QC | 13000 | 43567.2973 | 56567.2973 | 20 | 56430.5766 | 56711.5194 | 75.6875 | 1.9055 | 24.5707 | 24.5948 | 0.53399 | 0.53511 | Yes | PASS
O-M-MECH | 4000 | 47580.1244 | 51580.1244 | - | 51554.9161 | 51760.5689 | 82.3718 | 2.1906 | 25.1895 | 25.2149 | 0.56996 | 0.57252 | No | PASS
Hand-best feasible option | O-M-BUF+M-QC
Its exact TEC (INR) | 43992.0951
Tool's chosen option, n=10,000 | O-M-BUF+M-QC
Tool's chosen option, n=200,000 | O-M-BUF+M-QC
Decision agrees? | PASS
Tool command at n=10,000 | AUTHORIZE MITIGATION
Gap: 2nd best minus best TEC (INR) | 187.7222
A gap of a few hundred INR between first and second option is small against a cost scale of about 44,000 INR: treat the choice between them as not firm. Largest ¦z¦ at n=200,000 is 2.97 for one of 23 options, consistent with chance (see Test_Summary).

## Copula
Occurrence correlation (Gaussian copula): joint probability vs bivariate-normal value
rho | Exact P(A and B) (bivariate normal) | Tool P(A and B) | Difference | Tool marginal A | Tool marginal B | Result
-0.5 | 0.053485 | 0.053298 | -0.0001862 | 0.39916 | 0.30019 | PASS
0 | 0.12 | 0.12008 | 7.6667e-05 | 0.39916 | 0.30044 | PASS
0.6 | 0.2085 | 0.20837 | -0.00013224 | 0.39916 | 0.30024 | PASS
0.95 | 0.28722 | 0.28687 | -0.00035054 | 0.39916 | 0.2994 | PASS
Independent case (rho = 0) must equal pA x pB by hand:
pA x pB | 0.12 | Marginals set to 0.40 and 0.30 in the test.

## All_Checks
All 242 checks of the hand-calculation run (9 Oct 2026, code before fixes F1-F6; F6 case in row for V11)
Check id | Description | Hand / exact | Tool | ¦Difference¦ (formula) | Tolerance | Result (formula) | Result in run | Note
V1-mean-PERT(1,3,8) | mean PERT(1,3,8): hand vs tool formula | 3.5 | 3.5 | 0 | 1e-12 | PASS | PASS
V1-var-PERT(1,3,8) | variance PERT(1,3,8): hand vs tool formula | 1.6071 | 1.6071 | 0 | 1e-12 | PASS | PASS
V1-qmean-PERT(1,3,8) | mean PERT(1,3,8): hand vs integral of tool inverse-CDF | 3.5 | 3.5 | 2.6064e-09 | 0.0002 | PASS | PASS
V1-qvar-PERT(1,3,8) | variance PERT(1,3,8): hand vs variance of tool inverse-CDF | 1.6071 | 1.6071 | 2.4278e-08 | 0.0032143 | PASS | PASS
V1-cdf-PERT(1,3,8) | inverse-CDF round trip via independent CDF PERT(1,3,8) | 0 | 9.992e-16 | 9.992e-16 | 1e-05 | PASS | PASS
V1-mean-PERT(1,2,6) | mean PERT(1,2,6): hand vs tool formula | 2.5 | 2.5 | 0 | 1e-12 | PASS | PASS
V1-var-PERT(1,2,6) | variance PERT(1,2,6): hand vs tool formula | 0.75 | 0.75 | 0 | 1e-12 | PASS | PASS
V1-qmean-PERT(1,2,6) | mean PERT(1,2,6): hand vs integral of tool inverse-CDF | 2.5 | 2.5 | 2.8332e-09 | 0.0002 | PASS | PASS
V1-qvar-PERT(1,2,6) | variance PERT(1,2,6): hand vs variance of tool inverse-CDF | 0.75 | 0.75 | 1.9573e-08 | 0.002 | PASS | PASS
V1-cdf-PERT(1,2,6) | inverse-CDF round trip via independent CDF PERT(1,2,6) | 0 | 9.992e-16 | 9.992e-16 | 1e-05 | PASS | PASS
V1-mean-PERT(0,1,3) | mean PERT(0,1,3): hand vs tool formula | 1.1667 | 1.1667 | 0 | 1e-12 | PASS | PASS
V1-var-PERT(0,1,3) | variance PERT(0,1,3): hand vs tool formula | 0.30556 | 0.30556 | 0 | 1e-12 | PASS | PASS
V1-qmean-PERT(0,1,3) | mean PERT(0,1,3): hand vs integral of tool inverse-CDF | 1.1667 | 1.1667 | 8.3847e-10 | 0.0002 | PASS | PASS
V1-qvar-PERT(0,1,3) | variance PERT(0,1,3): hand vs variance of tool inverse-CDF | 0.30556 | 0.30556 | 3.4312e-09 | 0.002 | PASS | PASS
V1-cdf-PERT(0,1,3) | inverse-CDF round trip via independent CDF PERT(0,1,3) | 0 | 1.1102e-15 | 1.1102e-15 | 1e-05 | PASS | PASS
V1-mean-PERT(1,3,8) lam=6 | mean PERT(1,3,8) lam=6: hand vs tool formula | 3.375 | 3.375 | 0 | 1e-12 | PASS | PASS
V1-var-PERT(1,3,8) lam=6 | variance PERT(1,3,8) lam=6: hand vs tool formula | 1.2205 | 1.2205 | 0 | 1e-12 | PASS | PASS
V1-qmean-PERT(1,3,8) lam=6 | mean PERT(1,3,8) lam=6: hand vs integral of tool inverse-CDF | 3.375 | 3.375 | 5.6117e-09 | 0.0002 | PASS | PASS
V1-qvar-PERT(1,3,8) lam=6 | variance PERT(1,3,8) lam=6: hand vs variance of tool inverse-CDF | 1.2205 | 1.2205 | 5.3628e-08 | 0.002441 | PASS | PASS
V1-cdf-PERT(1,3,8) lam=6 | inverse-CDF round trip via independent CDF PERT(1,3,8) lam=6 | 0 | 1.1102e-15 | 1.1102e-15 | 1e-05 | PASS | PASS
V1-mean-PERT(2,2,9) m=a | mean PERT(2,2,9) m=a: hand vs tool formula | 3.1667 | 3.1667 | 0 | 1e-12 | PASS | PASS
V1-var-PERT(2,2,9) m=a | variance PERT(2,2,9) m=a: hand vs tool formula | 0.97222 | 0.97222 | 0 | 1e-12 | PASS | PASS
V1-qmean-PERT(2,2,9) m=a | mean PERT(2,2,9) m=a: hand vs integral of tool inverse-CDF | 3.1667 | 3.1667 | 8.7019e-09 | 0.0002 | PASS | PASS
V1-qvar-PERT(2,2,9) m=a | variance PERT(2,2,9) m=a: hand vs variance of tool inverse-CDF | 0.97222 | 0.97222 | 9.7099e-08 | 0.002 | PASS | PASS
V1-cdf-PERT(2,2,9) m=a | inverse-CDF round trip via independent CDF PERT(2,2,9) m=a | 0 | 2.7756e-16 | 2.7756e-16 | 1e-05 | PASS | PASS
V1-mean-PERT(2,9,9) m=b | mean PERT(2,9,9) m=b: hand vs tool formula | 7.8333 | 7.8333 | 0 | 1e-12 | PASS | PASS
V1-var-PERT(2,9,9) m=b | variance PERT(2,9,9) m=b: hand vs tool formula | 0.97222 | 0.97222 | 0 | 1e-12 | PASS | PASS
V1-qmean-PERT(2,9,9) m=b | mean PERT(2,9,9) m=b: hand vs integral of tool inverse-CDF | 7.8333 | 7.8333 | 8.7019e-09 | 0.0002 | PASS | PASS
V1-qvar-PERT(2,9,9) m=b | variance PERT(2,9,9) m=b: hand vs variance of tool inverse-CDF | 0.97222 | 0.97222 | 9.7099e-08 | 0.002 | PASS | PASS
V1-cdf-PERT(2,9,9) m=b | inverse-CDF round trip via independent CDF PERT(2,9,9) m=b | 0 | 1.3323e-15 | 1.3323e-15 | 1e-05 | PASS | PASS
V1-mean-Triangular(1,3,8) | mean Triangular(1,3,8): hand vs tool formula | 4 | 4 | 0 | 1e-12 | PASS | PASS
V1-var-Triangular(1,3,8) | variance Triangular(1,3,8): hand vs tool formula | 2.1667 | 2.1667 | 0 | 1e-12 | PASS | PASS
V1-qmean-Triangular(1,3,8) | mean Triangular(1,3,8): hand vs integral of tool inverse-CDF | 4 | 4 | 4.6809e-11 | 0.0002 | PASS | PASS
V1-qvar-Triangular(1,3,8) | variance Triangular(1,3,8): hand vs variance of tool inverse-CDF | 2.1667 | 2.1667 | 1.5016e-09 | 0.0043333 | PASS | PASS
V1-cdf-Triangular(1,3,8) | inverse-CDF round trip via independent CDF Triangular(1,3,8) | 0 | 2.7756e-16 | 2.7756e-16 | 1e-05 | PASS | PASS
V1-mean-Triangular(0,0,4) | mean Triangular(0,0,4): hand vs tool formula | 1.3333 | 1.3333 | 0 | 1e-12 | PASS | PASS
V1-var-Triangular(0,0,4) | variance Triangular(0,0,4): hand vs tool formula | 0.88889 | 0.88889 | 0 | 1e-12 | PASS | PASS
V1-qmean-Triangular(0,0,4) | mean Triangular(0,0,4): hand vs integral of tool inverse-CDF | 1.3333 | 1.3333 | 8.6088e-11 | 0.0002 | PASS | PASS
V1-qvar-Triangular(0,0,4) | variance Triangular(0,0,4): hand vs variance of tool inverse-CDF | 0.88889 | 0.88889 | 4.5914e-10 | 0.002 | PASS | PASS
V1-cdf-Triangular(0,0,4) | inverse-CDF round trip via independent CDF Triangular(0,0,4) | 0 | 1.6653e-16 | 1.6653e-16 | 1e-05 | PASS | PASS
V1-mean-Uniform(2,10) | mean Uniform(2,10): hand vs tool formula | 6 | 6 | 0 | 1e-12 | PASS | PASS
V1-var-Uniform(2,10) | variance Uniform(2,10): hand vs tool formula | 5.3333 | 5.3333 | 0 | 1e-12 | PASS | PASS
V1-qmean-Uniform(2,10) | mean Uniform(2,10): hand vs integral of tool inverse-CDF | 6 | 6 | 0 | 0.0002 | PASS | PASS
V1-qvar-Uniform(2,10) | variance Uniform(2,10): hand vs variance of tool inverse-CDF | 5.3333 | 5.3333 | 1.3332e-12 | 0.010667 | PASS | PASS
V1-cdf-Uniform(2,10) | inverse-CDF round trip via independent CDF Uniform(2,10) | 0 | 1.1102e-16 | 1.1102e-16 | 1e-05 | PASS | PASS
V1-mean-Fixed(4) | mean Fixed(4): hand vs tool formula | 4 | 4 | 0 | 1e-12 | PASS | PASS
V1-var-Fixed(4) | variance Fixed(4): hand vs tool formula | 0 | 0 | 0 | 1e-12 | PASS | PASS
V1-qmean-Fixed(4) | mean Fixed(4): hand vs integral of tool inverse-CDF | 4 | 4 | 0 | 0.0002 | PASS | PASS
V1-qvar-Fixed(4) | variance Fixed(4): hand vs variance of tool inverse-CDF | 0 | 0 | 0 | 0.002 | PASS | PASS
V1-cdf-Fixed(4) | inverse-CDF round trip via independent CDF Fixed(4) | 0 | 0 | 0 | 1e-05 | PASS | PASS
V2-mean-R-MAT | E[D¦occurs] R-MAT | 3.5 | 3.5 | 0 | 1e-12 | PASS | PASS
V2-emv-R-MAT | event EMV R-MAT (INR) | 14000 | 14000 | 0 | 1e-06 | PASS | PASS
V2-mean-R-LAB | E[D¦occurs] R-LAB | 2.5 | 2.5 | 0 | 1e-12 | PASS | PASS
V2-emv-R-LAB | event EMV R-LAB (INR) | 7000 | 7000 | 0 | 1e-06 | PASS | PASS
V2-mean-R-RWK | E[D¦occurs] R-RWK | 2.3333 | 2.3333 | 0 | 1e-12 | PASS | PASS
V2-emv-R-RWK | event EMV R-RWK (INR) | 4666.6667 | 4666.6667 | 0 | 1e-06 | PASS | PASS
V2-mean-R-WX | E[D¦occurs] R-WX | 2.6667 | 2.6667 | 0 | 1e-12 | PASS | PASS
V2-emv-R-WX | event EMV R-WX (INR) | 4266.6667 | 4266.6667 | 0 | 1e-06 | PASS | PASS
V2-mean-R-PLAN | E[D¦occurs] R-PLAN | 1.3333 | 1.3333 | 0 | 1e-12 | PASS | PASS
V2-emv-R-PLAN | event EMV R-PLAN (INR) | 1066.6667 | 1066.6667 | 0 | 1e-06 | PASS | PASS
V2-mean-R-SAFE | E[D¦occurs] R-SAFE | 2.5 | 2.5 | 0 | 1e-12 | PASS | PASS
V2-emv-R-SAFE | event EMV R-SAFE (INR) | 6000 | 6000 | 0 | 1e-06 | PASS | PASS
V2-mean-R-SKILL | E[D¦occurs] R-SKILL | 2.3333 | 2.3333 | 0 | 1e-12 | PASS | PASS
V2-emv-R-SKILL | event EMV R-SKILL (INR) | 4106.6667 | 4106.6667 | 0 | 1e-06 | PASS | PASS
V2-Edelay | expected total delay (days) | 5.1383 | 5.1383 | 0 | 1e-12 | PASS | PASS
V2-Var | variance of total delay | 10.7938 | 10.7938 | 0 | 1e-12 | PASS | PASS
V2-EMVsum | sum of event EMV (INR) | 41106.6667 | 41106.6667 | 0 | 1e-06 | PASS | PASS
V3-grid-mean | grid-convolution mean vs closed-form sum p*mu (validates the exact reference itself) | 5.1383 | 5.1383 | 2.6167e-07 | 0.002 | PASS | PASS
V3-grid-var | grid-convolution variance vs closed form (validates the exact reference itself) | 10.7938 | 10.7938 | 3.5478e-06 | 0.02 | PASS | PASS
V3-grid-p0 | P(no risk occurs) grid vs product(1-p) | 0.095823 | 0.095823 | 0 | 0.0005 | PASS | PASS | mass at zero also contains tiny mass of delays < H/2, so tolerance 5e-4
V3-TEC10-ACCEPT | total expected cost ACCEPT (n=10k), ¦diff¦ <= 4 SE | 50792.7375 | 50821.0481 | 28.3107 | 1547.0375 | PASS | PASS
V3-TEC200-ACCEPT | total expected cost ACCEPT (n=200k), ¦diff¦ <= 4 SE | 50792.7375 | 50960.9272 | 168.1897 | 341.4255 | PASS | PASS
V3-P90-ACCEPT | P90 duration ACCEPT (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 25.5677 | 25.5852 | 0.017524 | 0.047851 | PASS | PASS
V3-pexc-ACCEPT | P(duration > deadline) ACCEPT (n=200k), ¦diff¦ <= 4 SE | 0.60185 | 0.60408 | 0.0022238 | 0.0063742 | PASS | PASS
V3-Edel-ACCEPT | expected delay ACCEPT (n=200k) | 5.1383 | 5.1521 | 0.013759 | 0.06 | PASS | PASS
V3-TEC10-O-M-BUF | total expected cost O-M-BUF (n=10k), ¦diff¦ <= 4 SE | 45008.1783 | 44929.4269 | 78.7515 | 1364.7776 | PASS | PASS
V3-TEC200-O-M-BUF | total expected cost O-M-BUF (n=200k), ¦diff¦ <= 4 SE | 45008.1783 | 45197.6844 | 189.5061 | 303.4774 | PASS | PASS
V3-P90-O-M-BUF | P90 duration O-M-BUF (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.2336 | 24.2765 | 0.042929 | 0.04967 | PASS | PASS
V3-pexc-O-M-BUF | P(duration > deadline) O-M-BUF (n=200k), ¦diff¦ <= 4 SE | 0.463 | 0.4649 | 0.0018932 | 0.0064611 | PASS | PASS
V3-Edel-O-M-BUF | expected delay O-M-BUF (n=200k) | 4.0883 | 4.104 | 0.015668 | 0.06 | PASS | PASS
V3-TEC10-O-M-SUP | total expected cost O-M-SUP (n=10k), ¦diff¦ <= 4 SE | 47900.4579 | 48045.5098 | 145.0519 | 1490.5876 | PASS | PASS
V3-TEC200-O-M-SUP | total expected cost O-M-SUP (n=200k), ¦diff¦ <= 4 SE | 47900.4579 | 48083.1842 | 182.7263 | 327.2443 | PASS | PASS
V3-P90-O-M-SUP | P90 duration O-M-SUP (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.9806 | 25.0059 | 0.025326 | 0.048544 | PASS | PASS
V3-pexc-O-M-SUP | P(duration > deadline) O-M-SUP (n=200k), ¦diff¦ <= 4 SE | 0.53243 | 0.53509 | 0.0026635 | 0.0064611 | PASS | PASS
V3-Edel-O-M-SUP | expected delay O-M-SUP (n=200k) | 4.6133 | 4.6288 | 0.015457 | 0.06 | PASS | PASS
V3-TEC10-O-M-GANG | total expected cost O-M-GANG (n=10k), ¦diff¦ <= 4 SE | 57661.1539 | 57736.6198 | 75.4659 | 1472.8252 | PASS | PASS
V3-TEC200-O-M-GANG | total expected cost O-M-GANG (n=200k), ¦diff¦ <= 4 SE | 57661.1539 | 57817.0422 | 155.8884 | 323.3135 | PASS | PASS
V3-P90-O-M-GANG | P90 duration O-M-GANG (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 25.1951 | 25.2121 | 0.01701 | 0.04842 | PASS | PASS
V3-pexc-O-M-GANG | P(duration > deadline) O-M-GANG (n=200k), ¦diff¦ <= 4 SE | 0.58727 | 0.58889 | 0.0016159 | 0.0064009 | PASS | PASS
V3-Edel-O-M-GANG | expected delay O-M-GANG (n=200k) | 4.9717 | 4.9849 | 0.013193 | 0.06 | PASS | PASS
V3-TEC10-O-M-COV | total expected cost O-M-COV (n=10k), ¦diff¦ <= 4 SE | 50818.429 | 50770.295 | 48.134 | 1494.1649 | PASS | PASS
V3-TEC200-O-M-COV | total expected cost O-M-COV (n=200k), ¦diff¦ <= 4 SE | 50818.429 | 51012.5888 | 194.1598 | 331.1053 | PASS | PASS
V3-P90-O-M-COV | P90 duration O-M-COV (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 25.2603 | 25.2866 | 0.026267 | 0.050172 | PASS | PASS
V3-pexc-O-M-COV | P(duration > deadline) O-M-COV (n=200k), ¦diff¦ <= 4 SE | 0.57848 | 0.58088 | 0.0024037 | 0.0064132 | PASS | PASS
V3-Edel-O-M-COV | expected delay O-M-COV (n=200k) | 4.925 | 4.9409 | 0.015931 | 0.06 | PASS | PASS
V3-TEC10-O-M-QC | total expected cost O-M-QC (n=10k), ¦diff¦ <= 4 SE | 49623.9442 | 49518.3664 | 105.5778 | 1504.5492 | PASS | PASS
V3-TEC200-O-M-QC | total expected cost O-M-QC (n=200k), ¦diff¦ <= 4 SE | 49623.9442 | 49753.372 | 129.4278 | 332.1373 | PASS | PASS
V3-P90-O-M-QC | P90 duration O-M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 25.2619 | 25.2821 | 0.020177 | 0.049538 | PASS | PASS
V3-pexc-O-M-QC | P(duration > deadline) O-M-QC (n=200k), ¦diff¦ <= 4 SE | 0.57499 | 0.57646 | 0.0014643 | 0.0064195 | PASS | PASS
V3-Edel-O-M-QC | expected delay O-M-QC (n=200k) | 4.905 | 4.9153 | 0.010326 | 0.06 | PASS | PASS
V3-TEC10-O-M-BUF+M-GANG | total expected cost O-M-BUF+M-GANG (n=10k), ¦diff¦ <= 4 SE | 51944.3145 | 51932.5087 | 11.8058 | 1289.4815 | PASS | PASS
V3-TEC200-O-M-BUF+M-GANG | total expected cost O-M-BUF+M-GANG (n=200k), ¦diff¦ <= 4 SE | 51944.3145 | 52123.2195 | 178.9051 | 284.3052 | PASS | PASS
V3-P90-O-M-BUF+M-GANG | P90 duration O-M-BUF+M-GANG (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 23.8482 | 23.8876 | 0.039407 | 0.048489 | PASS | PASS
V3-pexc-O-M-BUF+M-GANG | P(duration > deadline) O-M-BUF+M-GANG (n=200k), ¦diff¦ <= 4 SE | 0.43849 | 0.44001 | 0.0015205 | 0.0064398 | PASS | PASS
V3-Edel-O-M-BUF+M-GANG | expected delay O-M-BUF+M-GANG (n=200k) | 3.9217 | 3.9368 | 0.015102 | 0.06 | PASS | PASS
V3-TEC10-O-M-BUF+M-COV | total expected cost O-M-BUF+M-COV (n=10k), ¦diff¦ <= 4 SE | 45163.1092 | 45023.4289 | 139.6803 | 1311.2444 | PASS | PASS
V3-TEC200-O-M-BUF+M-COV | total expected cost O-M-BUF+M-COV (n=200k), ¦diff¦ <= 4 SE | 45163.1092 | 45375.1415 | 212.0323 | 292.4838 | PASS | PASS
V3-P90-O-M-BUF+M-COV | P90 duration O-M-BUF+M-COV (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 23.9193 | 23.9679 | 0.048596 | 0.047728 | FAIL | FAIL
V3-pexc-O-M-BUF+M-COV | P(duration > deadline) O-M-BUF+M-COV (n=200k), ¦diff¦ <= 4 SE | 0.43439 | 0.43683 | 0.0024493 | 0.0064363 | PASS | PASS
V3-Edel-O-M-BUF+M-COV | expected delay O-M-BUF+M-COV (n=200k) | 3.875 | 3.8928 | 0.01784 | 0.06 | PASS | PASS
V3-TEC10-O-M-BUF+M-QC | total expected cost O-M-BUF+M-QC (n=10k), ¦diff¦ <= 4 SE | 43992.0951 | 43774.4452 | 217.6499 | 1319.5658 | PASS | PASS
V3-TEC200-O-M-BUF+M-QC | total expected cost O-M-BUF+M-QC (n=200k), ¦diff¦ <= 4 SE | 43992.0951 | 44143.4356 | 151.3405 | 293.8046 | PASS | PASS
V3-P90-O-M-BUF+M-QC | P90 duration O-M-BUF+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 23.9243 | 23.9753 | 0.051022 | 0.047463 | FAIL | FAIL
V3-pexc-O-M-BUF+M-QC | P(duration > deadline) O-M-BUF+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.43129 | 0.43241 | 0.0011213 | 0.0064311 | PASS | PASS
V3-Edel-O-M-BUF+M-QC | expected delay O-M-BUF+M-QC (n=200k) | 3.855 | 3.8672 | 0.012235 | 0.06 | PASS | PASS
V3-TEC10-O-M-SUP+M-GANG | total expected cost O-M-SUP+M-GANG (n=10k), ¦diff¦ <= 4 SE | 54802.7342 | 55002.7074 | 199.9732 | 1415.1464 | PASS | PASS
V3-TEC200-O-M-SUP+M-GANG | total expected cost O-M-SUP+M-GANG (n=200k), ¦diff¦ <= 4 SE | 54802.7342 | 54973.2552 | 170.521 | 308.8931 | PASS | PASS
V3-P90-O-M-SUP+M-GANG | P90 duration O-M-SUP+M-GANG (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.6093 | 24.631 | 0.021636 | 0.048902 | PASS | PASS
V3-pexc-O-M-SUP+M-GANG | P(duration > deadline) O-M-SUP+M-GANG (n=200k), ¦diff¦ <= 4 SE | 0.51288 | 0.51489 | 0.0020132 | 0.0064702 | PASS | PASS
V3-Edel-O-M-SUP+M-GANG | expected delay O-M-SUP+M-GANG (n=200k) | 4.4467 | 4.4616 | 0.01489 | 0.06 | PASS | PASS
V3-TEC10-O-M-SUP+M-COV | total expected cost O-M-SUP+M-COV (n=10k), ¦diff¦ <= 4 SE | 47990.7691 | 48072.5595 | 81.7904 | 1440.0665 | PASS | PASS
V3-TEC200-O-M-SUP+M-COV | total expected cost O-M-SUP+M-COV (n=200k), ¦diff¦ <= 4 SE | 47990.7691 | 48197.9074 | 207.1384 | 316.6431 | PASS | PASS
V3-P90-O-M-SUP+M-COV | P90 duration O-M-SUP+M-COV (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.6741 | 24.6957 | 0.021671 | 0.049473 | PASS | PASS
V3-pexc-O-M-SUP+M-COV | P(duration > deadline) O-M-SUP+M-COV (n=200k), ¦diff¦ <= 4 SE | 0.50643 | 0.50935 | 0.0029165 | 0.0064714 | PASS | PASS
V3-Edel-O-M-SUP+M-COV | expected delay O-M-SUP+M-COV (n=200k) | 4.4 | 4.4176 | 0.017628 | 0.06 | PASS | PASS
V3-TEC10-O-M-SUP+M-QC | total expected cost O-M-SUP+M-QC (n=10k), ¦diff¦ <= 4 SE | 46808.0196 | 46805.2802 | 2.7395 | 1445.4758 | PASS | PASS
V3-TEC200-O-M-SUP+M-QC | total expected cost O-M-SUP+M-QC (n=200k), ¦diff¦ <= 4 SE | 46808.0196 | 46951.9814 | 143.9617 | 317.801 | PASS | PASS
V3-P90-O-M-SUP+M-QC | P90 duration O-M-SUP+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.6759 | 24.7009 | 0.024917 | 0.049207 | PASS | PASS
V3-pexc-O-M-SUP+M-QC | P(duration > deadline) O-M-SUP+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.50314 | 0.50504 | 0.0019003 | 0.0064719 | PASS | PASS
V3-Edel-O-M-SUP+M-QC | expected delay O-M-SUP+M-QC (n=200k) | 4.38 | 4.392 | 0.012023 | 0.06 | PASS | PASS
V3-TEC10-O-M-GANG+M-COV | total expected cost O-M-GANG+M-COV (n=10k), ¦diff¦ <= 4 SE | 57696.2173 | 57700.1291 | 3.9118 | 1416.3357 | PASS | PASS
V3-TEC200-O-M-GANG+M-COV | total expected cost O-M-GANG+M-COV (n=200k), ¦diff¦ <= 4 SE | 57696.2173 | 57880.4858 | 184.2686 | 312.627 | PASS | PASS
V3-P90-O-M-GANG+M-COV | P90 duration O-M-GANG+M-COV (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.8825 | 24.9123 | 0.029801 | 0.047658 | PASS | PASS
V3-pexc-O-M-GANG+M-COV | P(duration > deadline) O-M-GANG+M-COV (n=200k), ¦diff¦ <= 4 SE | 0.56274 | 0.56446 | 0.0017294 | 0.0064348 | PASS | PASS
V3-Edel-O-M-GANG+M-COV | expected delay O-M-GANG+M-COV (n=200k) | 4.7583 | 4.7737 | 0.015365 | 0.06 | PASS | PASS
V3-TEC10-O-M-GANG+M-QC | total expected cost O-M-GANG+M-QC (n=10k), ¦diff¦ <= 4 SE | 56506 | 56444.8358 | 61.1642 | 1430.2098 | PASS | PASS
V3-TEC200-O-M-GANG+M-QC | total expected cost O-M-GANG+M-QC (n=200k), ¦diff¦ <= 4 SE | 56506 | 56622.4458 | 116.4458 | 313.6514 | PASS | PASS
V3-P90-O-M-GANG+M-QC | P90 duration O-M-GANG+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.8854 | 24.9135 | 0.028108 | 0.047891 | PASS | PASS
V3-pexc-O-M-GANG+M-QC | P(duration > deadline) O-M-GANG+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.55948 | 0.56031 | 0.00082527 | 0.0064395 | PASS | PASS
V3-Edel-O-M-GANG+M-QC | expected delay O-M-GANG+M-QC (n=200k) | 4.7383 | 4.7481 | 0.0097596 | 0.06 | PASS | PASS
V3-TEC10-O-M-COV+M-QC | total expected cost O-M-COV+M-QC (n=10k), ¦diff¦ <= 4 SE | 49674.0112 | 49490.8114 | 183.1998 | 1450.7443 | PASS | PASS
V3-TEC200-O-M-COV+M-QC | total expected cost O-M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 49674.0112 | 49828.7253 | 154.7141 | 321.6209 | PASS | PASS
V3-P90-O-M-COV+M-QC | P90 duration O-M-COV+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.9527 | 24.9861 | 0.033392 | 0.047124 | PASS | PASS
V3-pexc-O-M-COV+M-QC | P(duration > deadline) O-M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.55064 | 0.55244 | 0.0018048 | 0.0064475 | PASS | PASS
V3-Edel-O-M-COV+M-QC | expected delay O-M-COV+M-QC (n=200k) | 4.6917 | 4.7042 | 0.012497 | 0.06 | PASS | PASS
V3-TEC10-O-M-BUF+M-GANG+M-COV | total expected cost O-M-BUF+M-GANG+M-COV (n=10k), ¦diff¦ <= 4 SE | 52118.2341 | 52044.404 | 73.8301 | 1232.7941 | PASS | PASS
V3-TEC200-O-M-BUF+M-GANG+M-COV | total expected cost O-M-BUF+M-GANG+M-COV (n=200k), ¦diff¦ <= 4 SE | 52118.2341 | 52320.5678 | 202.3337 | 272.9489 | PASS | PASS
V3-P90-O-M-BUF+M-GANG+M-COV | P90 duration O-M-BUF+M-GANG+M-COV (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 23.5289 | 23.5619 | 0.033032 | 0.048154 | PASS | PASS
V3-pexc-O-M-BUF+M-GANG+M-COV | P(duration > deadline) O-M-BUF+M-GANG+M-COV (n=200k), ¦diff¦ <= 4 SE | 0.40812 | 0.41014 | 0.0020173 | 0.0063993 | PASS | PASS
V3-Edel-O-M-BUF+M-GANG+M-COV | expected delay O-M-BUF+M-GANG+M-COV (n=200k) | 3.7083 | 3.7256 | 0.017274 | 0.06 | PASS | PASS
V3-TEC10-O-M-BUF+M-GANG+M-QC | total expected cost O-M-BUF+M-GANG+M-QC (n=10k), ¦diff¦ <= 4 SE | 50955.1566 | 50810.9739 | 144.1827 | 1243.9969 | PASS | PASS
V3-TEC200-O-M-BUF+M-GANG+M-QC | total expected cost O-M-BUF+M-GANG+M-QC (n=200k), ¦diff¦ <= 4 SE | 50955.1566 | 51095.3876 | 140.231 | 274.2853 | PASS | PASS
V3-P90-O-M-BUF+M-GANG+M-QC | P90 duration O-M-BUF+M-GANG+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 23.5373 | 23.5831 | 0.045836 | 0.048701 | PASS | PASS
V3-pexc-O-M-BUF+M-GANG+M-QC | P(duration > deadline) O-M-BUF+M-GANG+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.40555 | 0.40608 | 0.00052886 | 0.0063925 | PASS | PASS
V3-Edel-O-M-BUF+M-GANG+M-QC | expected delay O-M-BUF+M-GANG+M-QC (n=200k) | 3.6883 | 3.7 | 0.011669 | 0.06 | PASS | PASS
V3-TEC10-O-M-BUF+M-COV+M-QC | total expected cost O-M-BUF+M-COV+M-QC (n=10k), ¦diff¦ <= 4 SE | 44179.8173 | 43904.591 | 275.2263 | 1265.3818 | PASS | PASS
V3-TEC200-O-M-BUF+M-COV+M-QC | total expected cost O-M-BUF+M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 44179.8173 | 44353.3251 | 173.5078 | 282.6647 | PASS | PASS
V3-P90-O-M-BUF+M-COV+M-QC | P90 duration O-M-BUF+M-COV+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 23.6077 | 23.647 | 0.039367 | 0.048521 | PASS | PASS
V3-pexc-O-M-BUF+M-COV+M-QC | P(duration > deadline) O-M-BUF+M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.40206 | 0.40393 | 0.0018758 | 0.0063888 | PASS | PASS
V3-Edel-O-M-BUF+M-COV+M-QC | expected delay O-M-BUF+M-COV+M-QC (n=200k) | 3.6417 | 3.6561 | 0.014406 | 0.06 | PASS | PASS
V3-TEC10-O-M-SUP+M-GANG+M-COV | total expected cost O-M-SUP+M-GANG+M-COV (n=10k), ¦diff¦ <= 4 SE | 54907.2257 | 55042.0925 | 134.8668 | 1361.6834 | PASS | PASS
V3-TEC200-O-M-SUP+M-GANG+M-COV | total expected cost O-M-SUP+M-GANG+M-COV (n=200k), ¦diff¦ <= 4 SE | 54907.2257 | 55104.1927 | 196.967 | 297.9348 | PASS | PASS
V3-P90-O-M-SUP+M-GANG+M-COV | P90 duration O-M-SUP+M-GANG+M-COV (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.2982 | 24.3237 | 0.025499 | 0.048696 | PASS | PASS
V3-pexc-O-M-SUP+M-GANG+M-COV | P(duration > deadline) O-M-SUP+M-GANG+M-COV (n=200k), ¦diff¦ <= 4 SE | 0.48543 | 0.48776 | 0.0023309 | 0.0064708 | PASS | PASS
V3-Edel-O-M-SUP+M-GANG+M-COV | expected delay O-M-SUP+M-GANG+M-COV (n=200k) | 4.2333 | 4.2504 | 0.017062 | 0.06 | PASS | PASS
V3-TEC10-O-M-SUP+M-GANG+M-QC | total expected cost O-M-SUP+M-GANG+M-QC (n=10k), ¦diff¦ <= 4 SE | 53730.5783 | 53786.0955 | 55.5172 | 1369.7226 | PASS | PASS
V3-TEC200-O-M-SUP+M-GANG+M-QC | total expected cost O-M-SUP+M-GANG+M-QC (n=200k), ¦diff¦ <= 4 SE | 53730.5783 | 53862.5876 | 132.0093 | 299.0945 | PASS | PASS
V3-P90-O-M-SUP+M-GANG+M-QC | P90 duration O-M-SUP+M-GANG+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.3017 | 24.3295 | 0.0278 | 0.048404 | PASS | PASS
V3-pexc-O-M-SUP+M-GANG+M-QC | P(duration > deadline) O-M-SUP+M-GANG+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.48252 | 0.48351 | 0.00098956 | 0.0064697 | PASS | PASS
V3-Edel-O-M-SUP+M-GANG+M-QC | expected delay O-M-SUP+M-GANG+M-QC (n=200k) | 4.2133 | 4.2248 | 0.011457 | 0.06 | PASS | PASS
V3-TEC10-O-M-SUP+M-COV+M-QC | total expected cost O-M-SUP+M-COV+M-QC (n=10k), ¦diff¦ <= 4 SE | 46926.9143 | 46862.8858 | 64.0284 | 1394.0924 | PASS | PASS
V3-TEC200-O-M-SUP+M-COV+M-QC | total expected cost O-M-SUP+M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 46926.9143 | 47094.8691 | 167.9549 | 307.0253 | PASS | PASS
V3-P90-O-M-SUP+M-COV+M-QC | P90 duration O-M-SUP+M-COV+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.3678 | 24.3963 | 0.028457 | 0.048375 | PASS | PASS
V3-pexc-O-M-SUP+M-COV+M-QC | P(duration > deadline) O-M-SUP+M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.47635 | 0.4787 | 0.0023578 | 0.0064681 | PASS | PASS
V3-Edel-O-M-SUP+M-COV+M-QC | expected delay O-M-SUP+M-COV+M-QC (n=200k) | 4.1667 | 4.1809 | 0.014194 | 0.06 | PASS | PASS
V3-TEC10-O-M-GANG+M-COV+M-QC | total expected cost O-M-GANG+M-COV+M-QC (n=10k), ¦diff¦ <= 4 SE | 56567.2973 | 56430.5766 | 136.7206 | 1372.763 | PASS | PASS
V3-TEC200-O-M-GANG+M-COV+M-QC | total expected cost O-M-GANG+M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 56567.2973 | 56711.5194 | 144.2221 | 302.7498 | PASS | PASS
V3-P90-O-M-GANG+M-COV+M-QC | P90 duration O-M-GANG+M-COV+M-QC (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 24.5707 | 24.5948 | 0.024119 | 0.045826 | PASS | PASS
V3-pexc-O-M-GANG+M-COV+M-QC | P(duration > deadline) O-M-GANG+M-COV+M-QC (n=200k), ¦diff¦ <= 4 SE | 0.53399 | 0.53511 | 0.0011128 | 0.0064611 | PASS | PASS
V3-Edel-O-M-GANG+M-COV+M-QC | expected delay O-M-GANG+M-COV+M-QC (n=200k) | 4.525 | 4.5369 | 0.011931 | 0.06 | PASS | PASS
V3-TEC10-O-M-MECH | total expected cost O-M-MECH (n=10k), ¦diff¦ <= 4 SE | 51580.1244 | 51554.9161 | 25.2084 | 1485.8293 | PASS | PASS
V3-TEC200-O-M-MECH | total expected cost O-M-MECH (n=200k), ¦diff¦ <= 4 SE | 51580.1244 | 51760.5689 | 180.4445 | 329.4871 | PASS | PASS
V3-P90-O-M-MECH | P90 duration O-M-MECH (n=200k): hand inside tool 95% CI (+0.02 d grid slack) | 25.1895 | 25.2149 | 0.025383 | 0.046406 | PASS | PASS
V3-pexc-O-M-MECH | P(duration > deadline) O-M-MECH (n=200k), ¦diff¦ <= 4 SE | 0.56996 | 0.57252 | 0.0025606 | 0.0064248 | PASS | PASS
V3-Edel-O-M-MECH | expected delay O-M-MECH (n=200k) | 4.8583 | 4.8733 | 0.014966 | 0.06 | PASS | PASS
V3-seed2024 | second seed n=200k: all ¦z¦ of TEC vs exact <= 4 | 0 | 1.0383 | 1.0383 | 4 | PASS | PASS
V3-decision | preferred option by hand == tool (n=200k) | 0 | 0 | 0 | 0 | PASS | PASS | hand O-M-BUF+M-QC / tool O-M-BUF+M-QC
V4-net-M-BUF | net benefit M-BUF (INR) | 2400 | 2400 | 0 | 1e-06 | PASS | PASS
V4-be-M-BUF | break-even required reduction M-BUF | 0.42857 | 0.42857 | 0 | 1e-12 | PASS | PASS
V4-pmax-M-BUF | max p-after that still pays M-BUF | 0.28571 | 0.28571 | 0 | 1e-12 | PASS | PASS
V4-net-M-SUP | net benefit M-SUP (INR) | 1200 | 1200 | 0 | 1e-06 | PASS | PASS
V4-be-M-SUP | break-even required reduction M-SUP | 0.21429 | 0.21429 | 0 | 1e-12 | PASS | PASS
V4-pmax-M-SUP | max p-after that still pays M-SUP | 0.39286 | 0.39286 | 0 | 1e-12 | PASS | PASS
V4-net-M-GANG | net benefit M-GANG (INR) | -7666.6667 | -7666.6667 | 0 | 1e-06 | PASS | PASS
V4-be-M-GANG | break-even required reduction M-GANG | 1.2857 | 1.2857 | 0 | 1e-12 | PASS | PASS
V4-net-M-COV | net benefit M-COV (INR) | -793.3333 | -793.3333 | 0 | 1e-06 | PASS | PASS
V4-be-M-COV | break-even required reduction M-COV | 0.58594 | 0.58594 | 0 | 1e-12 | PASS | PASS
V4-pmax-M-COV | max p-after that still pays M-COV | 0.082812 | 0.082812 | 0 | 1e-12 | PASS | PASS
V4-net-M-QC | net benefit M-QC (INR) | 366.6667 | 366.6667 | 0 | 1e-06 | PASS | PASS
V4-be-M-QC | break-even required reduction M-QC | 0.32143 | 0.32143 | 0 | 1e-12 | PASS | PASS
V4-pmax-M-QC | max p-after that still pays M-QC | 0.16964 | 0.16964 | 0 | 1e-12 | PASS | PASS
V4-net-M-MECH | net benefit M-MECH (INR) | -1760 | -1760 | 0 | 1e-06 | PASS | PASS
V4-be-M-MECH | break-even required reduction M-MECH | 0.97403 | 0.97403 | 0 | 1e-12 | PASS | PASS
V4-pmax-M-MECH | max p-after that still pays M-MECH | 0.0057143 | 0.0057143 | 0 | 1e-12 | PASS | PASS
V5-example | example risks: hand class/score/level == tool (count of mismatches) | 0 | 0 | 0 | 0 | PASS | PASS
V5-level25 | all 25 (p-class x impact-class) cells: level hand == tool (mismatches) | 0 | 0 | 0 | 0 | PASS | PASS
V5-pclass | p-class on 20010 values incl. exact edges: mismatches | 0 | 0 | 0 | 0 | PASS | PASS
V5-iclass | impact-class on 20004 values incl. exact edges: mismatches | 0 | 0 | 0 | 0 | PASS | PASS
V5-trap | ratios exactly on the 4 impact edges (0.32,0.8,1.6,3.2 d on 16 d) -> classes 2,3,4,5 | 0 | 0 | 0 | 0 | PASS | PASS | got (2, 3, 4, 5)
V6-fired | set of fired rules identical (symmetric difference size) | 0 | 0 | 0 | 0 | PASS | PASS
V6-levels | per-risk resolved level identical (mismatches) | 0 | 0 | 0 | 0 | PASS | PASS
V6-spot-RL-LAB | required_workers 6 > available_workers 5 -> fires | 1 | 1 | 0 | 0 | PASS | PASS
V6-spot-RL-MAT | stock 2 d <= lead 6 d -> fires | 1 | 1 | 0 | 0 | PASS | PASS
V7-seed | seed rank / mean RII / class for 30 seeded risks: mismatches | 0 | 0 | 0 | 0 | PASS | PASS | []
V7-cap | elevated flag raises probability class by 1, capped at 5 (top-ranked stays 5) | 5 | 5 | 0 | 0 | PASS | PASS
V7-raise | elevated flag on lowest class raises p-class 1->2, impact class unchanged | 2 | 2 | 0 | 0 | PASS | PASS
V7-noflag | no flag: p-class == impact-class == tier | 1 | 1 | 0 | 0 | PASS | PASS
V8-lin | linear model M03: 34.36 - 1.71*5 = 25.81 m2/day (crew of 2) | 25.81 | 25.81 | 0 | 1e-12 | PASS | PASS
V8-lin3 | linear model P1-01: 0.53 - 0.08*3 + 0.4*2 + 0.36*4 = 2.53 m2/hour/worker | 2.53 | 2.53 | 0 | 1e-12 | PASS | PASS
V8-crew | M03 scaled to a crew of 4 (linear): 25.81/2*4 = 51.62 m2/day | 51.62 | 51.62 | 0 | 1e-09 | PASS | PASS
V8-hours | P1-01: m2/hour/worker * 8 h * 3 workers | 60.72 | 60.72 | 0 | 1e-09 | PASS | PASS
V8-t0 | baseline mode = 1000/(2*25) = 20 d | 20 | 20 | 0 | 1e-12 | PASS | PASS
V8-tmin | baseline min = 1000/(2*30) | 16.6667 | 16.6667 | 0 | 1e-12 | PASS | PASS
V8-tmax | baseline max = 1000/(2*20) | 25 | 25 | 0 | 1e-12 | PASS | PASS
V8-is7272 | IS 7272 1-brick: 6 masons / 0.94 mason-days per m3 = 6.383 m3/day | 6.383 | 6.383 | 0 | 1e-12 | PASS | PASS
V8-cpwd | CPWD superstructure: 6 masons / (0.47+0.47) = 6.383 m3/day | 6.383 | 6.383 | 0 | 1e-12 | PASS | PASS
V8-support | required mazdoor for 6 masons = 6*1.8/0.94 = 11.489 | 11.4894 | 11.4894 | 0 | 1e-12 | PASS | PASS
V9-zmean | mean of z-scores of E[delay] over 200 seeds is ~0 (¦avg¦ <= 0.30 ~ 4 SE) | 0 | -0.03698 | 0.03698 | 0.3 | PASS | PASS
V9-zsd | sd of z-scores of E[delay] ~ 1 (reported standard error is honest) | 1 | 1.0368 | 0.036838 | 0.2 | PASS | PASS
V9-cov | 95% CI coverage of the analytic mean over 200 seeds (92%..98%) | 0.95 | 0.935 | 0.015 | 0.035 | PASS | PASS
V9-covp90 | P90 CI coverage of the exact P90 over 200 seeds (>= 90%) | 0.95 | 0.925 | 0.025 | 0.05 | PASS | PASS
V9-pany | mean z of P(any delay) ~ 0 | 0 | 0.021063 | 0.021063 | 0.3 | PASS | PASS
V10-joint--0.5 | P(A and B) at rho=-0.5: bivariate-normal CDF vs tool, 4 SE | 0.053485 | 0.053298 | 0.0001862 | 0.0012619 | PASS | PASS
V10-margA--0.5 | marginal P(A)=0.40 preserved at rho=-0.5 | 0.4 | 0.39916 | 0.00084333 | 0.0025298 | PASS | PASS
V10-joint-0.0 | P(A and B) at rho=0.0: bivariate-normal CDF vs tool, 4 SE | 0.12 | 0.12008 | 7.6667e-05 | 0.0017781 | PASS | PASS
V10-margA-0.0 | marginal P(A)=0.40 preserved at rho=0.0 | 0.4 | 0.39916 | 0.00084333 | 0.0025298 | PASS | PASS
V10-joint-0.6 | P(A and B) at rho=0.6: bivariate-normal CDF vs tool, 4 SE | 0.2085 | 0.20837 | 0.00013224 | 0.0021978 | PASS | PASS
V10-margA-0.6 | marginal P(A)=0.40 preserved at rho=0.6 | 0.4 | 0.39916 | 0.00084333 | 0.0025298 | PASS | PASS
V10-joint-0.95 | P(A and B) at rho=0.95: bivariate-normal CDF vs tool, 4 SE | 0.28722 | 0.28687 | 0.00035054 | 0.0024365 | PASS | PASS
V10-margA-0.95 | marginal P(A)=0.40 preserved at rho=0.95 | 0.4 | 0.39916 | 0.00084333 | 0.0025298 | PASS | PASS
V11-ex1 | examples/example_case.json equals service.example_case() | 1 | 1 | 0 | 0 | PASS | PASS
V11-ex2 | examples/example_analysis_case.json equals example_analysis_case() | 1 | 0 | 1 | 0 | FAIL | FAIL

## Test_Summary
Test summary, 9 October 2026
Test set | Checks | Passed before fixes | Passed after fixes | Failed after | Cause of remaining failures
Hand and exact calculation | 242 | 239 | 240 | 2 | Two P90 differences of 0.049 and 0.051 d at n=200,000: sampling noise
CLI, API, front end, packaging flows | 86 | 79 | 85 | 1 | One wrong expectation in the test script (run on a case without a cost model exits 0 by design)
Edge cases, wrong-shape inputs, performance | 85 | 68 | 83 | 2 | Two wrong expectations in the test script (lambda = 0 is correctly rejected; truncation notice is in the report)
Total | 413 | 386 | 408 | 5
Other test sets | Size | Before fixes | After fixes |  | Note
Fuzzing, mutated inputs | 7700 | 12 unhandled errors | 0 unhandled |  | 4,000 register + 3,000 analysis-case + 700 run_analysis mutations
Invariants on random valid cases | 140 | 140 held | 140 held |  | No valid case rejected
Repository test suite | 557 | 522 passed, 3 skipped (of 525) | 554 passed, 3 skipped |  | 32 new regression tests in tests/test_validation_fixes.py; 3 skipped need a database not built here
Finding | Severity | Where | What happened | Fix | Status
F1 | Medium | app/cli.py, analyze | Bad case file ended in a traceback (6 of 6 file types) | Same loader and error handling as run | Fixed, tested
F2 | Medium | app/analysis.py | Wrong-type containers crashed (14 of 19 shapes) | Type-check each container, report a case problem | Fixed, tested
F3 | Low | app/analysis.py, decision.py:96 | Mixed-type evidence ids failed when sorted | Convert ids to text | Fixed, tested
F4 | Low | simulation.py, convergence() | Empty checkpoints for n < 10; n = 1 crashed | At least one draw per checkpoint | Fixed, tested
F5 | Low | simulation.py, simulate() | Two ids with equal CRC32 share a random stream | Refuse and ask for a rename (hash unchanged) | Fixed, tested
F6 | Low | examples/example_analysis_case.json | File differed from the generator function | Regenerated; test compares them | Fixed, tested
F7 | Info | app/engine/options.py | Automatic search stops at 3 responses and 40 options | Document in the GUI | Open
Not verified: the PySide6 window and Windows executables (PySide6 not installable here), the browser UI operated by a person, LLM-assisted risk suggestions (no key), line coverage.
Source: report/scripts/validation_2026-10-09/ (first-run and after_fixes outputs). Counts typed from those outputs.