## README
Manual check of the tool's calculations
Case | ILLUSTRATIVE analysis example. Activity: Brick masonry, ground-floor walls.
What this is | Closed-form quantities recomputed by hand as live Excel formulas from the inputs on the Inputs sheet, beside the number the tool printed, with a difference and a PASS / FAIL formula. If you change a blue input, the hand column recomputes but the pasted tool column does not, so differences will then appear.
Checked here | Delay moments by distribution kind; event EMV = p x (mean delay x delay cost + direct cost); 5 x 5 class and level; net benefit of each response (EMV removed - secondary EMV - cost); expected total delay and probability of any delay against the simulation (within 3 standard errors).
NOT checked here | Simulated duration and cost percentiles (P50, P90), liquidated-damage costs, and the option comparison need the full distribution. They are checked by the validation scripts in report/scripts/validation_2026-10-09/ (exact grid convolution and a large independent simulation).
Occurrence correlation | No occurrence correlation was entered; the independence formulas apply.
Colour legend | Blue on yellow = input. Blue on white = value pasted from the tool. Black = formula. Green = link to another sheet.
Not evidence | A PASS shows the arithmetic is right, not that the entered probabilities, delays and costs describe a real site.
Tool run | n = 10000, seed = 12345, criterion = min_expected_total_cost.
Overall | ALL 23 CHECKS PASS

## Inputs
Inputs (from the case)
Quantity | Value | Unit
Planned duration T0 | 16 | days
Deadline | 20 | days (blank = none)
Delay cost per day Cd | 8000 | INR per day
Liquidated damages per day | 5000 | INR per day (not used in these checks)
Simulation draws n | 10000 | draws
Seed | 12345
Risk id | Name | Delay kind | a (min) | m (mode) | b (max) | lambda | p | Direct cost if it occurs
R-MAT | Brick / material shortage | pert | 1 | 3 | 8 | 4 | 0.5 | 0
R-LAB | Labour absenteeism / shortage | pert | 1 | 2 | 6 | 4 | 0.35 | 0
R-RWK | Rework due to workmanship | pert | 1 | 2 | 5 | 4 | 0.25 | 0
R-WX | Rain / monsoon stoppage | pert | 1 | 2 | 7 | 4 | 0.2 | 0
R-PLAN | Poor planning or unrealistic scheduling | pert | 1 | 1 | 3 | 4 | 0.1 | 0
R-SAFE | Unsafe conditions / work at height | pert | 1 | 2 | 6 | 4 | 0.3 | 0
R-SKILL | Unskilled or unqualified labour | pert | 1 | 2 | 5 | 4 | 0.22 | 0
Response id | Targets risk | Cost | p after | Delay-after kind | a | m | b | lambda | Feasible?
M-BUF | R-MAT | 6000 | 0.2 | [5 empty] | Yes
M-SUP | R-MAT | 3000 | 0.35 | [5 empty] | Yes
M-GANG | R-LAB | 9000 |  | pert | 0 | 1 | 3 | 4 | Yes
M-COV | R-WX | 2500 | 0.12 | [5 empty] | Yes
M-QC | R-RWK | 1500 | 0.15 | [5 empty] | Yes
M-MECH | R-SKILL | 4000 | 0.1 | [5 empty] | No
Response id | Secondary risk id | p | Delay kind | a | m | b | lambda | Direct cost
M-GANG | S-CONG | 0.3 | pert | 0 | 1 | 2 | 4 | 0
Probability class edges (lower-edge inclusive) | 0.2 | 0.4 | 0.6 | 0.8
Impact edges (fraction of T0) | 0.02 | 0.05 | 0.1 | 0.2
Level cut-offs on score (Low <=, Moderate <=, High <=) | 5 | 10 | 15

## Risks
Per-risk moments and event EMV: hand vs tool
Risk id | p | Mean delay if it occurs (d) | Variance (d^2) | Conditional cost =mean x Cd + direct | Event EMV =p x conditional cost | Tool mean (d) | Tool EMV | Mean diff | EMV diff | Result | 1 - p
R-MAT | 0.5 | 3.5 | 1.6071 | 28000 | 14000 | 3.5 | 14000 | 0 | 0 | PASS | 0.5
R-LAB | 0.35 | 2.5 | 0.75 | 20000 | 7000 | 2.5 | 7000 | 0 | 0 | PASS | 0.65
R-RWK | 0.25 | 2.3333 | 0.50794 | 18666.6667 | 4666.6667 | 2.3333 | 4666.6667 | 0 | 0 | PASS | 0.75
R-WX | 0.2 | 2.6667 | 1.0317 | 21333.3333 | 4266.6667 | 2.6667 | 4266.6667 | 0 | 0 | PASS | 0.8
R-PLAN | 0.1 | 1.3333 | 0.079365 | 10666.6667 | 1066.6667 | 1.3333 | 1066.6667 | 0 | 0 | PASS | 0.9
R-SAFE | 0.3 | 2.5 | 0.75 | 20000 | 6000 | 2.5 | 6000 | 0 | 0 | PASS | 0.7
R-SKILL | 0.22 | 2.3333 | 0.50794 | 18666.6667 | 4106.6667 | 2.3333 | 4106.6667 | 0 | 0 | PASS | 0.78

## Totals
Expected total delay and probability of any delay: hand vs simulation
Quantity | Hand (formula) | Tool (simulated) | Difference | Tolerance (3 standard errors) | Result
Expected total delay (d) = sum of p x mean | 5.1383 | 5.1323 | 0.0060485 | 0.10023 | PASS
Probability of any delay = 1 - product(1 - p) | 0.90418 | 0.8975 | 0.006677 | 0.0088305 | PASS
Sum of event EMV (cost units) | 41106.6667 | 41106.6667 | 0 | 0.041108 | PASS
Tolerance for the first two rows uses the tool's own standard error of the mean and the binomial standard error at the number of draws used. A simulation will miss its exact value by more than 3 standard errors about 3 times in 1,000.

## Matrix
5 x 5 class and level: hand vs tool
Risk id | p | Mean delay (d) | Ratio = mean / T0 | Probability class | Impact class | Score | Level | Tool p class | Tool impact class | Tool score | Tool level | Result
R-MAT | 0.5 | 3.5 | 0.21875 | 3 | 5 | 15 | High | 3 | 5 | 15 | High | PASS
R-LAB | 0.35 | 2.5 | 0.15625 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-RWK | 0.25 | 2.3333 | 0.14583 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-WX | 0.2 | 2.6667 | 0.16667 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-PLAN | 0.1 | 1.3333 | 0.083333 | 1 | 3 | 3 | Low | 1 | 3 | 3 | Low | PASS
R-SAFE | 0.3 | 2.5 | 0.15625 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS
R-SKILL | 0.22 | 2.3333 | 0.14583 | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | PASS

## Responses
Net benefit of each response: hand vs tool (this response alone, analytic, linear cost)
Response | Targets | EMV before | p after (or original p) | Mean delay after (d) | Direct cost | EMV after | Secondary EMV | Cost | Net benefit =before - after - secondary - cost | Break-even: cost / EMV before | Feasible? | Tool EMV before | Tool EMV after | Tool secondary | Tool net | Net diff | Result
M-BUF | R-MAT | 14000 | 0.2 | 3.5 | 0 | 5600 | 0 | 6000 | 2400 | 0.42857 | Yes | 14000 | 5600 | 0 | 2400 | 0 | PASS
M-SUP | R-MAT | 14000 | 0.35 | 3.5 | 0 | 9800 | 0 | 3000 | 1200 | 0.21429 | Yes | 14000 | 9800 | 0 | 1200 | 0 | PASS
M-GANG | R-LAB | 7000 | 0.35 | 1.1667 | 0 | 3266.6667 | 2400 | 9000 | -7666.6667 | 1.2857 | Yes | 7000 | 3266.6667 | 2400 | -7666.6667 | 0 | PASS
M-COV | R-WX | 4266.6667 | 0.12 | 2.6667 | 0 | 2560 | 0 | 2500 | -793.3333 | 0.58594 | Yes | 4266.6667 | 2560 | 0 | -793.3333 | 0 | PASS
M-QC | R-RWK | 4666.6667 | 0.15 | 2.3333 | 0 | 2800 | 0 | 1500 | 366.6667 | 0.32143 | Yes | 4666.6667 | 2800 | 0 | 366.6667 | 0 | PASS
M-MECH | R-SKILL | 4106.6667 | 0.1 | 2.3333 | 0 | 1866.6667 | 0 | 4000 | -1760 | 0.97403 | No | 4106.6667 | 1866.6667 | 0 | -1760 | 0 | PASS
Secondary risks created by a response (hand EMV = p x (mean x Cd + direct cost))
Response | Secondary risk | p | Mean delay (d) | EMV
M-GANG | S-CONG | 0.3 | 1 | 2400