## Slide 1
Bricks-ly
Delay-risk identification, register and matrix for one brick-masonry activity
Progress report | 14 October 2026 | B.Tech civil engineering final-year project
Notes: Opening. One sentence: Bricks-ly helps a site engineer list, rank and review the delay risks of a single brick-masonry activity. Today: where the project stands, what the audit found and fixed, what the tool can and cannot claim, and the next test against real site data.

## Slide 2: Where we stand
46 + 22
risks in the library and site-fact rules that flag them
182
published survey values from 11 studies feed the starting ranking
600
automated tests pass (553 before this round)
The tool prioritises risks on an ordinal scale. It does not predict days of delay, and it has not yet been tested against site data.
Source: data/ files and test run, 2026-10-13
Notes: Three numbers. 46 risks and 22 rules are the library and rule base. 182 rows from 11 published surveys are the literature starting point. 600 tests pass in the cloud copy after this round; the local run had 556 collected before. Say the limit out loud: ordinal prioritisation, not a prediction, and no site comparison yet.

## Slide 3: What the tool does
1 Identify
Risk library of 46, site-fact rules, evidence-cited suggestions
2 Register
Probability and delay range per risk, each with a Source label
3 Matrix
5x5 probability-impact matrix; level = class x class
4 Export
report.html, matrix png/svg, register md/csv, case JSON
Ordinal prioritisation only. Matrix levels are labels, not quantities. Risks without entered numbers sit at a labelled literature tier (Assumption), never at a made-up probability.
Notes: Walk the four steps left to right. Stress the rule that every number shown was entered with a Source, and that tool-supplied placements are labelled as an Assumption.

## Slide 4: The evidence behind the ranking
11
published surveys; 5 serve as the seed
30 of 46
risks get a starting tier from survey rankings
16
risks have no survey value and need your numbers
14 of 30
seeded risks rest on a single study
How to read it
A relative importance index measures how important respondents rated a factor, not how likely it is or how many days it costs.
Ranks 12 and 13 differ by 0.0008 RII, so neighbouring ranks are not reliably ordered.
Agreement with held-out surveys is weak: none of three tests survives correction for multiple testing.
Source: data/literature_seed.json; docs/refine_round_1/lead_D.md; Handoff section 8
Notes: This is the honest evidence slide. The seed is a starting position, not a probability. Two facts a reviewer may probe: 14 of the 30 seeded risks come from one study only, and rank 12 versus 13 differ by 0.0008. Agreement with the held-out surveys was weak and none of three tests survived correction (Holm).

## Slide 5: Independent audit: 140 findings
Chart: Findings by area (round 1)
| GUI and usability | Engine, API, error paths, tests | Research data and scripts | Documents and numbers
Findings | 48 | 35 | 31 | 26
Every finding was triaged
Fix now, with a test or command
Owner decision (scope, deleting, seed values)
Needs local data (database, PDFs)
Rejected, with the reason
Agent output counted as a claim until a command or a file confirmed it.
Source: docs/refine_round_1/ (lead_A, A2_error_path, lead_B, lead_C, lead_D, triage)
Notes: Four audit leads plus an error-path audit reviewed engine, GUI, data and documents: 15 + 20 + 48 + 31 + 26 = 140 findings. Each was triaged; worker claims were not trusted until reproduced. Several were re-run by hand before fixing.

## Slide 6: What we fixed
Engine guards
Matrix rejects true/false, NaN, unsorted edges and negative delay instead of returning a class.
Input validation
Plain ASCII decimals only; anything above 1e12 or non-finite is rejected with the field name.
Repeatable output
Output changed between runs because a set was iterated in hash order. Now identical across seeds.
Usable on a phone
Sideways scroll at 375 px fell from 509 px to none; keyboard focus and screen-reader names added.
Source: pull request #1; tests/test_round1_hardening.py (76 tests)
Notes: Pick the repeatable-output item to explain: it is the kind of quiet variation that makes a tool look unreliable in a demo. It was found by the root reviewer, not by the audits.

## Slide 7: Clean-up and outlier control
Removed (nothing used it)
6 retired GUI screens
Unused productivity-prediction package and its tests
Unused LLM narrative path (a route for invented numbers, with no caller)
Duplicate scenarios folder, generated output, empty files
Kept: decision layer (Monte Carlo, EMV) pending a scope decision
Controls against bad data
Data check over 46 risks, 22 rules, 182 seed rows, 13 catalogue entries: no dangling ids, no value outside (0, 1], no rank contradicting its value
Warning when a delay exceeds 5x the activity duration (hours entered as days)
AI suggestions: no numbers accepted; empty or uncited quotes flagged
No seed value was edited
Source: docs/Project_Audit_2026-10-13.md; scripts/check_data.py
Notes: The tool never invents a probability, delay or cost: entered numbers carry a Source, and tool placements are labelled. This slide shows how the remaining entry points for bad numbers were narrowed. The removal is one commit and can be reverted.

## Slide 8: Quality, measured
553 > 600
tests passing (3 skipped without local data)
509 > 0 px
sideways scroll on a phone-width screen
Identical
outputs across three Python hash seeds
Static checks (flake8) are clean on app, gui and tests apart from one unused import in a legacy test. Each fix has a test or a command that shows it.
Source: pytest, scripts/golden_hash.py, scripts/gui_layout_check.py, run 2026-10-13
Notes: These are measured numbers from commands run this week, not estimates. Say plainly that passing tests show the code does what we wrote, not that the method is right: that is what the site comparison is for.

## Slide 9: What we cannot claim yet
No site test yet
All outputs rest on literature rankings and entered assumptions.
Thin literature base
14 of 30 seeded risks rest on one study; neighbouring ranks are nearly tied.
Corpus figures disagree
Reports quote different record counts; 761 works await review.
Survey not run
No expert survey yet; factor-to-risk mapping has one coder.
Source: Project_Audit_2026-10-13.md; lead_D.md
Notes: State these before anyone asks. They are the reason the next step is a comparison against real data.

## Slide 10: Next: test against site data
Planned, not started. The baseline will be a real schedule from one site, exported from MS Project or Primavera.
1
Obtain
Planned vs actual dates and the delay log, anonymised, with the site's permission
2
Map
Code each logged delay cause to a library risk; two coders, agreement reported
3
Compare
Run the tool on the same activity; compare its ranking and flags with what happened
4
Report
State agreement with its uncertainty; no claim of validation
Notes: This is the main point of the next phase. Everything so far shows the tool is built carefully; this shows whether it helps. The data source is a site schedule from MS Project or Primavera P6. It is a plan: no site data has been received yet.

## Slide 11: How the comparison will work
Question | Proposed method | Reported as
Does the tool's risk ranking match what delayed the site? | Rank agreement (Spearman) against observed delay days per cause; permutation p-value with correction | Agreement with its uncertainty and n
Do the rule flags coincide with real events? | Count flagged risks that appear in the delay log, and logged causes the rules missed | Hits and misses, listed
Do site numbers give sensible levels? | Re-run with p and delay taken from the schedule; compare matrix levels with the actual slip | Before and after matrix
Proposed protocol; the statistical method is an open decision for the supervisor. Needs: the schedule file, permission, and a second coder.
Notes: Be clear this is a proposal. The method choices (rank agreement, permutation p-value, correction for multiple tests) follow what the project already uses for the literature check, but the supervisor should confirm. What we will not say afterwards: validated, or predicts.

## Slide 12: Decisions we need
Scope
Keep the cost and decision layer, or limit to identify, register, matrix? The official title describes a larger scope.
Site data
Which site, which schedule export, and permission to use it.
Corpus figure
One agreed record count for all reports, after the pending review.
Old documents
Regenerate or retire Word files that still carry withdrawn wording.
Full list of open decisions: docs/refine_round_1/lead_D.md
Notes: Close on the asks. The scope question and the site data are the two that change the plan most.